## DDR#173
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 173
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4692.2 | 4692.2 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 172.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4693 | 4693 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-10-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 32 |  | BHA NO. |  |  | 33 | IN (M) |  | 4692.2 |  | OUT (M) |  |  | STRING (BBL) | 185.6
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 18 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 812.1
DEPTH, MD (M) | 4692.2 | 4692.2 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.3 | 0.073 |  | PITS (BBL) | 463
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | HALLIBURTON |  | BIT SUB |  |  | 6.75 | 3 |  | 4 1/2 IF |  | 1.07 | 0.14064 |  | ACT. SYS (BBL) | 1460.7
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MMD65DH |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.34 | 1.2277 |  | RESV. SYS (BBL) | 1698
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 13223626 |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.78 | 0.23397 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | M424 |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.24 | 1.2145 |  | KILL MW (SG)
µ FUNNEL (SEC) | 61 | 61 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6 x 13/32 |  | ST. STAB |  |  | 8.375 | 2.75 |  | 4 1/2 IF |  | 1.4 | 0.18402 |  | TOTAL | 3158.7
PV | 42 | 43 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4692.2 |  | PBL SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 3.48 | 0.45742 |  | DIESEL (LTR)
YIELD POINT | 25 | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 13 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 120.15 | 15.7928 |  | RIG TANK | 136851
GEL ST. | 10/15 | 11/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.7 | 1.275 |  | CAMP TANK | 22795
WL (ml/30 min) | 4.1 | 4.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 3 x DC |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 27.16 | 3.57 |  | CONSUMED | 3516
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.19 | 8.2315 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 159646
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 70000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 113400
KCl (mg/l) | 57201 | 57201 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 133400
CHLORIDES (mg/l) | 29000 | 29000 | 5" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 520000
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS |  | STAB - 3 |  | TFA (IN²) |  |  | 0.778 | [12 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 295.81 |  |  | MPCL | 5
OIL % | 0.5 | 0.5 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 16
SOLIDS % | 32.85 | 32.85 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 73782.1633 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13662303.015 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 68.63% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1945.7226
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4680 | 545/550 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4680 | 725/735 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4680 | 900/895 |  |  | CHINJI | 338/338
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI | 4576/4576
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR | 4667/4667
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43761 | 43761.0833 | 2 | DRL | PT-P | COR / BHA | POOH CORING BHA FROM 302M TO SURFACE. L/D JAR & PBL SUB.
43761.0833 | 43761.1354 | 1.25 | DRL | PT-P | COR / BHA | HELD PJSM. HANDLED CORE BARREL AT SURFACE. BROKE OUT & L/D INNER BARREL ALONG WITH CORE. SOFT BROKE OUTER BARREL CONNECTIONS. L/D CORE HEAD.
43761.1354 | 43761.3438 | 5 | DRL | PT-P | BOPT | HELD PJSM. M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING. RIH 2x5" DP STDS. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/TESTED ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), LOWER PIPE RAMS, BLIND RAMS, KILL LINE NRV, HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. INSTALLED WEAR BUSHING & L/D PLUG ASSY.
43761.3438 | 43761.4688 | 3 | DRL | PT-P | BHA | L/DOWN 18x 6 1/2" DC & 12x 5" HWDP SINGLE BY SINGLE FOR INSPECTION.
43761.4688 | 43761.4896 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43761.4896 | 43761.5417 | 1.25 | DRL | PT-P | BHA | HELD PJSM. P/U & M/U NEW 8 1/2" PDC BIT + BIT SUB + 1x DC + ST. STAB + 1x DC + ST. STAB + PBL SUB.
43761.5417 | 43761.5729 | 0.75 | DRL | PT-P | E/C | FUNCTION TESTED PBL SUB AT SURFACE. PBL SUB ACTIVATED AT 255 PSI; 300 GPM AND DEACTIVTED @ 3000 PSI. RECOVERED DART & BALLS FROM PBL SUB.
43761.5729 | 43761.7188 | 3.5 | DRL | PT-P | BHA | CONT'D RIH BHA FROM 26M TO 324M. WHILE RIH, P/UP 16x 6 1/2" DC, 12x 5" HWDP & 6 1/2" DRL JAR FROM CATWALK SINGLE BY SINGLE. FLUSHED BHA.
43761.7188 | 43762 | 6.75 | DRL | PT-P | RIH | RIH FROM 324M TO 3350M. FILLED STRING AFTER EVERY 15 STANDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43762 | 43762.1458 | 3.5 | DRL | PT-P | RIH | CONT'D RIH FROM 3350M TO 4632M. FILLED STRING AFTER EVERY 15 STANDS.
43762.1458 | 43762.2188 | 1.75 | DRL | PT-P | RW | REAMED DOWN FROM 4632M TO BOTTOM. (MAX TRIP GAS: 7.35%)
43762.2188 | 43762.25 | 0.75 | DRL | PT-P | D | BROKE IN BIT & DRILLED 8 1/2" HOLE FROM 4692.2M TO 4693M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | SAKESSAR / LIMESTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. L/DOWN COR BARREL. PRESSURE TESTED BOP STACK. L/DOWN RACKED BHA FOR INSPECTION. RIH 8 1/2" PDC BIT INSPECTED ROTARY BHA DOWN TO 3350M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15