## DDR#175
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 175
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-06-14
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4535 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 174.5833
RIG REP.: |  | TARIQ BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4535 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-06-13 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  | 21 | IN (M) |  | 4535 |  | OUT (M) |  |  | STRING (BBL) | 286
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1773
DEPTH, MD (M) | 4535 | 4535 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | TAPERED MILL BIT |  |  | 12 |  |  | 6 5/8 REG |  | 1.04 | 0.23223 |  | PITS (BBL) | 840
MW IN (SG) | 2.13 | 2.13 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | BIT SUB |  |  | 8.1875 | 3 |  | 6 5/8 REG |  | 1.04 | 0.23223 |  | ACT. SYS (BBL) | 2899
MW OUT (SG) | 2.13 | 2.13 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | 2 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 18.51 | 4.1333 |  | RESV. SYS (BBL) | 192
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | STRING STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.71 | 0.38184 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  |  |  | 7 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 64.79 | 14.4675 |  | KILL MW (SG) | 2.4
µ FUNNEL (SEC) | 64 | 62 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | DRILLING JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 5.24 | 1.1701 |  | TOTAL | 3691
PV | 33 | 34 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 1 X 8" DC |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 9.18 | 2.0499 |  | DIESEL (LTR)
YIELD POINT | 29 | 30 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | X/OVER |  |  | 8.125 | 2.875 |  | 4 1/2 IF |  | 0.95 | 0.21213 |  | RIG TANK | 119500
GEL ST. | 16/38 | 17/39 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 7 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 65.63 | 4.885 |  | CAMP TANK | 24000
WL (ml/30 min.) | 5.5 | 5.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 10600
CT ( in/32) | 2.5 | 2.5 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 143500
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 182200
KCl (mg/l) | 31460.5 | 31460.5 | JAR | 37.83 | STAB - 1 | 37.83 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 182200
CHLORIDES | 14500 | 14500 | 5" HWDPS | 37.83 | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM | 240 | 240 | 8" DCS | 37.83 |  |  | HSI | [14 empty] | POB
OIL % | 5 | 5 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 168.09 |  |  | MPCL | 3
LUBE % |  |  | BHA ROT. HRS |  | 37.83 |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 19.5738 |  |  | MPCL SERV | 17
SOLIDS % | 37 | 37 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13.7102 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 38.15 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 100 | 1 x 100 |  | 20" SURFACE CASING |  |  | 594 | 4439 |  | 0.97 |  | 100.7 |  |  | 0.46 |  | EMS |  | TOTAL | 104
DAILY WELL COST (US$) |  | 40800.4609 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4467 |  | 0.72 |  | 125.2 |  |  | 0.46 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 10989223.1385 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 4496 |  | 0.79 |  | 108.12 |  |  | 0.24 |  | EMS |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 60.89% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.6 |  | 154.31 |  |  | 0.59 |  | EMS |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 233
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4500 |  | 310/310 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4500 |  | 500/500 |  | CHINJI | 342
FIRE DRILL | 2018-05-20 | 2018-06-19 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4500 |  | 670/670 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-05-18 | 2018-06-17 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 744 |  | SAKESAR
STRETCHER DRILL | 2018-05-20 | 2018-06-19 | NEXT BOP TEST DATE |  | 2018-06-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 18 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43264 | 43264.5833 | 14 | DRL | NPT-UP | RW | HARD REAMED FROM 4229M TO 4497M. WHILE REAMING OBSERVED ROTARY STALLED FREQUENTLY.
43264.5833 | 43265 | 10 | DRL | NPT-UP | MIL | MILLED CENTRALIZERS FROM 4497M TO 4503.5M (OBSERVED FINE METAL SHAVINGS ON DITCH MAGNET).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43265 | 43265.25 | 6 | DRL | NPT-UP | MIL | CONT'D MILLED CENTRALIZERS FROM 4503.5M TO 4506M (OBSERVED FINE METAL SHAVINGS ON DITCH MAGNET).
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | MILLING WITH TAPERED MILL
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | HARD REAMED FROM 4229M TO 4497M. WHILE REAMING OBSERVED ROTARY STALLED FREQUENTLY. MILLED CENTRALIZERS FROM 4497M TO 4503.5M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | MILL CENTRALIZERS & REAM DOWN TO BTM. CIRCULATE BTM UP. POOH TO SURFACE.
REMARKS
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14