## DDR#175
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 175
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIF TURK / MASOOD / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4839 | 4839 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 174.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4861 | 4861 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 86
2019-10-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8.5 |  | RUN NO. |  |  | 32 |  | BHA NO. |  |  | 33 | IN (M) |  | 4692.2 |  | OUT (M) |  |  | STRING (BBL) | 273
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4839 |  | BIT NO. |  |  | 18 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 728.7
DEPTH, MD (M) | 4800 | 4839 | TVD @ 00:00HR (M) |  | 4839 |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.3 | 0.073 |  | PITS (BBL) | 722
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  | 86 |  | MANUFACTURER |  |  | HALLIBURTON |  | BIT SUB |  |  | 6.75 | 3 |  | 4 1/2 IF |  | 1.07 | 0.14064 |  | ACT. SYS (BBL) | 1723.7
MW OUT (SG) | 1.7 | 1.7 | INST. ROP (M/HR) |  | - |  | TYPE |  |  | MMD65DH |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.34 | 1.2277 |  | RESV. SYS (BBL) | 633
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 4.4404 |  | SERIAL NO. |  |  | 13223626 |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.78 | 0.23397 |  | KILL MUD (BBL) | 2.28
FL TEMP. °F | 148 | 148 | AVG. WOB (TON) |  | 4-8 |  | IADC CODE |  |  | M424 |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.24 | 1.2145 |  | KILL MW (SG) | 800
µ FUNNEL (SEC) | 52 | 51 | AVG. RPM SURFACE |  | 115-120 |  | NOZZLES (1/32") |  |  | 6 x 13/32 |  | ST. STAB |  |  | 8.375 | 2.75 |  | 4 1/2 IF |  | 1.4 | 0.18402 |  | TOTAL | 2356.7
PV | 43 | 43 | AVG. RPM DOWNHOLE |  | 115-120 |  | DEPTH IN (M) |  |  | 4692.2 |  | PBL SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 3.48 | 0.45742 |  | DIESEL (LTR)
YIELD POINT | 27 | 28 | FLOWRATE (GPM) |  | 495-502 |  | DEPTH OUT (M) |  |  |  |  | 13 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 120.15 | 15.7928 |  | RIG TANK | 143887
GEL ST. | 10/15 | 11/16 | PRESSURE (PSI) |  | 3530-3650 |  | METERAGE (M) |  |  | 146.8 |  | DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.7 | 1.275 |  | CAMP TANK | 21861
WL (ml/30 min) | 3.8 | 3.8 | TORQ. ON-BTM (KLB-FT) |  | 5-8 |  | RPM SURF. |  |  | 115-120 |  | 3 x DC |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 27.16 | 3.57 |  | CONSUMED | 10420
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | RPM BTM. |  |  | 115-120 |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.19 | 8.2315 |  | RECEIVED | 24000
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 173 |  | WOB (TON) |  |  | 4-8 | [12 empty] | TOTAL | 165748
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  | 185 |  | AVG. ROP (M/HR) |  |  | 4.4404 | [12 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 165 |  | BIT ROT HRS. |  |  | 33.06 | [12 empty] | RIG STORAGE | 470000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 126.71 | [12 empty] | CAMP STORAGE | 74000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 229.52 | [12 empty] | CONSUMED | 180400
KCl (mg/l) | 57201 | 57201 | JAR | 40.6 | STAB - 1 | 40.6 | ANN. VEL. (M/MIN) |  |  | 89.6 | [12 empty] | RECEIVED | 199400
CHLORIDES (mg/l) | 29000 | 29500 | 5" HWDPS | 40.6 | STAB - 2 | 40.6 | JET VELOCITY (M/SEC) |  |  | 27.61 | [12 empty] | TOTAL | 544000
HARDNESS (mg/l) | 320 | 300 | 6 1/2" DCS | 40.6 | STAB - 3 |  | TFA (IN²) |  |  | 0.778 | [12 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB | 40.6 |  |  | HSI |  |  | 0.53 |  | TOTAL LENGTH (M) | [7 empty] | 295.81 |  |  | MPCL | 6
OIL % | 0.5 | 0.5 | DAILY BHA ROT. HRS |  | 21.4 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 19
SOLIDS % | 33.06 | 33.04 | DAILY ON BOTTOM HRS |  | 17.9 |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 22.75 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 53751.44 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13764366.305 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 69.15% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1945.7226
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4808 | 500/510 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4808 | 675/665 |  |  | CHINJI | 338/338
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4808 | 820/815 |  |  | KAMLIAL | 1245/1245
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE / KULD | 1416/1416
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI | 4576/4576
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR | 4667/4667
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 6 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL | 4756/4756
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43763 | 43763.6875 | 16.5 | DRL | PT-P | D | DRILLED 8 1/2" HOLE FROM 4753M TO 4818M. REAMED AT CONNECTION.
43763.6875 | 43763.7083 | 0.5 | DRL | PT-P | FC | OBSERVED DRILLING BREAK AT 4818M. FLOW CHECKED, WELL STATIC.
43763.7083 | 43764 | 7 | DRL | PT-P | D | RESUMED DRILLING & DRILLED 8 1/2" HOLE FROM 4818M TO 4839M. REAMED AT CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43764 | 43764.25 | 6 | DRL | PT-P | D | DRILLED 8 1/2" HOLE FROM 4839M TO 4861M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAMMAL / LIMESTONE, CLAYSTONE, MARL, SHALE
OPERATIONS AT 06:00 HRS |  |  | DRILLING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2" HOLE FROM 4753M TO 4839M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" HOLE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15