## DDR#176
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 176
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD / HAMZA / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4864 | 4864 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 175.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4864 | 4864 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 25
2019-10-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8.5 |  | RUN NO. |  |  | 32 |  | BHA NO. |  |  | 33 | IN (M) |  | 4692.2 |  | OUT (M) |  |  | STRING (BBL) | 272.4
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4864 |  | BIT NO. |  |  | 18 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 733.9
DEPTH, MD (M) | 4864 | 4864 | TVD @ 00:00HR (M) |  | 4864 |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.3 | 0.073 |  | PITS (BBL) | 694
MW IN (SG) | 1.7 | 1.7 | DAILY PROGRESS (M) |  | 25 |  | MANUFACTURER |  |  | HALLIBURTON |  | BIT SUB |  |  | 6.75 | 3 |  | 4 1/2 IF |  | 1.07 | 0.14064 |  | ACT. SYS (BBL) | 1700.3
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | - |  | TYPE |  |  | MMD65DH |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.34 | 1.2277 |  | RESV. SYS (BBL) | 683
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 4.0519 |  | SERIAL NO. |  |  | 13223626 |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.78 | 0.23397 |  | KILL MUD (BBL) | 2.28
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 5-8 |  | IADC CODE |  |  | M424 |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.24 | 1.2145 |  | KILL MW (SG) | 800
µ FUNNEL (SEC) | 53 | 54 | AVG. RPM SURFACE |  | 110-130 |  | NOZZLES (1/32") |  |  | 6 x 13/32 |  | ST. STAB |  |  | 8.375 | 2.75 |  | 4 1/2 IF |  | 1.4 | 0.18402 |  | TOTAL | 2383.3
PV | 43 | 42 | AVG. RPM DOWNHOLE |  | 110-130 |  | DEPTH IN (M) |  |  | 4692.2 |  | PBL SUB |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 3.48 | 0.45742 |  | DIESEL (LTR)
YIELD POINT | 26 | 27 | FLOWRATE (GPM) |  | 502 |  | DEPTH OUT (M) |  |  |  |  | 13 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 120.15 | 15.7928 |  | RIG TANK | 135272
GEL ST. | 10/15 | 10/15 | PRESSURE (PSI) |  | 3530-3580 |  | METERAGE (M) |  |  | 171.8 |  | DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.7 | 1.275 |  | CAMP TANK | 21391
WL (ml/30 min) | 3.6 | 3.5 | TORQ. ON-BTM (KLB-FT) |  | 5-7 |  | RPM SURF. |  |  | 110-130 |  | 3 x DC |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 27.16 | 3.57 |  | CONSUMED | 9085
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | RPM BTM. |  |  | 110-130 |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.19 | 8.2315 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 173 |  | WOB (TON) |  |  | 5-8 | [12 empty] | TOTAL | 156663
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  | 185 |  | AVG. ROP (M/HR) |  |  | 4.3793 | [12 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 165 |  | BIT ROT HRS. |  |  | 39.23 | [12 empty] | RIG STORAGE | 460000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 44.75 | [12 empty] | CAMP STORAGE | 74000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 274.27 | [12 empty] | CONSUMED | 122900
KCl (mg/l) | 57201 | 57201 | JAR | 47.83 | STAB - 1 | 47.83 | ANN. VEL. (M/MIN) |  |  | 90.2 | [12 empty] | RECEIVED | 112900
CHLORIDES (mg/l) | 29000 | 29000 | 5" HWDPS | 47.83 | STAB - 2 | 47.83 | JET VELOCITY (M/SEC) |  |  | 27.8 | [12 empty] | TOTAL | 534000
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 47.83 | STAB - 3 |  | TFA (IN²) |  |  | 0.778 | [12 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB | 47.83 |  |  | HSI |  |  | 0.55 |  | TOTAL LENGTH (M) | [7 empty] | 295.81 |  |  | MPCL | 6
OIL % | 0.5 | 0.5 | DAILY BHA ROT. HRS |  | 7.23 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 24 |  |  | MPCL SERV | 22
SOLIDS % | 33.36 | 33.36 | DAILY ON BOTTOM HRS |  | 6.17 |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 7.58 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 42396.5092 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13806762.8142 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 69.36% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1945.7226
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4808 | 500/510 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4808 | 675/665 |  |  | CHINJI | 338/338
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4808 | 820/815 |  |  | KAMLIAL | 1245/1245
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE / KULD | 1416/1416
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI | 4576/4576
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR | 4667/4667
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 2 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL | 4756/4756
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43764 | 43764.2917 | 7 | DRL | PT-P | D | DRILLED 8 1/2" HOLE FROM 4839M TO 4864M.
43764.2917 | 43764.3125 | 0.5 | DRL | NPT-UP | POOH | OBSERVED LEAKAGE IN WASH PIPE. POOH FROM 4864M TO 4781M.
43764.3125 | 43764.3438 | 0.75 | DRL | NPT-UP | RR | REPLACED WASHPIPE. MEANWHILE ATTEMPTED TO RESUME CIRCULATION THROUGH CIRC. HEAD & ROTATION THROUGH ROTARY BUT NO SUCCESS.
43764.3438 | 43765 | 15.75 | DRL | NPT-UP | STK | P/U ONE SINGLE & M/U TDS. WORKED ON STUCK STRING BY APPLYING UPWARD / DOWNWARD JARRING & TORQUE; BUT NO SUCCESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43765 | 43765.1875 | 4.5 | DRL | NPT-UP | STK | WORKED ON STUCK STRING BY APPLYING UPWARD / DOWNWARD JARRING & TORQUE; BUT NO SUCCESS.
43765.1875 | 43765.25 | 1.5 | DRL | NPT-UP | RU | HELD PJSM. R/U WFD WIRELINE GEARS FOR FPIT JOB.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAMMAL / LIMESTONE, CLAYSTONE, MARL, SHALE
OPERATIONS AT 06:00 HRS |  |  | R/U IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2" HOLE FROM 4839M TO 4864M. OBSERVED LEAKAGE IN WASHPIPE. POOH TO 4781M & REPLACED WASHPIPE. OBSERVED STRING STUCK & NO CIRCULATION. WORKED ON STUCK STRING.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONDUCT FPIT. PERFORM BACK-OFF JOB AND PLAN AHEAD ACCORDINGLY.
REMARKS |  |  | WIRELINE UNIT, TOOLS & ENGINEER ARRIVED AT LOCATION. FISHING TOOLS & ENGINEER ARRIVED AT LOCATION.
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15