## DDR#178
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 178
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-10-29
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD / HAMZA / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 4864 | 4864 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 177.9792
RIG REP.: |  | TARIQ BUTT / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 4864 | 4864 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-10-28 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 33 |  | BHA NO. |  |  | 34 | IN (M) |  | 4864 |  | OUT (M) |  |  | STRING (BBL) | 3.6
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 14 RR2 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1108.4
DEPTH, MD (M) | 4864 | 4864 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.26 | 0.05 |  | PITS (BBL) | 851
MW IN (SG) | 1.72 | 1.72 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 1.07 | 0.14064 |  | ACT. SYS (BBL) | 1963
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi616 |  | 1 x DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.27 | 1.2185 |  | RESV. SYS (BBL) | 453
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JN5340 |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.59 | 0.20899 |  | KILL MUD (BBL) | 2.28
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 9 x DC |  |  | 6.5 | 2.25 |  | 4 1/2 IF |  | 83.22 | 10.9386 |  | KILL MW (SG) | 800
µ FUNNEL (SEC) | 54 | 55 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6 x 18/32 |  | DRL JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.8 | 1.2881 |  | TOTAL | 2416
PV | 44 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4864 |  | 3 x DC |  |  | 6.5 | 2.3125 |  | 4 1/2 IF |  | 27.64 | 3.6331 |  | DIESEL (LTR)
YIELD POINT | 27 | 28 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 12 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.44 | 8.1764 |  | RIG TANK | 125585
GEL ST. | 11/15 | 11/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 20447
WL (ml/30 min) | 3.5 | 3.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 6523
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 146032
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 75000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 51400
KCl (mg/l) | 58154.3 | 58154.3 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 52400
CHLORIDES (mg/l) | 29500 | 29500 | 5" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | TOTAL | 525000
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS |  | STAB - 3 |  | TFA (IN²) |  |  | 1.491 | [12 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 244.29 |  |  | MPCL | 7
OIL % | 0.5 | 0.5 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 25
SOLIDS % | 33.7 | 33.7 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 118
DAILY WELL COST (US$) |  | 44980.6533 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 13880629.4467 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 69.73% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1810
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4808 | 500/510 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL | 2019-07-19 | 2019-09-17 | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4808 | 675/665 |  |  | CHINJI | 338/338
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4808 | 820/815 |  |  | KAMLIAL | 1245/1245
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE / KULD | 1416/1416
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI | 4576/4576
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR | 4667/4667
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL | 4756/4756
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43766 | 43766.0417 | 1 | DRL | NPT-UP | W/L | POOH W/L TO SURFACE AND L/D TOOLS. R/D W/L GEARS.
43766.0417 | 43766.25 | 5 | DRL | NPT-UP | CIR | ESTABLISHED CIRCULATION. PUMPED 25 BBL HI-VIS AND CONT'D CIRCULATION TO INCREASE MW & HOMOGENIZE (MWIN/OUT - 1.72 SG).
43766.25 | 43766.2604 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED, WELL STATIC.
43766.2604 | 43766.2812 | 0.5 | DRL | NPT-UP | SP | SPOTTED 35 BBL HI-VIS AT BOTTOM PRIOR TO POOH.
43766.2812 | 43766.7708 | 11.75 | DRL | NPT-UP | POOH | POOH FROM 4707M TO 295M (BHA TOP). FLOW CHECKED AT CSG SHOE AND PUMPED SLUG. OBSERVED CONNECTIONS OVERTORQUED.
43766.7708 | 43766.7812 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED AT BHA, WELL STATIC.
43766.7812 | 43766.9062 | 3 | DRL | NPT-UP | BHA | POOH BHA FROM 295M TO SURFACE. L/D JAR & 8x 6 1/2" DC.
43766.9062 | 43767 | 2.25 | DRL | NPT-UP | BHA | M/U RR 8 1/2" PDC BIT & RIH WITH INSPECTED ROTARY BHA DOWN TO 150M FOR CONDITION TRIP.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-10-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43767 | 43767.0521 | 1.25 | DRL | NPT-UP | BHA | CONT'D RIH BHA FROM 150M TO 265M. FLUSHED BHA. WHILE RIH, P/U COMPLETE BHA SINGLE BY SINGLE FROM CATWALK.
43767.0521 | 43767.25 | 4.75 | DRL | NPT-UP | RIH | RIH FROM 265M TO 2287M & IS IN PROGRESS. FILLED STRING AFTER EVERY 20 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAMMAL / LIMESTONE, CLAYSTONE, MARL, SHALE
OPERATIONS AT 06:00 HRS |  |  | RIH IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH W/L & R/D W/L GEARS. CIRCULATED TO INCREASE AND HOMOGENIZE MW. SPOTTED HI-VIS & POOH TO SURFACE. RIH 8 1/2" PDC BIT WITH INSPECTED ROTARY BHA FOR CONDITION TRIP.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH & TAG TOP OF FISH. CONDITION MUD & POOH TO SURFACE FOR FMI LOG.
REMARKS |  |  | SLB WIRELINE UNIT AND CREW ARRIVED AT LOCATION. 73M FISH LEFT IN HOLE (8 1/2" PDC BIT + BIT SUB + 1x 6 1/2" DC + ST. STAB + 1x 6 1/2" DC + ST. STAB + PBL SUB + 5x 6 1/2" DC)
Formulas:
MIRAJ-1 = [DATE]+60
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15