## DDR#179
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 179
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-06-18
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4535 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 178.5833
RIG REP.: |  | TARIQ BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4535 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-06-17 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  | 8RR |  | BHA No. |  |  | 22 | IN (M) |  | 4535 |  | OUT (M) |  |  | STRING (BBL) | 287
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 12.25 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1770
DEPTH, MD (M) | 4535 | 4535 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | TRICONE BIT |  |  | 12.25 |  |  | 6 5/8 REG |  | 0.31 | 0.069223 |  | PITS (BBL) | 563
MW IN (SG) | 2.16 | 2.17 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SB137CPS |  | BIT SUB (F.V) |  |  | 8.1875 | 3 |  | 6 5/8 REG |  | 1.04 | 0.23223 |  | ACT. SYS (BBL) | 2620
MW OUT (SG) |  | 2.15 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RJ1456 |  | 1 X 8" DC |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 9.15 | 2.0432 |  | RESV. SYS (BBL) | 348
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 137 |  | STRING STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.56 | 0.34835 |  | KILL MUD (BBL) | 550
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | OPEN JETS |  | 1 X 8" DC |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 9.36 | 2.0901 |  | KILL MW (SG) | 2.4
µ FUNNEL (SEC) | 60 | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4535 |  | STRING STAB |  |  | 12.125 | 3 |  | 6 5/8 REG |  | 1.71 | 0.38184 |  | TOTAL | 3518
PV | 36 | 37 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 7 X 8" DCS |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 64.79 | 14.4675 |  | DIESEL (LTR)
YIELD POINT | 29 | 30 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | DRILLING JAR |  |  | 7.875 | 3 |  | 6 5/8 REG |  | 5.24 | 1.1701 |  | RIG TANK | 92800
GEL ST. | 17/38 | 18/38 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 1 X 8" DC |  |  | 8 | 2.75 |  | 6 5/8 REG |  | 9.18 | 2.0499 |  | CAMP TANK | 21600
WL (ml/30 min.) | 4.8 | 4.8 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | X/OVER |  |  | 8.125 | 2.875 |  | 4 1/2 IF |  | 0.95 | 0.21213 |  | CONSUMED | 5300
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 7 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 65.63 | 4.885 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 114400
ALK (FILT.) | 0.6 | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 99930
KCl (mg/l) | 31460.5 | 31460.5 | JAR | 75.91 | STAB - 1 | 75.91 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 99930
CHLORIDES | 14500 | 14500 | 5" HWDPS | 75.91 | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM | 240 | 240 | 8" DCS | 75.91 |  |  | HSI | [14 empty] | POB
OIL % | 5 | 5 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 168.92 |  |  | MPCL | 3
LUBE % |  |  | BHA ROT. HRS |  | 75.91 |  | BIT No. 8RR |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 20.2914 |  |  | MPCL SERV | 22
SOLIDS % | 38.01 | 38.51 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14.2531 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 85.49 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 45
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 100 | 1 x 100 |  | 20" SURFACE CASING |  |  | 594 | 4439 |  | 0.97 |  | 100.7 |  |  | 0.46 |  | EMS |  | TOTAL | 105
DAILY WELL COST (US$) |  | 43836.0357 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4467 |  | 0.72 |  | 125.2 |  |  | 0.46 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 11143088.8834 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 4496 |  | 0.79 |  | 108.12 |  |  | 0.24 |  | EMS |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 61.74% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.6 |  | 154.31 |  |  | 0.59 |  | EMS |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 233
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4500 |  | 310/310 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4500 |  | 500/500 |  | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4500 |  | 670/670 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 744 |  | SAKESAR
STRETCHER DRILL | 2018-05-20 | 2018-06-19 | NEXT BOP TEST DATE |  | 2018-06-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43268 | 43268.2917 | 7 | DRL | NPT-UP | WC | CIRCULATED THRU CHOKE TO CONTROL WELL & HOMOGENIZED MUD COLUMN (MW IN = 2.16 S.G & MW OUT = 2.14 S.G). MEANWHILE TREATED MUD & MAINTAINED MW IN ACTIVE SYSTEM.
43268.2917 | 43268.3125 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED THRU CHOKE LINE - OK. OPENED BOP & FLOW CHECKED - WELL STATIC.
43268.3125 | 43268.3333 | 0.5 | DRL | NPT-UP | POOH | POOH FROM 4535M TO 4464M & OBSVD TIGHT SPOT.
43268.3333 | 43268.3958 | 1.5 | DRL | NPT-UP | RW | BACK REAMED / REAMED DOWN TO CLEAR TIGHT HOLE FROM 4464M TO 4404M.
43268.3958 | 43268.5417 | 3.5 | DRL | NPT-UP | POOH | POOH FROM 4404M TO 3500M.
43268.5417 | 43268.5521 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC
43268.5521 | 43268.7188 | 4 | DRL | NPT-UP | RIH | RIH FROM 3500M TO BTM @ 4535M. WHILE RIH OBSVD & CLEARED TIGHT SPOTS @ 3915M, 4322M & 4474M.
43268.7188 | 43268.8542 | 3.25 | DRL | NPT-UP | CIR | CIRCULATED TO BTM UP. OBSVD INCREASE IN FLOW OUT & RECORDED MW IN = 2.16 S.G & MINIMUM MW OUT = 2.05 S.G.
43268.8542 | 43268.875 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED - OBSVD WELL TRICKLING.
43268.875 | 43269 | 3 | DRL | NPT-UP | CIR | CIRCULATED TO HOMOGENIZE MUD COLUMN & INCREASED MW IN TO 2.17 S.G.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43269 | 43269.0312 | 0.75 | DRL | NPT-UP | CIR | CONT'D CIRCULATED TO HOMOGENIZE MUD COLUMN & INCREASED MW (MW IN = 2.17 S.G & MW OUT = 2.15 S.G).
43269.0312 | 43269.0417 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC
43269.0417 | 43269.125 | 2 | DRL | NPT-UP | WT | CONDUCTED SHORT WIPER TRIP FROM 4535M TO 4370M. WHILE POOH OBSVD & CLEARED TIGHT SPOTS @ 4483M & 4454M.
43269.125 | 43269.1667 | 1 | DRL | NPT-UP | SP | PUMPED & SPOTTED 285 BBL LUBRA BEADS PILL OF 6 PPB IN OPEN HOLE FROM BTM TO 4000M.
43269.1667 | 43269.1771 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC
43269.1771 | 43269.25 | 1.75 | DRL | NPT-UP | POOH | POOH FROM 4535M TO 4120M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED THRU CHOKE TO CONTROL WELL & HOMOGENIZED MUD. FLOW CHECKED, OK. CONDUCTED WIPER TRIP FROM BTM TO 3500M. CIRCULATED TO BTM UP. OBSVD INCREASE IN FLOW OUT & WELL TRICKLING. CIRCULATED TO HOMOGENIZE MUD COLUMN & INCREASE MW TO 2.17 S.G.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO 4000M & SPOT LUBRA BEADS FROM 4000M TO 3500M. POOH TO 13 3/8" CASING SHOE. CUT & SLIP DRILL LINE. POOH TO SURFACE. RIH 9 5/8" CASING.
REMARKS |  |  | CONDUCTED FIRE DRILL AT CAMPSITE YESTERDAY. W.F TRS CREW & EQUIPMENT RECEIVED YESTERDAY.
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14