## DDR#183
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 183
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-06-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4535 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 182.5833
RIG REP.: |  | TARIQ BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4535 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-06-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 7:30 | 23:30 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1901
DEPTH, MD (M) | 4535 | 4535 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | 9 5/8" F/SHOE |  |  | 10.5625 | 8.5 |  | 140HC,VT |  | 0.853 |  |  | PITS (BBL) | 807
MW IN (SG) | 2.17 | 2.17 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | 2 X 9 5/8" JTS |  |  | 9.625 | 8.535 |  | 140HC,VT |  | 25.644 |  |  | ACT. SYS (BBL) | 2708
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | 9 5/8" F/COLLAR |  |  | 10.5625 | 8.5 |  | 140HC,VT |  | 0.898 |  |  | RESV. SYS (BBL) | 239
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 1 X 9 5/8" JT |  |  | 9.625 | 8.535 |  | 140HC,VT |  | 12.82 |  |  | KILL MUD (BBL) | 550
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  |  |  | 9 5/8" L/COLLAR |  |  | 10.5625 | 8.543 |  | 140HC,VT |  | 0.546 |  |  | KILL MW (SG) | 2.4
µ FUNNEL (SEC) | 67 | 64 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 145 X 9 5/8" JTS |  |  | 9.625 | 8.535 |  | 140HC,VT |  | 1848.895 |  |  | TOTAL | 3497
PV | 39 | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 26 X 9 5/8" JTS |  |  | 9.625 | 8.535 |  | Q125,VT |  | 323.855 |  |  | DIESEL (LTR)
YIELD POINT | 27 | 27 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | ACP |  |  | 11 | 8.661 |  | P110,VT |  | 3.073 |  |  | RIG TANK | 103000
GEL ST. | 14/32 | 13/31 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | PUP JOINT # 3 |  |  | 9.625 | 8.535 |  | Q125,VT |  | 4.523 |  |  | CAMP TANK | 19200
WL (ml/30 min.) | 4.6 | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 1 X 9 5/8" JT |  |  | 9.625 | 8.535 |  | Q125,VT |  | 12.162 |  |  | CONSUMED | 4600
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | STAGE TOOL |  |  | 11.125 | 8.661 |  | P110,VT |  | 1.083 |  |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | 99 X 9 5/8" JTS |  |  | 9.625 | 8.535 |  | Q125,VT |  | 1238.429 |  |  | TOTAL | 122200
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | 80 X 9 5/8" JTS |  |  | 9.625 | 8.535 |  | P110,VT |  | 959.797 |  |  | WATER (LTR)
PH | 9.3 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | X/OVER |  |  | 9.625 | 8.535 |  | VT X JFE |  | 1.39 |  |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS |  |  |  | 8 X 9 5/8" JTS |  |  | 9.625 | 8.535 |  | P110,JFE |  | 95.247 |  |  | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  |  | PUP JOINT # 7 |  |  | 9.625 | 8.535 |  | P110,JFE |  | 4.628 |  |  | CONSUMED | 225110
KCl (mg/l) | 31651.2 | 31651.2 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 225110
CHLORIDES | 15000 | 15000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM | 280 | 260 | 8" DCS |  |  |  | HSI | [14 empty] | POB
OIL % | 5 | 5 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 4533.843 |  |  | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 29
SOLIDS % | 38.51 | 38.51 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 100 | 1 x 100 |  | 20" SURFACE CASING |  |  | 594 | 4439 |  | 0.97 |  | 100.7 |  |  | 0.46 |  | EMS |  | TOTAL | 120
DAILY WELL COST (US$) |  | 30111.8399 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4467 |  | 0.72 |  | 125.2 |  |  | 0.46 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 11274260.1348 | SHAKER-3 | 2 x 140 | 1 x 140 |  | 9 5/8" PRODUCTION CSG |  |  |  | 4496 |  | 0.79 |  | 108.12 |  |  | 0.24 |  | EMS |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 62.46% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.6 |  | 154.31 |  |  | 0.59 |  | EMS |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 233
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4500 |  | 310/310 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4500 |  | 500/500 |  | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4500 |  | 670/670 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES |  |  |  | 744 |  | SAKESAR
STRETCHER DRILL | 2018-05-20 | 2018-06-19 | NEXT BOP TEST DATE |  | 2018-06-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43272 | 43272.625 | 15 | DRL | PT-P | RC | RIH 9 5/8" CSG (53.5 PPF, Q-125/P-110, VAMTOP) FROM 3170M TO 4167M (TOTAL 332 JOINTS). RIH EVERY CSG JOINT WITH SLOW CIRC & CIRCULATED FOR 15 MIN AFTER EVERY 10 JOINTS. W.F JAM UNIT MALFUNCTIONED.
43272.625 | 43272.6458 | 0.5 | DRL | NPT-UP | E/F | TROUBLE SHOOTED & ATTEMPTED TO RECTIFY W.F JAM UNIT, NO SUCCESS. REPLACED THE SAME.
43272.6458 | 43272.9375 | 7 | DRL | PT-P | RC | CONT'D RIH 9 5/8" CSG (53.5 PPF, P-110, VAMTOP/JFE BEAR) FROM 4167M TO 4533M (TOTAL 362 JOINTS). RIH EVERY CSG JOINT WITH SLOW CIRC & CIRCULATED FOR 15 MIN AFTER EVERY 5 JOINTS. OBSVD DRAG OF 50 - 175 TON WHILE RIH CSG FROM 4167M TO 4533M.
43272.9375 | 43273 | 1.5 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD PRIOR CEMENT JOB.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43273 | 43273.0521 | 1.25 | DRL | PT-P | CIR | CONT'D CIRCULATED TO CONDITION MUD PRIOR CEMENT JOB. MEANWHILE PREPARING MIX FLUID FOR CEMENT SLURRIES & WEIGHTED UP SPACER.
43273.0521 | 43273.1042 | 1.25 | DRL | PT-P | RD | R/DOWN W.F TRS GEAR. L/DOWN CIRCULATING DEVICE (LA-FLEUR) & INSTALLED CIRCULATING HEAD.
43273.1042 | 43273.25 | 3.5 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD PRIOR CEMENT JOB. MEANWHILE PREPARING MIX FLUID FOR CEMENT SLURRIES & WEIGHTED UP SPACER.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION PRIOR CEMENT JOB
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH 9 5/8" CSG FROM 3170M TO 4533M. RIH EVERY CSG JOINT WITH CIRC. CIRCULATED TO CONDITION MUD PRIOR CEMENT JOB.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONDUCT 1ST STAGE CEMENT JOB AS PER PROGRAM. WOC FOR +/- 24 HRS. CONDUCT 2ND STAGE CEMENT JOB.
REMARKS |  |  | FMC WELLHEAD ENGINEER ARRIVED TODAY ON 22-JUN-18 @ 0530 HRS.
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14