## DDR#184
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 184
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-11-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD / HAMZA / MOHSIN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4864 | 4864 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 183.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4864 | 4864 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-11-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 37 | IN (M) |  | 4720( TOF) |  | OUT (M) |  |  | STRING (BBL) | 268
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 739.9
DEPTH, MD (M) | 4864 | 4864 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | SCREW IN SUB |  |  | 6.5 | 2.875 |  | 4 1/2 REG |  | 1.03 | 0.13542 |  | PITS (BBL) | 662
MW IN (SG) | 1.78 | 1.78 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | 9 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 83.23 | 10.9429 |  | ACT. SYS (BBL) | 1669.9
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | D. JAR |  |  | 6.375 | 2.75 |  | 4 1/2 IF |  | 9.9 | 1.3016 |  | RESV. SYS (BBL) | 688
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | 3 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.64 | 3.6341 |  | KILL MUD (BBL) | 2.28
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 12 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.44 | 8.1787 |  | KILL MW (SG) | 800
µ FUNNEL (SEC) | 61 | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") | [15 empty] | TOTAL | 2357.9
PV | 43 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 31 | 31 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 118891
GEL ST. | 10/15 | 10/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 17593
WL (ml/30 min) | 3.4 | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5222
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 136484
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 470000
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 75000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 41800
KCl (mg/l) | 59108 | 59107.7 | JAR | 2.08 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 48800
CHLORIDES (mg/l) | 30000 | 30000 | 5" HWDPS | 32.28 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 0
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS | 32.28 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 233.24 |  |  | MPCL | 6
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 2.08 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 28
SOLIDS % | 36.38 | 36.38 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 14RR3 |  |  | 4-2-BT-N-X-I-WT-BHA |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 3.03 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 120
DAILY WELL COST (US$) |  | 41154 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14183630 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 71.25% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1428
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4808 | 500/510 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4808 | 675/665 |  |  | CHINJI | 338/338
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4808 | 820/815 |  |  | KAMLIAL | 1245/1245
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE / KULD | 1416/1416
KICK DRILL | 2019-10-31 | 2019-11-30 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI | 4576/4576
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR | 4667/4667
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL | 4756/4756
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43772 | 43772.3854 | 9.25 | DRL | NPT-UP | POOH | CONT'D POOH FROM 4720M TO 233M.
43772.3854 | 43772.3958 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43772.3958 | 43772.4375 | 1 | DRL | NPT-UP | BHA | POOH BHA FROM 233M TO SURFACE. B/OUT & L/DOWN BIT SUB, BIT.
43772.4375 | 43772.4792 | 1 | DRL | NPT-UP | BHA | P/UP AND M/UP W.FORD 6 1/2'' SCREW IN SUB. RIH AS PER BHA DOWN TO 233M. FLUSHED SAME.
43772.4792 | 43772.8333 | 8.5 | DRL | NPT-UP | RIH | RIH FROM 233M TO 4546M.
43772.8333 | 43772.8438 | 0.25 | DRL | NPT-UP | CIR | BROKE CIRCULATION.
43772.8438 | 43772.8646 | 0.5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 4546M TO 4700M.
43772.8646 | 43772.875 | 0.25 | DRL | NPT-UP | RW | CONNECTED TDS, WASHED DOWN FROM 4700M TO TAG TOF AT 4720M.
43772.875 | 43772.9583 | 2 | DRL | NPT-UP | F | WORKED ON SCREW-IN-SUB, MADE SEVERAL ATTEMPTS TO SCREW IN THE FISH WITH & WITHOUT CIRCULATION. NO SUCCESS.
43772.9583 | 43772.9688 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43772.9688 | 43773 | 0.75 | DRL | NPT-UP | SP | SPOTTED 40 BBL HI-VIS PILL PRIOR POOH.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43773 | 43773.0312 | 0.75 | DRL | NPT-UP | POOH | POOH FROM 4720M TO 4546M.
43773.0312 | 43773.0417 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43773.0417 | 43773.25 | 5 | DRL | NPT-UP | POOH | POOH FROM 4546M TO 2017M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAMMAL / LIMESTONE, CLAYSTONE, MARL, SHALE
OPERATIONS AT 06:00 HRS |  |  | POOH IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN BIT & BIT SUB, RIH WITH FISHING BHA (SCREW IN SUB), ATTEMPTED TO ENGAGE FISH. NO SUCCESS. SPOTTED 40 BBL HI-VIS PILL PRIOR POOH.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE, L/DOWN SCREW IN SUB, RIH WITH FISHING BHA (GUIDED SCREW IN SUB), ATTEMPT # 2 TO RECOVER FISH.
REMARKS |  |  | WASH PIPE ROTATING HRS = 38.23 ; CIRC HRS = 64.62 @ 0:00 HRS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15