## DDR#185
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 185
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-06-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4535 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 184.5833
RIG REP.: |  | TARIQ BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4535 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-06-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 7:59 | 21:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1053
DEPTH, MD (M) | 4535 | 4535 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 908
MW IN (SG) | 2.17 | 2.17 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1961
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 474
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 550
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | 2.4
µ FUNNEL (SEC) | 58 | 57 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 2985
PV | 38 | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT | 24 | 22 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 118000
GEL ST. | 12/26 | 12/27 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 25900
WL (ml/30 min.) | 4.5 | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5150
CT ( in/32) | 1.5 | 1.5 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 143900
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 183540
KCl (mg/l) | 31651.2 | 31651.2 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 183540
CHLORIDES | 15000 | 15000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM | 260 | 260 | 8" DCS |  |  |  | HSI | [14 empty] | POB
OIL % | 5 | 5 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 4
LUBE % | 2 | 2 | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 25
SOLIDS % | 38.51 | 38.51 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 50 | 1 x 50 |  | 20" SURFACE CASING |  |  | 594 | 4439 |  | 0.97 |  | 100.7 |  |  | 0.46 |  | EMS |  | TOTAL | 116
DAILY WELL COST (US$) |  | 39327.9499 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4467 |  | 0.72 |  | 125.2 |  |  | 0.46 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 11398318.2896 | SHAKER-3 | 2 x 35 | 1 x 35 |  | 9 5/8" PRODUCTION CSG |  |  | 4533 | 4496 |  | 0.79 |  | 108.12 |  |  | 0.24 |  | EMS |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 63.15% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.6 |  | 154.31 |  |  | 0.59 |  | EMS |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 233
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-05-20 | 2018-06-19 | NEXT BOP TEST DATE |  | 2018-06-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43274 | 43274.6771 | 16.25 | DRL | PT-P | WOC | WOC, MEANWHILE CIRCULATED THRU STAGE COLLAR PORTS @ 3 BPM & PREPARED SPACER & MIX FLUID FOR 2nd STAGE CEMENT SLURRIES.
43274.6771 | 43274.875 | 4.75 | DRL | PT-P | CMC | HELD PJSM. LOADED CEMENTING HEAD WITH 2nd STAGE CLOSING PLUG. PUMPED 100 BBL MUDPUSH II SPACER OF 18.6 PPG FROM RIG PUMP @ 7-8 BPM. SWITCHED OVER TO CEMENT UNIT & PUMPED 340 BBL FLY MIXED LEAD SLURRY OF 19.5 PPG @ 4-5 BPM FOLLOWED BY 100 BBL BATCH MIXED TAIL SLURRY OF 19.5 PPG @ 4-5 BPM. DROPPED 2ND STAGE CLOSING PLUG. DISPLACED CEMENT WITH 10 BBL WATER THRU CEMENT UNIT @ 5 BPM, SWITCHED OVER TO RIG PUMP & DISPLACED CEMENT WITH 500 BBL MUD @ 8-10 BPM. DISPLACED LAST 40 BBL MUD (8 BBL OVER-DISPLACEMENT) @ 2-3 BPM & BUMPED PLUG @ 800 PSI (TOTAL DISPLACEMENT = 550 BBL). INCREASED PRESSURE TO 2200 PSI, HELD PRESSURE FOR 5 MIN & OBSERVED STAGE TOOL PORTS CLOSED SUCCESSFULLY. BLED-OFF PRESSURE & CHECKED BACK FLOW - NO BACK FLOW. DISCARDED 100 BBL SPACER CONTAMINATION & 174 BBL NEAT CEMENT WHILE DISPLACEMENT. R/DOWN CEMENT LINES.
43274.875 | 43275 | 3 | DRL | PT-P | NDB | WOC. FLUSHED BOP STACK & WELLHEAD WITH WATER. REMOVED CHOKE LINE, CUT & L/DOWN FLOW LINE & BELL NIPPLE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43275 | 43275.0521 | 1.25 | DRL | PT-P | NDB | MADE PREPARATIONS & LIFTED BOP STACK WITH BOP TROLLEY.
43275.0521 | 43275.0938 | 1 | DRL | PT-P | WH | CENTRED CASING & SET 9 5/8" SLIP & SEAL ASSY IN CASING HEAD SPOOL (CHS). SLACKED OFF CASING WEIGHT ON SLIP & SEAL ASSY.
43275.0938 | 43275.1875 | 2.25 | DRL | PT-P | CC | ROUGH CUT 9 5/8" CASING. R/DOWN CEMENTING HEAD & L/DOWN 9 5/8" CASING PUP JOINT WITH CUT PIECE.
43275.1875 | 43275.2292 | 1 | DRL | PT-P | NDB | N/DOWN 13 5/8" - 10K SPACER SPOOL.
43275.2292 | 43275.25 | 0.5 | DRL | PT-P | CC | FINAL CUT 9 5/8" CASING WITH WELLSERVE COLD CUTTER IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | FINAL CUT 9 5/8" CASING
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WOC, MEANWHILE CIRCULATED THRU STAGE COLLAR PORTS. CONDUCTED 2ND STAGE 9 5/8" CASING CEMENT JOB AS PER PROGRAM. WOC. CUT & L/DOWN FLOW LINE & BELL NIPPLE TO LIFT BOP STACK.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | FINAL CUT 9 5/8" CASING. INSTALL & P/TEST 13 5/8" - 10K X 11" - 10K THS. N/UP & P/TEST BOP STACK. L/DOWN 8" DCS + 5 1/2" DP FROM DERRICK.
REMARKS
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14