## DDR#186
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 186
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-06-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP.: DSV |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4535 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 185.5833
RIG REP.: TP |  | TARIQ BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4535 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-06-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME |  | 23:30 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1053
DEPTH, MD (M) |  | 4535 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 303
MW IN (SG) |  | 2.17 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1356
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 32
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | 2.17
µ FUNNEL (SEC) |  | 58 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 1988
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 23 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 115000
GEL ST. |  | 12/27 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 25250
WL (ml/30 min.) |  | 4.7 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 3650
CT ( in/32) |  | 1.5 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 140250
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 309710
KCl (mg/l) |  | 31651.2 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 309710
CHLORIDES |  | 15000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 485000
CALCIUM |  | 260 | 8" DCS |  |  |  | HSI | [14 empty] | POB
OIL % |  | 5 | 9 1/2" DCS |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 19
SOLIDS % |  | 38.51 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 50 | 1 x 50 |  | 20" SURFACE CASING |  |  | 594 | 4439 |  | 0.97 |  | 100.7 |  |  | 0.46 |  | EMS |  | TOTAL | 109
DAILY WELL COST (US$) |  | 1084634.0383 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4467 |  | 0.72 |  | 125.2 |  |  | 0.46 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 12482952.3279 | SHAKER-3 | 2 x 35 | 1 x 35 |  | 9 5/8" PRODUCTION CSG |  |  | 4533 | 4496 |  | 0.79 |  | 108.12 |  |  | 0.24 |  | EMS |  | LAST CSG SIZE | 13 3/8"
% OF AFE SPENT |  | 69.16% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.6 |  | 154.31 |  |  | 0.59 |  | EMS |  | FIT (EMW) | 2.2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 233
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43275 | 43275.0521 | 1.25 | DRL | PT-P | NDB | MADE PREPARATIONS & LIFTED BOP STACK WITH BOP TROLLEY.
43275.0521 | 43275.0938 | 1 | DRL | PT-P | WH | CENTRED CASING & SET 9 5/8" SLIP & SEAL ASSY IN CASING HEAD SPOOL (CHS). SLACKED OFF CASING WEIGHT ON SLIP & SEAL ASSY.
43275.0938 | 43275.1875 | 2.25 | DRL | PT-P | CC | ROUGH CUT 9 5/8" CASING. R/DOWN CEMENTING HEAD & L/DOWN 9 5/8" CASING PUP JOINT WITH CUT PIECE.
43275.1875 | 43275.2292 | 1 | DRL | PT-P | NDB | N/DOWN 13 5/8" - 10K SPACER SPOOL.
43275.2292 | 43275.375 | 3.5 | DRL | PT-P | CC | FINAL CUT 9 5/8" CASING @ 6.75" WITH WELLSERVE COLD CUTTER, BEVELLED & DRESSED THE SAME.
43275.375 | 43275.6042 | 5.5 | DRL | PT-P | WH | INSTALLED 13 5/8" - 10K BTM X 11" - 10K TOP TUBING HEAD SPOOL (THS) & TIGHTENED STUD BOLTS. P/TESTED FS SEALS, METAL SEAL & FLANGE @ 4800 PSI EACH FOR 15 MIN - OK. REPAIRED ONE DAMAGED TIE DOWN BOLT OF CASING HEAD SPOOL (CHS).
43275.6042 | 43275.8125 | 5 | DRL | PT-P | NUB | N/UP 13 5/8" - 10K BOP STACK. REPAIRED/MODIFIED & INSTALLED BELL NIPPLE, FLOW LINE & FILL UP LINE. CHANGED UPPER PIPE RAMS FROM 9 5/8" CSG RAM TO 4 1/2" - 7" VARIABLE PIPE RAM. FUNCTION TESTED BOP STACK - OK.
43275.8125 | 43275.9792 | 4 | DRL | PT-P | BOPT | HELD PJSM. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), TDS IBOP, FOSV, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE & LOWER PIPE RAM BOP (5" RAMS) @ 300/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG, SET WEAR BUSHING INSIDE THS, FUNCTION TESTED BLIND RAM & L/DOWN TEST PLUG ASSY.
43275.9792 | 43276 | 0.5 | DRL | PT-P | BHA | L/DOWN 4 X 5" HWDPS FROM DERRICK FOR INSPECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43276 | 43276.1042 | 2.5 | DRL | PT-P | BHA | L/DOWN 3 X 5" HWDPS (FOR INSPECTION) + 10 X 8" DCS FROM DERRICK.
43276.1042 | 43276.25 | 3.5 | DRL | PT-P | DP | L/DOWN 25 X 5 1/2" DP FROM DERRICK. BROKE OUT ALL DP CONNECTIONS WITH MANUAL TONGS DUE TO HIGH TORQUE.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | L/DOWN 5 1/2" DP
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | LIFTED BOP STACK & SET 9 5/8" SLIP & SEAL ASSY. ROUGH CUT 9 5/8" CSG & L/DOWN LANDING JOINT. INSTALLED & P/TESTED 13 5/8" - 10K X 11" - 10K TUBING HEAD SPOOL. N/UP & P/TESTED BOP STACK.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | L/DOWN REMAINING 5 1/2" DP FROM DERRICK. P/UP 5" DP FROM PIPERACKS SINGLE BY SINGLE.
REMARKS
Formulas:
DHARIAN - 1 = [KCL LIGNOSULPHONATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14