## DDR#187
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 187
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-11-07
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4864 | 4864 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 186.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4864 | 4864 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-11-06 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 40 | IN (M) |  | 4720( TOF) |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1119.4
DEPTH, MD (M) | 4864 | 4864 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | LIP GUIDE |  |  | 8.125 | 7.3125 |  | FJWP |  | 1.3 | 0.17092 |  | PITS (BBL) | 608
MW IN (SG) | 1.78 | 1.78 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | DRIVE SUB |  |  | 8.125 | 2.25 |  | 4 1/2 IF |  | 0.85 | 0.11176 |  | ACT. SYS (BBL) | 1727.4
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | 3 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 27.65 | 2.0293 |  | RESV. SYS (BBL) | 596
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | 9 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 83.23 | 10.9429 |  | KILL MUD (BBL) | 2.28
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | D. JAR |  |  | 6.375 | 2.75 |  | 4 1/2 IF |  | 9.9 | 1.3016 |  | KILL MW (SG) | 800
µ FUNNEL (SEC) | 59 | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | 3 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.64 | 3.6341 |  | TOTAL | 2323.4
PV | 43 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 9 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 83.79 | 6.1494 |  | DIESEL (LTR)
YIELD POINT | 32 | 31 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 105629
GEL ST. | 10/15 | 10/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 16008
WL (ml/30 min) | 3.4 | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 6420
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 121637
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 480000
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 90000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 39000
KCl (mg/l) | 59108 | 59107.7 | JAR | 5.1 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 44000
CHLORIDES (mg/l) | 29500 | 29500 | 5" HWDPS | 36.1 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 0
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS | 36.1 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 234.36 |  |  | MPCL | 6
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 2.4 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 28
SOLIDS % | 36.38 | 36.38 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 4.55 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 122
DAILY WELL COST (US$) |  | 40867 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14452939 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 72.61% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1428
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4808 | 500/510 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4808 | 675/665 |  |  | CHINJI | 338/338
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4808 | 820/815 |  |  | KAMLIAL | 1245/1245
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE / KULD | 1416/1416
KICK DRILL | 2019-10-31 | 2019-11-30 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI | 4576/4576
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR | 4667/4667
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-11-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL | 4756/4756
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43775 | 43775.1667 | 4 | DRL | NPT-UP | RIH | CONT'D RIH FROM 3010M TO 4529M.
43775.1667 | 43775.1771 | 0.25 | DRL | NPT-UP | CIR | BROKE CIRCULATION.
43775.1771 | 43775.1979 | 0.5 | DRL | NPT-UP | RIH | RIH FROM 4529M TO 4700M.
43775.1979 | 43775.2083 | 0.25 | DRL | NPT-UP | RIH | PRECAUTIONARY WASHED DOWN FROM 4700M TO 4716M, OBSERVED COMPRESSION AT 4716M. REAMED DOWN TO 4720M.
43775.2083 | 43775.375 | 4 | DRL | NPT-UP | F | WORKED ON FISH WITH GUIDED SCREW-IN SUB & BENT PIPE. ATTEMPTED TO SCREW IN WITH & WITHOUT CIRCULATION. SCREWED IN THE FISH AND P/UP STRING, OBSERVED FISH WEIGHT ALONG WITH 20 TONS O/PULL AND PRESSURE INCREASED FROM 325 PSI TO 1900 PSI (NO RETURN). SUDDENLY FISH WEIGHT DROPPED FOLLOWED BY SPP (FISH SLIPPED DOWN). ATTEMPTED TO SCREW IN FISH SEVERAL TIMES AGAIN. NO SUCCESS. TAGGED AND CONFIRM TOF AT 4720M.
43775.375 | 43775.4062 | 0.75 | DRL | NPT-UP | SP | SPOTTED 30BBL HI-VIS PRIOR POOH.
43775.4062 | 43775.4167 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED- WELL STATIC.
43775.4167 | 43775.4479 | 0.75 | DRL | NPT-UP | POOH | POOH GUIDED SCREW IN SUB FROM 4720M TO 4500M (INSIDE CSG).
43775.4479 | 43775.4583 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED- WELL STATIC.
43775.4583 | 43775.8438 | 9.25 | DRL | NPT-UP | POOH | POOH FROM 4500M TO 243M (TOP OF BHA)
43775.8438 | 43775.8542 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED- WELL STATIC.
43775.8542 | 43775.9375 | 2 | DRL | NPT-UP | BHA | POOH BHA FROM 243M TO SURFACE. L/DOWN D. JAR, 5'' BENT PIPE, DRIVE SUB, LIP GUIDE AND SCREW IN SUB.
43775.9375 | 43776 | 1.5 | DRL | NPT-UP | BHA | P/UP AND M/UP NEW LIP GUIDE + SCREW IN SUB ALONG WITH DRIVE SUB. RIH AS PER BHA TO 84M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-07
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43776 | 43776.0208 | 0.5 | DRL | NPT-UP | BHA | CONT'D RIH 84M TO 234 AS PER BHA.
43776.0208 | 43776.25 | 5.5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 234M TO 2885M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAMMAL / LIMESTONE, CLAYSTONE, MARL, SHALE
OPERATIONS AT 06:00 HRS |  |  | RIH WITH GUIDED SCREW IN SUB IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO TAG TOF AT 4720M, MADE SEVERAL ATTEMPTS TO CATCH AND RECOVER THE FISH, NO SUCCESS, SPOTTED 30 BBL HI-VIS PILL AND POOH TO SURFACE, L/DOWN FISHING BHA, P/UP AND M/UP NEW GUIDED SCREW IN SUB AND RIH TO 84M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH TO TAG TOF AT 4720M, FISHING JOB.
REMARKS |  |  | WASH PIPE ROTATING HRS = 41.23 ; CIRC HRS = 71.6 @ 0:00 HRS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15