## DDR#19
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 19
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-23
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD / HAMZA / ADNAN / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 1884 / 1884 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 18.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 1914 / 1914 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 126
2019-05-22 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MOD. LIGNO |  | HOLE SIZE (IN) |  | 17 1/2'' |  | BIT No. |  | 4 |  | BHA No. |  |  | 5 | IN (M) |  | 590 |  | OUT (M) |  |  | STRING (BBL) | 122
CHECK TIME | 15:00 | 23:45 | MD @ 00:00HR (M) |  | 1884 |  | SIZE (IN) |  | 17 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1728
DEPTH, MD (M) | 1824 | 1884 | TVD @ 00:00HR (M) |  | 1884 |  | MANUFACTURER |  | NOV |  | 17 1/2'' PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 853
MW IN (SG) | 1.35 | 1.39 | DAILY PROGRESS (M) |  | 126 |  | TYPE |  | TFH519S |  | PD |  |  | 9 | 5.125 |  | 7 5/8 REG |  | 4.29 | 1.3667 |  | ACT. SYS (BBL) | 2703
MW OUT (SG) | 1.35 | 1.36 | INST. ROP (M/HR) |  | 8.6 |  | SERIAL NO. |  | E260745 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.76 | 0.24212 |  | RESV. SYS (BBL) | 972
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 8.71 |  | IADC CODE |  | S422 |  | MUD MOTOR (SLEEVE STAB) |  |  | 9.625 | 7 |  | 6 5/8 REG |  | 10.53 | 3.3546 |  | KILL MUD (BBL) | 550
FL TEMP. °F |  | 147.2 | AVG. WOB (TON) |  | 13 |  | NOZZLES |  | 3X 18, 2 X 16 |  | X/O |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.1 | 0.35043 |  | KILL MW (SG) | 1.97
µ FUNNEL (SEC) | 47 | 50 | AVG. RPM SURFACE |  | 47 |  | DEPTH IN (M) |  | 590 |  | FLOAT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | TOTAL | 3675
PV | 19 | 22 | AVG. RPM DOWNHOLE |  | 150 |  | DEPTH OUT (M) |  |  |  | ST. STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.44 | 0.77732 |  | DIESEL (LTR)
YIELD POINT | 30 | 29 | FLOWRATE (GPM) |  | 920 |  | METERAGE (M) |  | 1294 |  | LOWER S. SUB |  |  | 9.625 | 3.5 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | RIG TANK | 78797
GEL ST. | 8/9 | 10/13 | PRESSURE (PSI) |  | 2800 |  | RPM SURF. |  | 40-70 |  | SLIM PULSE |  |  | 9.5625 | 5 |  | 7 5/8 REG |  | 9.27 | 2.9532 |  | CAMP TANK | 19110
WL (ml/30 min.) | 4.8 | 4.9 | TORQ. ON-BTM (KLB-FT) |  | 8-13 |  | RPM BTM. |  | 140-170 |  | UPPER S. SUB |  |  | 9.5625 | 3 |  | 7 5/8 REG |  | 0.67 | 0.21344 |  | CONSUMED | 12680
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 5-18 |  | ST. STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.37 | 0.75502 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 125 |  | AVG. ROP (M/HR) |  | 15.0064 |  | NMDC |  |  | 9 | 3.5 |  | 7 5/8 REG |  | 9.36 | 2.9818 |  | TOTAL | 97907
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  | 126 |  | BIT ROT HRS. |  | 86.23 |  | 3 X 9 1/2'' DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.53 | 8.7703 |  | WATER (LTR)
PH | 9 | 9.5 | SLACK-OFF WT. (TON) |  | 123 |  | K-REVS IN 24 HRS |  | 128.14 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29627 |  | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 861.02 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CAMP STORAGE | 80000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 25.7 |  | D. JAR |  |  | 7.9375 | 3.0625 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | CONSUMED | 182200
KCl (mg/l) | 57010 | 56247.7 | JAR | 119.61 | NMDC | 109.6 | JET VELOCITY (M/SEC) |  | 77.19 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | RECEIVED | 87200
CHLORIDES (mg/l) | 27000 | 26500 | MOTOR | 109.6 | STAB - 1 | 109.6 | TFA (IN²) |  | 1.138 |  | X/O |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | TOTAL
HARDNESS (mg/l) | 420 | 400 | 9 1/2" DCS | 119.61 | STAB - 2 | 109.6 | HSI |  | 1.419 |  | 10 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 3.4703 |  | POB
SAND % |  |  | 8" DCS | 119.61 | SPSA | 109.6 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 212.69 |  |  | MPCL | 6
LUBRICANT % | 0.5 | 0.5 | BHA ROT. HRS |  | 109.6 |  | BIT No. 4 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 25
SOLIDS % | 11.58 | 13.13 | ON BOTTOM HRS |  | 14.46 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 23 |  |  | SECURITY | 2
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 19.3 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 56
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 100 | 2 X 100 |  | 30" CONDUCTOR |  |  | 37 | 1781/1781 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 120
DAILY WELL COST (US$) |  | 71005 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | 1810/1810 |  | 0.14 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2374153 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 1838/1838 |  | 0.11 | [6 empty] | MWD |  | LAST CSG SIZE | 20''
% OF AFE SPENT |  | 11.93% | MUD CLEANER | 2 X 140, 1 x 170 | [6 empty] | 1867/1867 |  | 0.19 | [6 empty] | MWD |  | LOT (EMW) | 1.95
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 494
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS.PSI |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 1882 | 250 / 250 / 250 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 1882 | 320 / 320 / 300 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 1882 | 400 / 400 / 350 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 10 | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-05-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43607 | 43607.1771 | 4.25 | DRL | PT-P | DM | CONT'D DRILLING 17.5" HOLE FROM 1758M TO 1787M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY PRIOR TO CONNECTION.
43607.1771 | 43607.25 | 1.75 | DRL | PT-P | CIR | SWEPT OUT 30 BBL HI-VIS PILL, KEPT CIRCULATING TILL SHAKERS CLEAN PRIOR TO WIPER TRIP.
43607.25 | 43607.2604 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43607.2604 | 43607.4167 | 3.75 | DRL | PT-P | WT | POOH FROM 1787M TO 1357M. HOLE CONDITION, GOOD. RIH BACK TO BOTTOM AT 1787M. WASHED DOWN LAST STAND.
43607.4167 | 43608 | 14 | DRL | PT-P | DM | RESUMED DRILLING. DRILLED 17.5'' HOLE FROM 1787M TO 1884M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY PRIOR TO CONNECTION. WHILE DRILLING INCREASED MUD WT. GRADUALLY FROM 1.35 SG TO 1.36 SG.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43608 | 43608.0208 | 0.5 | DRL | PT-P | DM | CONT'D DRILLING 17.5" HOLE FROM 1884M TO 1886M.
43608.0208 | 43608.0521 | 0.75 | DRL | NPT-UP | RR | WORKED ON MP-3 (CHANGED LINER), MEANWHILE CIRCULATED TO CLEAN HOLE.
43608.0521 | 43608.1667 | 2.75 | DRL | PT-P | DM | CONT'D DRILLING 17.5" HOLE FROM 1886M TO 1902M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY PRIOR TO CONNECTION. WHILE DRILLING INCREASED MUD WT. GRADUALLY FROM 1.36SG TO 1.40SG.
43608.1667 | 43608.1875 | 0.5 | DRL | NPT-UP | RR | WORKED ON MP-3 (POP OFF VALVE ACTIVATED, CHANGED SAME), MEANWHILE CIRCULATED TO CLEAN HOLE.
43608.1875 | 43608.25 | 1.5 | DRL | PT-P | DM | CONT'D DRILLING 17.5" HOLE FROM 1902M TO 1914M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | DRILLING 17.5'' HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 17.5'' HOLE DOWN TO 1787M, PERFORMED WIPER TRIP TO 1357M, HOLE CONDITION,GOOD, RIH TO 1787M, DRILLED DOWN 17.5'' HOLE TO 1884M. MEANWHILE INCREASED MUD WT. GRADUALLY FROM 1.35 SG TO 1.36SG.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17.5'' HOLE DOWN TO 2074M, PERFORM WIPER TRIP TO 1787M, DRILL AHEAD 17 1/2'' HOLE.
REMARKS |  |  | PUMPED 20 BBL HI-VIS BRIDGE PILL AT EVERY STAND.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14