## DDR#190
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 190
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-06-29
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4535 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 189.5833
RIG REP. (TP): |  | JAVED IQBAL / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4535 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-06-28 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT No. |  | 9RR1 |  | BHA No. |  |  | 24 | IN (M) |  | 4535 |  | OUT (M) |  |  | STRING (BBL) | 181
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 697
DEPTH, MD (M) |  | 4535 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.25 | 0.034239 |  | PITS (BBL) | 503
MW IN (SG) |  | 2.14 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SB137C |  | 9 5/8" CSG SCRAPER |  |  | 9.625 | 2.25 |  | 4 1/2 REG |  | 1.23 | 0.16846 |  | ACT. SYS (BBL) | 1381
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RH3659 |  | BIT SUB (F.V) |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 1.07 | 0.14654 |  | RESV. SYS (BBL) | 1662
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 137 |  | 14 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 129.62 | 17.7523 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3 X OPEN |  | DRILLING JAR |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 6.07 | 0.83133 |  | KILL MW (SG)
µ FUNNEL (SEC) |  | 58 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4535 |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | TOTAL | 3043
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.03 | 6.2546 |  | DIESEL (LTR)
YIELD POINT |  | 21 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 127000
GEL ST. |  | 12/26 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 22700
WL (ml/30 min.) |  | 4.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 7150
CT ( in/32) |  | 1.5 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 149700
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 121160
KCl (mg/l) |  | 29553.9 | JAR | 9.51 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 121160
CHLORIDES |  | 14000 | 5" HWDPS | 9.51 | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 390000
CALCIUM |  | 260 | 6 1/2" DCS | 9.51 |  |  | HSI | [14 empty] | POB
OIL % |  | 5 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 231.53 |  |  | MPCL | 3
LUBE % |  |  | BHA ROT. HRS |  | 9.51 |  | BIT No. 9 |  | 2-1-WT-A-E-I-BT-BHA |  | BHA WT. IN MUD (TON) | [7 empty] | 19.2597 |  |  | MPCL SERV | 23
SOLIDS % |  | 37.52 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 13.1779 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 15.91 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | 4439 |  | 0.97 |  | 100.7 |  |  | 0.46 |  | EMS |  | TOTAL | 120
DAILY WELL COST (US$) |  | 40432.958 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4467 |  | 0.72 |  | 125.2 |  |  | 0.46 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 12824343.6317 | SHAKER-3 | 2 x 50 | 1 x 50 |  | 9 5/8" PRODUCTION CSG |  |  | 4533 | 4496 |  | 0.79 |  | 108.12 |  |  | 0.24 |  | EMS |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 71.05% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.6 |  | 154.31 |  |  | 0.59 |  | EMS |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43279 | 43279.2604 | 6.25 | DRL | PT-P | POOH | POOH FROM 3185M TO TOP OF BHA @ 230M.
43279.2604 | 43279.3125 | 1.25 | DRL | PT-P | BHA | POOH BHA FROM 230M TO SURFACE.
43279.3125 | 43279.375 | 1.5 | DRL | PT-P | BHA | M/UP & RIH SAME 8 1/2" TRICONE BIT (RR) WITH 9 5/8" CSG SCRAPER TO 231M.
43279.375 | 43279.75 | 9 | DRL | PT-P | RIH | RIH SCRAPER FROM 231M TO 4450M. WHILE RIH FILLED UP STRING AFTER EVERY 15 STANDS.
43279.75 | 43279.8125 | 1.5 | DRL | PT-P | COC | WORKED ON SCRAPER WITH ROTATION, TWICE ON EACH STAND FROM 4450M TO 4529M.
43279.8125 | 43279.8854 | 1.75 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE TILL SHAKERS CLEAN. PUMPED SLUG.
43279.8854 | 43280 | 2.75 | DRL | PT-P | POOH | POOH FROM 4529M TO 3244M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-06-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43280 | 43280.25 | 6 | DRL | PT-P | POOH | CONT'D POOH FROM 3244M TO TOP OF BHA @ 231M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | POOH
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH BIT FROM 315M TO SURFACE. M/UP & RIH SAME 8 1/2" TRICONE BIT (RR) WITH 9 5/8" CSG SCRAPER TO 4529M & SCRAPED CSG TWICE FROM 4450M TO 4529M. CIRCULATED TO CLEAN HOLE & POOH FROM 4529M TO 3244M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH TO SURFACE. RECORD CBL-VDL W/LINE LOGS. M/UP & RIH NEW 8 1/2" TCI BIT WITH 02 X STRING STABS.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14