## DDR#192
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 192
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-11-12
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4864 | 4864 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 191.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4864 | 4864 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-11-11 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 43 | IN (M) |  | 4720( TOF) |  | OUT (M) |  |  | STRING (BBL) | 220
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 823
DEPTH, MD (M) | 4864 | 4864 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | WASHOVER SHOE |  |  | 8.375 | 7.25 |  | FJWP |  | 1.64 | 0.21562 |  | PITS (BBL) | 659
MW IN (SG) | 1.78 | 1.78 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | 6 X WASHPIPES |  |  | 8.125 | 7.3125 |  | FJWP |  | 55.57 | 7.3062 |  | ACT. SYS (BBL) | 1702
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | DRIVE SUB |  |  | 8.125 | 2.25 |  | FJWP |  | 0.56 | 0.041099 |  | RESV. SYS (BBL) | 586
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | BIT SUB (F.V) |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 1.07 | 0.14068 |  | KILL MUD (BBL) | 800
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 9 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 83.23 | 10.9429 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 59 | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | D.JAR |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 9.73 | 0.71409 |  | TOTAL
PV | 44 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 3 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.64 | 3.6341 |  | DIESEL (LTR)
YIELD POINT | 31 | 29 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 12 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.44 | 8.1787 |  | RIG TANK | 84552
GEL ST. | 10/15 | 09/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 13035
WL (ml/30 min) | 3.6 | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4686
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 97587
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 475000
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 72000
KCl (mg/l) | 57201 | 57201 | JAR | 10.6 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 62000
CHLORIDES (mg/l) | 29000 | 29000 | 5" HWDPS | 59.2 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 127600
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS | 59.2 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 290.88 |  |  | MPCL | 6
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 10.6 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 19 |  |  | MPCL SERV | 21
SOLIDS % | 36.5 | 36.5 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 11 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 10.9 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 116
DAILY WELL COST (US$) |  | 40735 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14649940 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 73.6% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1428
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4808 | 500/510 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4808 | 675/665 |  |  | CHINJI | 338/338
FIRE DRILL | 2019-10-08 | 2019-11-07 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4808 | 820/815 |  |  | KAMLIAL | 1245/1245
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE / KULD | 1416/1416
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI | 4576/4576
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR | 4667/4667
STRETCHER DRILL | 2019-10-08 | 2019-11-07 | NEXT BOP TEST DATE |  | 2019-11-13 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL | 4756/4756
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43780 | 43780.3958 | 9.5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 1354M TO 4643M. FILLED UP STRING AFTER EVERY 15 STDS. OBSERVED COMPRESSION AT 4643M.
43780.3958 | 43780.4479 | 1.25 | DRL | NPT-UP | RW | WASHED / REAMED DOWN FROM 4643M TO TOF AT 4720M.
43780.4479 | 43780.7292 | 6.75 | DRL | NPT-UP | F | SUCCESSFULLY SWALLOWED THE FISH FOLLOWED BY COMMENCEMENT OF WASHING OVER BELOW 4720M. WASHED OVER FISH (5 JTs 6 1/2'' DC + PBL SUB) FROM 4720M TO 4771M. MEANWHILE P/UP STRING TO CHECK INTERMITTENTLY, OK. ( WASHOVER PARAMETERS: GPM: 215-300, WOB: 1-8 T, RPM : 30-40, SPP : 1000-1800 PSI)
43780.7292 | 43780.8125 | 2 | DRL | NPT-UP | CIR | CIRCULATED FOR BTM UP. KEPT CIRCULATING TO CONDITION MUD.
43780.8125 | 43780.8229 | 0.25 | DRL | NPT-UP | RW | PUMPED OUT OF HOLE FROM 4771M TO 4719M.
43780.8229 | 43780.8438 | 0.5 | DRL | NPT-UP | SP | SPOTTED 25 BBL HI-VIS PILL PRIOR POOH. MEANWHILE REAMED / WASHED DOWN FROM 4719M TO 4725M.
43780.8438 | 43780.875 | 0.75 | DRL | NPT-UP | POOH | POOH FROM 4725M TO 4546M (INSIDE CSG).
43780.875 | 43780.8854 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43780.8854 | 43780.8958 | 0.25 | DRL | NPT-UP | RS | SERVICED TDS.
43780.8958 | 43781 | 2.5 | DRL | NPT-UP | POOH | POOH FROM 4546M TO 3288M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43781 | 43781.25 | 6 | DRL | NPT-UP | POOH | CONT'D POOH FROM 3288M TO 490M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAMMAL / LIMESTONE, CLAYSTONE, MARL, SHALE
OPERATIONS AT 06:00 HRS |  |  | POOH WASHOVER SHOE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO 4643M, OBSERVED COMPRESSION, REAMED/WASHED DOWN FROM 4643M TO 4720M (TOF), WASHED OVER FROM 4720M TO 4771M, SPOTTED 25 BBL HI-VIS, POOH TO 3288M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | FISHING JOB (ATTEMPT TO RETRIEVE FISH)
REMARKS |  |  | WASH PIPE ROTATING HRS = 64.31 ; CIRC HRS = 98.68 @ 0:00 HRS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21