## DDR#193
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 193
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-02
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4562 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 192.5833
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4565 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 16
2018-07-01 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 10 |  | BHA No. |  |  | 25 | IN (M) |  | 4535 |  | OUT (M) |  |  | STRING (BBL) | 258
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4562 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 688
DEPTH, MD (M) | 4550 | 4562 | TVD @ 00:00HR (M) |  | 4562 |  | MANUFACTURER |  | SMITH |  | TRICONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.24 | 0.03287 |  | PITS (BBL) | 733
MW IN (SG) | 1.5 | 1.5 | DAILY PROGRESS (M) |  | 16 |  | TYPE |  | SB537 |  | BIT SUB (F.V) |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 1.07 | 0.14654 |  | ACT. SYS (BBL) | 1679
MW OUT (SG) | 1.5 | 1.5 | INST. ROP (M/HR) |  | 0.4 |  | SERIAL NO. |  | RJ2252 |  | 2 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 18.51 | 2.5351 |  | RESV. SYS (BBL) | 908
ECD (SG) | 1.57 | 1.57 | AVG. ROP (M/HR) |  | 0.71269 |  | IADC CODE |  | 537 |  | STRING STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.39 | 0.19037 |  | KILL MUD (BBL) | 600
FL TEMP. °F | 141 | 142 | AVG. WOB (TON) |  | 8 - 12 |  | NOZZLES |  | 3 X OPEN |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 59 | 58 | AVG. RPM SURFACE |  | 60 |  | DEPTH IN (M) |  | 4535 |  | STRING STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.61 | 0.2205 |  | TOTAL | 3187
PV | 32 | 32 | AVG. RPM DOWNHOLE |  | 60 |  | DEPTH OUT (M) |  |  |  | 11 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 101.85 | 13.949 |  | DIESEL (LTR)
YIELD POINT | 23 | 24 | FLOWRATE (GPM) |  | 510 |  | METERAGE (M) |  | 27 |  | DRILLING JAR |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 6.07 | 0.83133 |  | RIG TANK | 108500
GEL ST. | 6/11 | 6/10 | PRESSURE (PSI) |  | 2850 - 3000 |  | RPM SURF. |  | 60 |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | CAMP TANK | 20750
WL (ml/30 min.) | 3.6 | 3.8 | TORQ. ON-BTM (KLB-FT) |  | 5 - 6 |  | RPM BTM. |  | 60 |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.03 | 6.2546 |  | CONSUMED | 8650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 4 - 5 |  | WOB (TON) |  | 5 -12 | [12 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 165 |  | AVG. ROP (M/HR) |  | 0.8354 | [12 empty] | TOTAL | 129250
ALK (FILT.) | 0.5 | 0.6 | PICK-UP WT. (TON) |  | 167 |  | BIT ROT HRS. |  | 32.32 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 160 |  | K-REVS IN 24 HRS |  | 83.514 | [12 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS |  | 119.046 | [12 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 80 | [12 empty] | CONSUMED | 202900
KCl (mg/l) | 51976.6 | 50908.9 | JAR | 45.81 | STAB - 1 | 36.3 | JET VELOCITY (M/SEC) |  | 21.2 | [12 empty] | RECEIVED | 252900
CHLORIDES | 23500 | 23000 | 5" HWDPS | 45.81 | STAB - 2 | 36.3 | TFA (IN²) |  | 2.356 | [12 empty] | TOTAL | 385000
CALCIUM | 220 | 220 | 6 1/2" DCS | 45.81 |  |  | HSI |  | 0.3 | [12 empty] | POB
OIL % | 2 | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 233.29 |  |  | MPCL | 3
LUBE % |  |  | BHA ROT. HRS |  | 45.81 |  | BIT No. 10 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 21.5976 |  |  | MPCL SERV | 17
SOLIDS % | 16.86 | 17.29 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14.8391 |  |  | SECURITY | 4
M.B.T. | 8 | 8 | CIRC. HRS |  | 58.53 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 22
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | 4439 |  | 0.97 |  | 100.7 |  |  | 0.46 |  | EMS |  | TOTAL | 110
DAILY WELL COST (US$) |  | 38410.9769 | SHAKER-2 | 2 x 140 | 1 x 140 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4467 |  | 0.72 |  | 125.2 |  |  | 0.46 |  | EMS |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 12946623.09 | SHAKER-3 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4496 |  | 0.79 |  | 108.12 |  |  | 0.24 |  | EMS |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 71.73% | MUD CLEANER | 1 x 170 + 2 x 140 |  |  | 7" LINER |  |  |  | 4525 |  | 0.6 |  | 154.31 |  |  | 0.59 |  | EMS |  | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4543 |  | 415/420 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4543 |  | 600/620 |  | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4543 |  | 850/860 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 17 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43282 | 43283 | 24 | DRL | PT-P | D | DRILLED AHEAD 8 1/2" HOLE FROM 4546M TO 4562M. REAMED DRILLED SECTION PRIOR CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43283 | 43283.25 | 6 | DRL | PT-P | D | DRILLED AHEAD 8 1/2" HOLE FROM 4562M TO 4565M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE & SANDSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2" HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED AHEAD 8 1/2" HOLE FROM 4546M TO 4562M. REAMED DRILLED SECTION PRIOR CONNECTION.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" HOLE.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14