## DDR#193
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 193
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-11-13
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4864 | 4864 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 192.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4864 | 4864 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-11-12 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  | 44 | IN (M) |  | 4720( TOF) |  | OUT (M) |  |  | STRING (BBL) | 250
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 773.6
DEPTH, MD (M) | 4864 | 4864 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | OVERSHOT GUIDE |  |  | 8.125 | 6.6875 |  | MFC |  | 0.12 | 0.015777 |  | PITS (BBL) | 709
MW IN (SG) | 1.78 | 1.78 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | OVERSHOT |  |  | 8.125 | 6.5 |  | MFC |  | 0.51 | 0.067054 |  | ACT. SYS (BBL) | 1732.6
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | EXTENSION #1 |  |  | 8.125 | 6.625 |  | MFC |  | 0.92 | 0.06752 |  | RESV. SYS (BBL) | 543
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | EXTENSION #2 |  |  | 6.5 | 6.625 |  | MFC |  | 0.84 | 0.11044 |  | KILL MUD (BBL) | 800
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | TOP SUB |  |  | 6.5 | 3.75 |  | 4 1/2 IF |  | 0.37 | 0.048647 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 65 | 64 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | 1 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 9.21 | 0.67593 |  | TOTAL
PV | 44 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 3 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.79 | 3.6538 |  | DIESEL (LTR)
YIELD POINT | 29 | 30 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | D.JAR |  |  | 6.25 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71629 |  | RIG TANK | 79477
GEL ST. | 10/15 | 09/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 3 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.77 | 3.6511 |  | CAMP TANK | 12497
WL (ml/30 min) | 3.5 | 3.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 9 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 83.5 | 6.1281 |  | CONSUMED | 5613
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 91974
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 475000
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 104000
KCl (mg/l) | 58154 | 58154 | JAR | 0.7 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 104000
CHLORIDES (mg/l) | 29500 | 29500 | 5" HWDPS | 59.99 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 0
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS | 59.99 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 160.79 |  |  | MPCL | 6
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 0.7 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 12 |  |  | MPCL SERV | 26
SOLIDS % | 36.5 | 36.5 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 4 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 1.6 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 28
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 124
DAILY WELL COST (US$) |  | 36941 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14686881 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 73.78% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1428
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4808 | 500/510 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4808 | 675/665 |  |  | CHINJI | 338/338
FIRE DRILL | 2019-11-09 | 2019-12-09 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4808 | 820/815 |  |  | KAMLIAL | 1245/1245
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE / KULD | 1416/1416
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | CHORGALI | 4576/4576
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-10-23 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR | 4667/4667
STRETCHER DRILL | 2019-11-09 | 2019-12-09 | NEXT BOP TEST DATE |  | 2019-11-13 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL | 4756/4756
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43781 | 43781.2708 | 6.5 | DRL | NPT-UP | POOH | CONT'D POOH FROM 3288M TO 290M.
43781.2708 | 43781.2812 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43781.2812 | 43781.3646 | 2 | DRL | NPT-UP | BHA | POOH BHA FROM 290M TO SURFACE. B/OUT AND L/DOWN SGL BY SGL D. JAR , 6 X WASHPIPES & WASHOVER SHOE. INSPECTED SAME.
43781.3646 | 43781.4062 | 1 | DRL | NPT-UP | BHA | P/UP AND M/UP OVERSHOT ASSEMBLY (GUIDE + O/SHOT + 2X EXTENSION + TOP SUB). RIH AS PER BHA TO 162M.
43781.4062 | 43781.7917 | 9.25 | DRL | NPT-UP | RIH | RIH FISHING ASSEMBLY FROM 162M TO 4530M.
43781.7917 | 43781.8021 | 0.25 | DRL | NPT-UP | CIR | BROKE CIRCULATION.
43781.8021 | 43781.8229 | 0.5 | DRL | NPT-UP | RIH | CONT'D RIH FROM 4530M TO 4704M.
43781.8229 | 43781.8333 | 0.25 | DRL | NPT-UP | FC | CONNECTED TDS, PRECAUTIONARY WASHED DOWN FROM 4704M TO TAG TOF AT 4720M.
43781.8333 | 43781.8646 | 0.75 | DRL | NPT-UP | F | WORKED ON OVERSHOT, ENGAGED FISH SUCCESSFULLY WITH SLOW CIRCULATION & ROTATION. P/UP STRING, OBSERVED O/PULL (FISH LATCHED). ESTABLISHED CIRCULATION THROUGH PBL SUB, SPP INCREASED (MAX 2000 PSI). RELEASED/PULLED OUT FISH WITH UPWARD JARRING (MAX. O/PULL 50 TON). FISH WEIGHT ADDED IN STRING.
43781.8646 | 43781.8958 | 0.75 | DRL | NPT-UP | POOH | POOH ALONG WITH FISH FROM 4720M TO 4586M. WHILE POOH OBSERVED TIGHT SPOTS AT 4718M TO 4716M, 4669M TO 4667M. CLEARED SAME WITH UPWARD JARRING (MAX. 40-50 TON).
43781.8958 | 43781.9271 | 0.75 | DRL | NPT-UP | F | WHILE POOH AT 4586M OBSERVED TIGHT SPOT. ATTEMPTED TO RELEASE STRING WITH UPWARD JARRING (MAX O/PULL 60-70 TON). OBSERVED STRING WEIGHT DROPPED. TAGGED AGAIN TOF AT 4586M. ATTEMPTED TO ENGAGE FISH (OBSERVED INCREASE IN PRESSURE BUT FISH IS NOT LATCHED). DECIDED TO POOH AND CHECK CONDITION OF OVERSHOT ASSEMBLY.
43781.9271 | 43781.9375 | 0.25 | DRL | NPT-UP | POOH | POOH FROM 4586M TO 4530M (INSIDE CSG)
43781.9375 | 43781.9479 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43781.9479 | 43782 | 1.25 | DRL | NPT-UP | POOH | POOH FROM 4530M TO 3990M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-13
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43782 | 43782.25 | 6 | DRL | NPT-UP | POOH | CONT'D POOH FROM 3990M TO 764M
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | NAMMAL / LIMESTONE, CLAYSTONE, MARL, SHALE
OPERATIONS AT 06:00 HRS |  |  | POOH OVERSHOT ASSEMBLY IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH FROM 3288M TO SURFACE. L/DOWN WASHOVER ASSEMBLY, P/UP AND M/UP OVERSHOT ASSEMBLY, RIH TO TAG TOF AT 4720M, ATTEMPTED TO ENGAGE FISH, SUCCESSFUL, POOH ALONG WITH FISH TO 4586M, OBSERVED TIGHT HOLE, ATTEMPTED TO RELEASE WITH UPWARD JARRING, OBSERVED FISH SLIPPED, TAGGED TOF AT 4586M, ATTEMPTED TO ENGAGE FISH AGAIN, NO SUCCESS, POOH O/SHOT ASSY TO 3990M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | FISHING JOB (ATTEMPT TO RETRIEVE FISH)
REMARKS |  |  | WASH PIPE ROTATING HRS = 65.01 ; CIRC HRS = 100.28 @ 0:00 HRS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21