## DDR#197
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 197
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-06
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / AHSEN / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4724 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 196.5833
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4736 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 62
2018-07-05 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 11 |  | BHA No. |  |  | 26 | IN (M) |  | 4580 |  | OUT (M) |  |  | STRING (BBL) | 267
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4724 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 712.6
DEPTH, MD (M) | 4695 | 4724 | TVD @ 00:00HR (M) |  | 4724 |  | MANUFACTURER |  | BAKER |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.37 | 0.050674 |  | PITS (BBL) | 804
MW IN (SG) | 1.5 | 1.5 | DAILY PROGRESS (M) |  | 62 |  | TYPE |  | TD506FX |  | BIT SUB (F.V) |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 1.07 | 0.14654 |  | ACT. SYS (BBL) | 1783.6
MW OUT (SG) | 1.5 | 1.5 | INST. ROP (M/HR) |  | 2.82 |  | SERIAL NO. |  | 5280230 |  | 2 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 18.51 | 2.5351 |  | RESV. SYS (BBL) | 636
ECD (SG) | 1.57 | 1.57 | AVG. ROP (M/HR) |  | 2.8 |  | IADC CODE |  | - |  | STRING STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.39 | 0.19037 |  | KILL MUD (BBL) | 600
FL TEMP. °F | 148 | 148 | AVG. WOB (TON) |  | 5 - 10 |  | NOZZLES |  | 6 X OPEN |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 60 | 61 | AVG. RPM SURFACE |  | 120 |  | DEPTH IN (M) |  | 4580 |  | STRING STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.61 | 0.2205 |  | TOTAL | 3019.6
PV | 37 | 39 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH OUT (M) |  |  |  | 11 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 101.85 | 13.949 |  | DIESEL (LTR)
YIELD POINT | 28 | 27 | FLOWRATE (GPM) |  | 500 |  | METERAGE (M) |  | 144 |  | DRILLING JAR |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 6.07 | 0.83133 |  | RIG TANK | 121000
GEL ST. | 5/8 | 6/12 | PRESSURE (PSI) |  | 2650 - 2900 |  | RPM SURF. |  | 120 |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | CAMP TANK | 18150
WL (ml/30 min.) | 3.3 | 3.4 | TORQ. ON-BTM (KLB-FT) |  | 7 - 9 |  | RPM BTM. |  | 120 |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.03 | 6.2546 |  | CONSUMED | 10650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3 - 6 |  | WOB (TON) |  | 5 - 10 | [12 empty] | RECEIVED
ALK (MUD) | 0.3 | 0.4 | STRING WT. (TON) - ROT |  | 170 |  | AVG. ROP (M/HR) |  | 3.6163 | [12 empty] | TOTAL | 139150
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  | 178 |  | BIT ROT HRS. |  | 39.82 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 162 |  | K-REVS IN 24 HRS |  | 159.46 | [12 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS |  | 285.89 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 89.86 | [12 empty] | CONSUMED | 230030
KCl (mg/l) | 50908.9 | 50649.6 | JAR | 119.03 | STAB - 1 | 109.52 | JET VELOCITY (M/SEC) |  | 10.4 | [12 empty] | RECEIVED | 280030
CHLORIDES | 23000 | 22900 | 5" HWDPS | 119.03 | STAB - 2 | 109.52 | TFA (IN²) |  | 4.71 | [12 empty] | TOTAL | 490000
CALCIUM | 240 | 240 | 6 1/2" DCS | 119.03 |  |  | HSI |  | 0.1 | [12 empty] | POB
OIL % | 2 | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 233.42 |  |  | MPCL | 5
LUBE % |  |  | BHA ROT. HRS |  | 119.03 |  | BIT No. 11 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 21.612 |  |  | MPCL SERV | 15
SOLIDS % | 18.2 | 18.56 | ON BOTTOM HRS |  | 98.82 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 14.8535 |  |  | SECURITY | 4
M.B.T. | 8 | 8 | CIRC. HRS |  | 132.56 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 15
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 110
DAILY WELL COST (US$) |  | 40539 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 13149877 | SHAKER-3 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 72.86% | MUD CLEANER | 2 x 140 + 1 x 120 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P3) | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4728 |  | 480/600 |  | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4728 |  | 480/600 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 19 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43286 | 43286.1458 | 3.5 | DRL | PT-P | D | DRILLED AHEAD 8 1/2" HOLE FROM 4662M TO 4671M. REAMED DRILLED SECTION PRIOR CONNECTION.
43286.1458 | 43286.1667 | 0.5 | DRL | PT-P | RS | SERVICED TDS.
43286.1667 | 43287 | 20 | DRL | PT-P | D | DRILLED AHEAD 8 1/2" HOLE FROM 4671M TO 4724M. REAMED DRILLED SECTION PRIOR CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-06
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43287 | 43287.25 | 6 | DRL | PT-P | D | DRILLED AHEAD 8 1/2" HOLE FROM 4724M TO 4736M. REAMED DRILLED SECTION PRIOR CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2" HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2'' HOLE FROM 4662M TO 4724M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" HOLE.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14