## DDR#199
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 199
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-11-19
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 4866 | 4866 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 198.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4866 | 4866 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 2
2019-11-18 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8.5 |  | RUN NO. |  |  | 34 |  | BHA NO. |  |  | 47 | IN (M) |  | 4864 |  | OUT (M) | 4866 |  | STRING (BBL) | 260
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4866 |  | BIT NO. |  |  | 19 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 758.3
DEPTH, MD (M) | 4864 | 4864 | TVD @ 00:00HR (M) |  | 4866 |  | SIZE (IN) |  |  | 8.5 |  | TC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.25 | 0.03287 |  | PITS (BBL) | 816
MW IN (SG) | 1.8 | 1.8 | DAILY PROGRESS (M) |  | 2 |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 6.375 | 3.75 |  | 4 1/2 IF |  | 1.07 | 0.14068 |  | ACT. SYS (BBL) | 1834.3
MW OUT (SG) | 1.8 |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MFDGH |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.24 | 0.67813 |  | RESV. SYS (BBL) | 341
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 0.69 |  | SERIAL NO. |  |  | RL0945 |  | ST.STAB |  |  | 8.375 | 2.75 |  | 4 1/2 IF |  | 1.88 | 0.24718 |  | KILL MUD (BBL) | 800
FL TEMP. °F | 148 |  | AVG. WOB (TON) |  | 6 |  | IADC CODE |  |  | 137 |  | 1 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.26 | 1.2175 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 62 | 58 | AVG. RPM SURFACE |  | 100 |  | NOZZLES (1/32") |  |  | 3 X 18 |  | ST.STAB |  |  | 8.375 | 2.75 |  | 4 1/2 IF |  | 1.55 | 0.11376 |  | TOTAL
PV | 45 | 45 | AVG. RPM DOWNHOLE |  | 100 |  | DEPTH IN (M) |  |  | 4864 |  | 6 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 55.46 | 7.2918 |  | DIESEL (LTR)
YIELD POINT | 31 | 29 | FLOWRATE (GPM) |  | 460-470 |  | DEPTH OUT (M) |  |  | 4866 |  | D-JAR |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.76 | 0.71629 |  | RIG TANK | 93234
GEL ST. | 11/16 | 10/16 | PRESSURE (PSI) |  | 3500-3600 |  | METERAGE (M) |  |  | 2 |  | 3 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.64 | 3.6341 |  | CAMP TANK | 9073
WL (ml/30 min) | 3.6 | 3.4 | TORQ. ON-BTM (KLB-FT) |  | 3-4 |  | RPM SURF. |  |  | 100-110 |  | 12 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 111.44 | 8.1787 |  | CONSUMED | 8751
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 2-2.5 |  | RPM BTM. |  |  | 100-110 | [12 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 168 |  | WOB (TON) |  |  | 4-6 | [12 empty] | TOTAL | 102307
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  | 170 |  | AVG. ROP (M/HR) |  |  | 0.69204 | [12 empty] | WATER (LTR)
pH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 163 |  | BIT ROT HRS. |  |  | 2.89 | [12 empty] | RIG STORAGE | 435000
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 18.12 | [12 empty] | CAMP STORAGE | 64000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 18.12 | [12 empty] | CONSUMED | 183300
KCl (mg/l) | 56247.7 | 55294.2 | JAR | 43.4 | STAB - 1 | 40.8 | ANN. VEL. (M/MIN) |  |  | 81.1 | [12 empty] | RECEIVED | 177300
CHLORIDES (mg/l) | 29000 | 28500 | 5" HWDPS | 102.7 | STAB - 2 | 40.8 | JET VELOCITY (M/SEC) |  |  | 62.01 | [12 empty] | DRL WASTE | 81200
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS | 102.7 | STAB - 3 |  | TFA (IN²) |  |  | 0.7455 | [12 empty] | POB
PENETREX % | 2 | 2 | 6.75" PBL SUB |  |  |  | HSI |  |  | 2.7 |  | TOTAL LENGTH (M) | [7 empty] | 227.55 |  |  | MPCL | 6
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 18.8 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 18 |  |  | MPCL SERV | 16
SOLIDS % | 37.43 | 37.55 | DAILY ON BOTTOM HRS |  | 2.89 |  | BIT NO. 19 |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 10 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 19.4 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 57
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4449 |  | 1.76 |  | 245.07 |  |  | 0.15 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 50076 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4482 |  | 1.7 |  | 253.93 |  |  | 0.28 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14938820 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4487 |  | 1.73 |  | 260.54 |  |  | 1.2 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 75.05% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4511 |  | 2.01 |  | 263.96 |  |  | 0.38 |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.80SG) | [5 empty] | MAASP (PSI) | 1291.916
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4862 | 580/560 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4862 | 630/640 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2019-11-09 | 2019-12-09 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4862 | 830/830 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-11-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-11-13 | 2019-12-12 | NEXT BOP TEST DATE |  | 2019-11-29 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43787 | 43787.5208 | 12.5 | DRL | NPT-UP | RW | CONT'D REAM DOWN FROM 4812M TO 4864M. PUMPED AND CIRCULATED OUT 25 BBL HI-VIS WHILE REAMING. INCREASED MUD SP. GR. FROM 1.78 SG TO 1.80 SG.
43787.5208 | 43787.6458 | 3 | DRL | PT-P | D | DRILLED 8-1/2" HOLE FROM 4864M TO 4865.5M.
43787.6458 | 43787.6562 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43787.6562 | 43787.7292 | 1.75 | DRL | PT-P | WT | PERFORMED WIPER TRIP FROM 4865.5M TO 4549M (9-5/8" CSG SHOE). PUMPED OUT TIGHT HOLE INTERVALS: 4865-4817M & 4675-4727M.
43787.7292 | 43787.75 | 0.5 | DRL | NPT-P | RS | SERVICED TDS.
43787.75 | 43787.7917 | 1 | DRL | PT-P | WT | RIH FROM 4549M TO 4837M. OBSERVED COMPRESSION AT 4837M.
43787.7917 | 43787.875 | 2 | DRL | PT-P | RW | REAMED/WASHED DOWN FROM 4837M TO 4865.5M. MEANWHILE SWEPT 25 BBL HI-VIS PILL.
43787.875 | 43787.8958 | 0.5 | DRL | PT-P | D | DRILLED 8-1/2" HOLE FROM 4865.5M TO 4866M.
43787.8958 | 43787.9375 | 1 | DRL | PT-P | CIR | CIRCULATED TO CLEAN HOLE.
43787.9375 | 43787.9479 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43787.9479 | 43788 | 1.25 | DRL | PT-P | POOH | POOH 8-1/2" BIT FROM 4866M TO 4627M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43788 | 43788.0208 | 0.5 | DRL | PT-P | POOH | CONT'D POOH 8-1/2" BIT FROM 4627M TO 4549M (CSG SHOE). HOLE CONDITION GOOD.
43788.0208 | 43788.0312 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43788.0312 | 43788.25 | 5.25 | DRL | PT-P | POOH | POOH 8-1/2" BIT FROM 4549M TO 2000M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | POOH IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D REAM DOWN TO BTM AT 4864M, DRILLED 8 1/2'' HOLE FROM 4864M TO 4965.5M, PERFORMED WIPER TRIP TO CSG SHOE, DRILLED AHEAD 8 1/2'' HOLE TO 4866M, FLOW CHECKED- WELL STATIC, POOH TO 4627M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH TO SURFACE, L/DOWN TC BIT, P/UP AND M/UP NEW 8 1/2'' PDC BIT. RIH WITH ROTARY + MWD BHA TO BTM AT 4866M, RESUME DRILLING.
REMARKS |  |  | WASH PIPE ROTATING HRS = 107.69 ; CIRC HRS = 149.66 @ 0:00 HRS / TOP OF PATALA FORMATION @ 4790M.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15