## DDR#201
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 201
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-10
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4874 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 200.5833
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4874 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 12
2018-07-09 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 11 |  | BHA No. |  |  | 26 | IN (M) |  | 4580 |  | OUT (M) | 4874 |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  | 4874 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1011.35
DEPTH, MD (M) | 4874 | 4874 | TVD @ 00:00HR (M) |  | 4874 |  | MANUFACTURER |  | BAKER |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.37 | 0.050674 |  | PITS (BBL) | 792
MW IN (SG) | 1.5 | 1.5 | DAILY PROGRESS (M) |  | 12 |  | TYPE |  | TD506FX |  | BIT SUB (F.V) |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 1.07 | 0.14654 |  | ACT. SYS (BBL) | 1803.35
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5280230 |  | 2 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 18.51 | 2.5351 |  | RESV. SYS (BBL) | 213
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 1.18 |  | IADC CODE |  | - |  | STRING STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.39 | 0.19037 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  | 8 |  | NOZZLES |  | 6 X OPEN |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 60 | 62 | AVG. RPM SURFACE |  | 120 |  | DEPTH IN (M) |  | 4580 |  | STRING STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.61 | 0.2205 |  | TOTAL | 2616.35
PV | 36 | 37 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH OUT (M) |  | 4874 |  | 11 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 101.85 | 13.949 |  | DIESEL (LTR)
YIELD POINT | 25 | 25 | FLOWRATE (GPM) |  | 475 |  | METERAGE (M) |  | 294 |  | DRILLING JAR |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 6.07 | 0.83133 |  | RIG TANK | 84000
GEL ST. | 6/11 | 6/12 | PRESSURE (PSI) |  | 2700-2800 |  | RPM SURF. |  | 120 |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.2682 |  | CAMP TANK | 15550
WL (ml/30 min.) | 3.2 | 3.3 | TORQ. ON-BTM (KLB-FT) |  | 6-8 |  | RPM BTM. |  | 120 |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.03 | 6.2546 |  | CONSUMED | 10650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-6 |  | WOB (TON) |  | 3-8 | [12 empty] | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 185 |  | AVG. ROP (M/HR) |  | 2.6164 | [12 empty] | TOTAL | 99550
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  | 174 |  | BIT ROT HRS. |  | 112.37 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 166 |  | K-REVS IN 24 HRS |  | 72.84 | [12 empty] | RIG STORAGE | 450000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS |  | 806.42 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 85.87 | [12 empty] | CONSUMED | 307900
KCl (mg/l) | 50908.9 | 50870.8 | JAR | 190.78 | STAB - 1 | 188.3 | JET VELOCITY (M/SEC) |  | 9.9 | [12 empty] | RECEIVED | 257900
CHLORIDES | 23000 | 23000 | 5" HWDPS | 190.78 | STAB - 2 | 188.3 | TFA (IN²) |  | 4.71 | [12 empty] | TOTAL | 490000
CALCIUM | 240 | 240 | 6 1/2" DCS | 190.78 |  |  | HSI |  | 0.1 | [12 empty] | POB
OIL % | 2 | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 7
LUBE % |  |  | BHA ROT. HRS |  | 190.78 |  | BIT No. 11 |  | 1-1-WT-A-X-I-NO-LOG |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 22
SOLIDS % | 19.32 | 19.42 | ON BOTTOM HRS |  | 171.34 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. | 8 | 8 | CIRC. HRS |  | 200.44 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 117
DAILY WELL COST (US$) |  | 39398 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 13305036 | SHAKER-3 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 73.72% | MUD CLEANER | 2 x 140 + 1 x 120 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4862 |  | 500/650 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4862 |  | 500/650 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-06-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 10 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-15 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43290 | 43290.4375 | 10.5 | DRL | PT-P | D | CONT'D DRILLING 8 1/2'' HOLE FROM 4870M TO 4874M. REAMED DRILLED SECTION PRIOR CONNECTION.
43290.4375 | 43290.4896 | 1.25 | EVAL | PT-P | CIR | CIRCULATED TO BOTTOMS UP.
43290.4896 | 43290.5 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43290.5 | 43290.6042 | 2.5 | EVAL | PT-P | WT | PERFORMED WIPER TRIP TO 9 5/8" CASING SHOE PRIOR TO VSP JOB. OBSERVED HOLE CONDITION GOOD.
43290.6042 | 43290.6667 | 1.5 | EVAL | PT-P | CIR | CIRCULATED TO BOTTOMS UP.
43290.6667 | 43290.6875 | 0.5 | EVAL | PT-P | S | PREPARED AND DROPPED TOTCO BARREL. WAITED FOR TOTCO BARREL TO SEAT ON BAFFLE PLATE WITH SLOW CIRCULATION.
43290.6875 | 43290.7188 | 0.75 | EVAL | PT-P | POOH | POOH FROM BTM AT 4874M TO 4529M (INSIDE 9 5/8'' CSG).
43290.7188 | 43290.7292 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43290.7292 | 43291 | 6.5 | EVAL | PT-P | POOH | CONT'D POOH FROM 4529M TO 1351M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43291 | 43291.0938 | 2.25 | EVAL | PT-P | POOH | CONT'D POOH FROM 1351M TO TOP OF BHA AT 233M.
43291.0938 | 43291.1042 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43291.1042 | 43291.2083 | 2.5 | EVAL | PT-P | BHA | POOH FROM 233M TO SURFACE. MEANWHILE L/DOWN BHA COMPONENTS + BIT. RETRIEVED TOTCO, FOUND INCL = 1.75° AT 4871M.
43291.2083 | 43291.25 | 1 | EVAL | PT-P | RU | HELD PJSM. R/UP SHOOTING NIPPLE + W/LINE BOP IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | R/UP SHOOTING NIPPLE + W/LINE BOP IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2'' HOLE FROM 4862M TO 4874M, CIRCULATION, PERFORMED WIPER TRIP TO 9 5/8'' CSG SHOE, CIRCULATION, DROPPED TOTCO AND POOH FROM 4874M TO 1351M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH FROM 1351M TO SURFACE, L/DOWN BHA COMPONENTS + BIT, R/UP SLB W/LINE, VSP JOB
REMARKS |  |  | SLB CREW + W/LINE UNIT ARRIVED AT LOCATION ON 09-07-18.
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21