## DDR#202
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 202
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-11
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4874 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 201.5833
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4874 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-07-10 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 11RR1 |  | BHA No. |  |  | 27 | IN (M) |  | 4874 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1130.94
DEPTH, MD (M) |  | 4874 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.37 | 0.05 |  | PITS (BBL) | 649
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TD506FX |  | BIT SUB (F.V) |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 1.07 | 0.15 |  | ACT. SYS (BBL) | 1779.94
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5280230 |  | 1 X 6 1/2'' NMDC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.34 | 1.25 |  | RESV. SYS (BBL) | 249
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | 1 X 6 1/2'' DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.25 | 1.25 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6 X OPEN |  | ST. STAB |  |  | 8.25 | 3 |  | 4 1/2 IF |  | 1.25 | 0.22 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 64 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4874 |  | 1 X 6 1/2'' DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 | 1.27 |  | TOTAL | 2628.94
PV |  | 37 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | ST. STAB |  |  | 8.25 | 3 |  | 4 1/2 IF |  | 1.22 | 0.22 |  | DIESEL (LTR)
YIELD POINT |  | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 6 X 6 1/2'' DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 57 | 7.8 |  | RIG TANK | 105000
GEL ST. |  | 6/13 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 14900
WL (ml/30 min.) |  | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 25000
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 119900
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT IN HOLE BHA |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 215510
KCl (mg/l) |  | 50908.9 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 165510
CHLORIDES |  | 23000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 260 | 6 1/2" DCS |  |  |  | HSI | [14 empty] | POB
OIL % |  | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 6
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT No. 11RR1 |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 23
SOLIDS % |  | 19.42 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 8 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 48
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 14
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 120
DAILY WELL COST (US$) |  | 28619 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 13333655 | SHAKER-3 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 73.87% | MUD CLEANER | 2 x 140 + 1 x 120 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4862 |  | 500/650 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4862 |  | 500/650 |  | KAMLIAL | 1255
PIT DRILL | 2018-04-25 | 2018-05-25 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43291 | 43291.0938 | 2.25 | EVAL | PT-P | POOH | CONT'D POOH FROM 1351M TO TOP OF BHA AT 233M.
43291.0938 | 43291.1042 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43291.1042 | 43291.2083 | 2.5 | EVAL | PT-P | BHA | POOH FROM 233M TO SURFACE. MEANWHILE L/DOWN BHA COMPONENTS + BIT. RETRIEVED TOTCO, FOUND INCL = 1.75° AT 4871M.
43291.2083 | 43291.3125 | 2.5 | EVAL | PT-P | RU | HELD PJSM. R/UP SHOOTING NIPPLE + W/LINE BOP. PRESSURE TESTED SAME AT 350 PSI, OK. R/UP W/LINE GEARS AND TOOLS.
43291.3125 | 43291.9167 | 14.5 | EVAL | PT-P | W/L | PERFORMED SLB W/LINE LOG (RUN #1 : VSP) AS PER PROGRAM.
43291.9167 | 43292 | 2 | EVAL | PT-P | RD | R/DOWN SLB W/LINE TOOLS AND GEARS. R/DOWN SHOOTING NIPPLE + W/LINE BOP.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43292 | 43292.1875 | 4.5 | EVAL | PT-P | BOPT | HELD PJSM. RETRIEVED WEAR BUSHING. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), TDS IBOP, FOSV, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE & LOWER PIPE RAM BOP (5" RAMS) @ 300/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG, SET WEAR BUSHING INSIDE THS, FUNCTION TESTED BLIND RAM & L/DOWN TEST PLUG ASSY.
43292.1875 | 43292.25 | 1.5 | EVAL | PT-P | BHA | P/UP & M/UP RE-RUN PDC BIT + BIT SUB + NMDC (INSTALLED EMS TOOL). RIH AS PER BHA TO 90M. MEANWHILE P/UP INSPECTED BHA COMPONENTS SINGLE BY SINGLE FROM CATWALK.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH BHA IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH FROM 1351M TO SURFACE. MEANWHILE L/DOWN ALL BHA COMPONENTS + BIT, R/UP W/LINE LOGGING GEARS + TOOLS, PERFORMED W/LINE LOG (VSP) AS PER PROGRAM, R/DOWN SLB W/LINE TOOLS & GEARS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | BOP TEST, EMS TRIP
REMARKS |  |  | PBL SUB ON LOCATION, EMS ENGR. + TOOLS ON LOCATION
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14