## DDR#204
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 204
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-11-24
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / TALHA SHAKIL |  |  | MD/TVD @ 00:00HRS: |  | 5043 | 5043 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 203.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 28
2019-11-23 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  | 8.5 |  | RUN NO. |  |  | 35 |  | BHA NO. |  |  | 48 | IN (M) |  | 4866 |  | OUT (M) |  |  | STRING (BBL) | 284
CHECK TIME | 9:00 | 23:59 | MD @ 00:00HR (M) |  | 5043 |  | BIT NO. |  |  | 18-RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 760.3
DEPTH, MD (M) | 5036 | 5043 | TVD @ 00:00HR (M) |  | 5043 |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.29 | 0.073 |  | PITS (BBL) | 619
MW IN (SG) | 1.83 | 1.85 | DAILY PROGRESS (M) |  | 28 |  | MANUFACTURER |  |  | HALLIBURTON |  | BIT SUB (F.V) |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 1.07 | 0.14064 |  | ACT. SYS (BBL) | 1663.3
MW OUT (SG) | 1.83 | 1.85 | INST. ROP (M/HR) |  | 2.33 |  | TYPE |  |  | MMD65DH |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.24 | 1.2145 |  | RESV. SYS (BBL) | 398
ECD (SG) | 1.95 | 1.98 | AVG. ROP (M/HR) |  | 3.18 |  | SERIAL NO. |  |  | 13223626 |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.89 | 0.24843 |  | KILL MUD (BBL) | 800
FL TEMP. °F | 160 | 160 | AVG. WOB (TON) |  | 6 |  | IADC CODE |  |  | M424 |  | LOWER SAVER SUB |  |  | 6.8125 | 2.75 |  | 4 1/2 IF |  | 0.5 | 0.065721 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 56 | 61 | AVG. RPM SURFACE |  | 120 |  | NOZZLES (1/32") |  |  | 6 x 13/32 |  | SPSA (MWD) |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 9.33 | 1.2264 |  | TOTAL
PV | 46 | 48 | AVG. RPM DOWNHOLE |  | 120 |  | DEPTH IN (M) |  |  | 4866 |  | ST. STAB |  |  | 8.375 | 3.125 |  | 4 1/2 IF |  | 1.41 | 0.18533 |  | DIESEL (LTR)
YIELD POINT | 30 | 32 | FLOWRATE (GPM) |  | 470 |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 8.35 | 1.0975 |  | RIG TANK | 86390
GEL ST. | 11/15 | 13/16 | PRESSURE (PSI) |  | 3980 |  | METERAGE (M) |  |  | 177 |  | 10 X DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 92.04 | 12.098 |  | CAMP TANK | 22407
WL (ml/30 min) | 3.2 | 3.5 | TORQ. ON-BTM (KLB-FT) |  | 6.5 |  | RPM SURF. |  |  | 100-125 |  | D. JAR |  |  | 6.6875 | 2.75 |  | 4 1/2 IF |  | 9.73 | 1.2789 |  | CONSUMED | 8188
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 4.0 |  | RPM BTM. |  |  | 100-125 |  | 3 X DC's |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 27.31 | 3.5848 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 173 |  | WOB (TON) |  |  | 5-7 |  | 12 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.41 | 8.2476 |  | TOTAL | 108797
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  | 179 |  | AVG. ROP (M/HR) |  |  | 3.5499 | [12 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 170 |  | BIT ROT HRS. |  |  | 49.86 | [12 empty] | RIG STORAGE | 607677
MAX SHIELD % | 2 | 2 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS |  |  | 62.96 | [12 empty] | CAMP STORAGE | 60000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS |  |  | 343.9 | [12 empty] | CONSUMED | 139418
KCl (mg/l) | 57201 | 57201 | JAR | 78.38 | STAB - 1 | 72.38 | ANN. VEL. (M/MIN) |  |  | 80.5 | [12 empty] | RECEIVED | 134100
CHLORIDES (mg/l) | 30000 | 32000 | 5" HWDPS | 72.38 | STAB - 2 | 72.38 | JET VELOCITY (M/SEC) |  |  | 58.99 | [12 empty] | DRL WASTE
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 72.38 | STAB - 3 |  | TFA (IN²) |  |  | 0.7777 | [12 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  | 2.46 |  | TOTAL LENGTH (M) | [7 empty] | 273.57 |  |  | MPCL | 4
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 20.38 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 17
SOLIDS % | 38.92 | 40.38 | DAILY ON BOTTOM HRS |  | 8.8 |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 21.7 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 107
DAILY WELL COST (US$) |  | 68866.9375 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15188047.5699 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 76.3% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.80SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4927 | 600/600/600 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4927 | 720/700/700 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2019-11-09 | 2019-12-09 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4927 | 900/900/900 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-11-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-11-13 | 2019-12-12 | NEXT BOP TEST DATE |  | 2019-11-29 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43792 | 43792.0312 | 0.75 | DRL | NPT-UP | P/T | P/TESTED MANUAL IBOP AT 8000 PSI, OK.
43792.0312 | 43792.1458 | 2.75 | DRL | NPT-UP | RIH | RIH FROM 4529M TO 5015M. WHILE RIH, OBSERVED COMPRESSION AT 4931M. HARD REAMED FROM 4931M TO 4941M.
43792.1458 | 43792.4062 | 6.25 | DRL | PT-P | D | RESUMED DRILLNG. DRILLED 8-1/2" HOLE FROM 5015M TO 5036M. OBSERVED TDS STALLED & STRING PARTIALLY PACKED OFF.
43792.4062 | 43792.4792 | 1.75 | DRL | PT-UP | STK | REDUCED PUMP DISCHARGE TO 215 GPM. WORKED ON STRING. BACK REAMED & PULLED BACK TO 5018M. OBSERVED FREQUENT STALLING & PACK OFF.
43792.4792 | 43792.5833 | 2.5 | DRL | PT-UP | CIR | AT 5018M, CIRCULATED TO INCREASE & HOMOGENIZE MUD WT TO 1.85 SG.
43792.5833 | 43792.625 | 1 | DRL | PT-UP | RW | ATTEMPTS TO REAM DOWN TO BOTTOM FAILED DUE TO FREQUENT PACK OFFS & TDS STALLING. PULLED BACK TO 5018M.
43792.625 | 43792.7292 | 2.5 | DRL | PT-UP | CIR | CIRCULATED AT 5018M & TREATED MUD WITH LC LUBE (5PPB) & MAXSHIELD (3PPB).
43792.7292 | 43792.8438 | 2.75 | DRL | PT-UP | RW | REAMED DOWN TO 5036M. HARD REAMING. OBSERVED FREQUENT PARTIAL PACK OFFS & TDS STALLING.
43792.8438 | 43793 | 3.75 | DRL | PT-P | D | RESUMED DRILLING 8-1/2" HOLE FROM 5018M TO 5043M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43793 | 43793.0625 | 1.5 | DRL | PT-P | D | CONTINUED DRILLING 8-1/2" HOLE FROM 5043M TO 5045M (STAND DOWN). WHILE BACK REAMING AT 5041M, OBSERVED SUDDEN INCREASE IN SPP (5000 PSI) & HI-TORQUE, TDS STALLED & POP OFF OPERATED. ATTEMPTED TO RECIPROCATE STRING & RESUME CIRCULATION, FOUND STRING STUCK (STRING PACKED OFF).
43793.0625 | 43793.25 | 4.5 | DRL | NPT-UP | STK | WORKED ON STUCK STRING BY COMBINATION OF COMPRESSION & TORQUE AND BY JARRING, NO SUCCESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | WORK ON STUCK STRING.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | P/TESTED MANUAL IBOP. RIH TO BOTTOM. REAMED FROM 4931M TO 4941M. DRILLED 8-1/2" HOLE FROM 5015M TO 5036M. OBSERVED PARTIAL PACK-OFF. WORKED ON STRING & PULLED BACK TO 5018M. INCREASED MUD WT TO 1.85SG & TREATED MUD. HARD REAMED DOWN TO 5036M & DRILLED DOWN TO 5043M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WORK ON STUCK STRING.
REMARKS |  |  | WASH PIPE ROTATING HRS = 72 HRS ; CIRC HRS = 79 HRS @ 0:00 HRS.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15