## DDR#206
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 206
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-15
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | SAIFULLAH TURK/ SAYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4874 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 205.5833
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4874 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-07-14 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 11RR2 |  | BHA No. |  |  | 28 | IN (M) |  | 4874 |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1125
DEPTH, MD (M) |  | 4874 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.37 |  |  | PITS (BBL) | 620
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TD506FX |  | BIT SUB (F.V) |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 1.07 |  |  | ACT. SYS (BBL) | 1745
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5280230 |  | 2 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 18.52 |  |  | RESV. SYS (BBL) | 255
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | - |  | STRING STAB |  |  | 8.375 | 3 |  | 4 1/2 IF |  | 1.88 |  |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6 X OPEN |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.24 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 63 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4874 |  | STRING STAB |  |  | 8.375 | 2.75 |  | 4 1/2 IF |  | 1.68 |  |  | TOTAL | 2600
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 11 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 101.82 |  |  | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | DRILLING JAR |  |  | 6.5 | 2.875 |  | 4 1/2 IF |  | 5.97 |  |  | RIG TANK | 91000
GEL ST. |  | 6/12 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 1 X 6 1/2" DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.26 |  |  | CAMP TANK | 12300
WL (ml/30 min.) |  | 3.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 9 X 5" HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.02 |  |  | CONSUMED | 3650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 103300
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 350000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 25000
KCl (mg/l) |  | 50908.9 | JAR | 2.6 | STAB - 1 | 2.6 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 25000
CHLORIDES |  | 23000 | 5" HWDPS | 2.6 | STAB - 2 | 2.6 | TFA (IN²) | [14 empty] | TOTAL | 390000
CALCIUM |  | 220 | 6 1/2" DCS | 2.6 |  |  | HSI | [14 empty] | POB
OIL % |  | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 233.83 |  |  | MPCL | 5
LUBE % |  |  | BHA ROT. HRS |  | 2.6 |  | BIT No. 11RR2 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 21
SOLIDS % |  | 19.47 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY | 4
M.B.T. |  | 8 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 113
DAILY WELL COST (US$) |  | 29850 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 13541810 | SHAKER-3 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 75.03% | MUD CLEANER | 2 x 140 + 1 x 120 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4862 |  | 500/650 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4862 |  | 500/650 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-14
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43295 | 43295.375 | 9 | EVAL | NPT-UP | WOE | WAITED ON VSP EQUIPMENT. CIRCULATED INTERMITTENTLY@ 1000 M.
43295.375 | 43295.4688 | 2.25 | EVAL | NPT-UP | POOH | POOH TO SURFACE.
43295.4688 | 43295.5208 | 1.25 | EVAL | PT-P | RU | PJSM. R/UP SHOOTING NIPPLE+W.L BOP. PRESSURE TESTED @ 400 PSI. R/UP W/LINE TOOLS.
43295.5208 | 43295.9062 | 9.25 | EVAL | PT-P | W/L | PERFORMED W.L LOG (OFFSET VSP). WHILE RIH OBSERVED COMPRESSION AT 4747M. ATTEMPTED TO GO DOWN, NO SUCCESS. DECIDED TO ACQUIRE DATA FROM 4747M. AS PER SCHL W.L ENGR. POOR DATA QUALITY WAS OBSERVED DUE TO HIGH BOTTOM HOLE STATIC TEMPERATURE. SUSPENDED LOG & POOH W.LINE TO SURFACE.
43295.9062 | 43295.9688 | 1.5 | EVAL | PT-P | RD | R/DOWN SCHL. W.LINE TOOLS + GEARS. R/DOWN SHOOTING NIPPLE + W.L BOP.
43295.9688 | 43296 | 0.75 | EVAL | PT-P | BHA | P/UP AND M/UP RR PDC BIT + BIT SUB (F.V). RIH AS PER BHA DOWN TO 60M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-15
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43296 | 43296.0312 | 0.75 | EVAL | PT-P | BHA | CONT'D RIH BHA FROM 60M TO 233M.
43296.0312 | 43296.25 | 5.25 | EVAL | PT-P | RIH | RIH FROM 233M TO 2648M. FILLED UP STRING AFTER EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | RIH IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WAITED ON VSP EQP. POOH OEDP TO SURFACE, PJSM, R/UP W/LINE GEARS, W/LINE LOG AS PER PROGRAM, R/DOWN W/LINE GEARS, P/UP RR PDC BIT + BIT SUB. RIH AS PER PREVIOUS BHA DOWN TO 60M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONDITION TRIP PRIOR TO VSP LOG.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14