## DDR#207
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 207
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-11-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 206.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-11-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 35 |  | BHA NO. |  |  | 48 | IN (M) |  | 4866 |  | OUT (M) |  |  | STRING (BBL) | 284.8
CHECK TIME | 9:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 18-RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 760.1
DEPTH, MD (M) | 5045 | 5045 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.29 | 0.073 |  | PITS (BBL) | 733
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | HALLIBURTON |  | BIT SUB (F.V) |  |  | 6.75 | 2.75 |  | 4 1/2 IF |  | 1.07 | 0.14064 |  | ACT. SYS (BBL) | 1777.9
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MMD65DH |  | 1 x DC |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 9.24 | 1.2145 |  | RESV. SYS (BBL) | 225
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 13223626 |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.89 | 0.24843 |  | KILL MUD (BBL) | 800
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | M424 |  | LOWER SAVER SUB |  |  | 6.8125 | 2.75 |  | 4 1/2 IF |  | 0.5 | 0.065721 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 60 | 63 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6 x 13/32 |  | SPSA (MWD) |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 9.33 | 1.2264 |  | TOTAL | 2002.9
PV | 46 | 48 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 4866 |  | ST. STAB |  |  | 8.375 | 3.125 |  | 4 1/2 IF |  | 1.41 | 0.18533 |  | DIESEL (LTR)
YIELD POINT | 31 | 32 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 8.35 | 1.0975 |  | RIG TANK | 94363
GEL ST. | 11/14 | 13/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | 10 X DC's |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 92.04 | 12.098 |  | CAMP TANK | 20921
WL (ml/30 min) | 3.6 | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | D. JAR |  |  | 6.6875 | 2.75 |  | 4 1/2 IF |  | 9.73 | 1.2789 |  | CONSUMED | 5929
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | 3 X DC's |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 27.31 | 3.5848 |  | RECEIVED | 24000
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) |  |  |  |  | 12 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 112.41 | 8.2476 |  | TOTAL | 115284
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 594355
MAX SHIELD % | 3 | 3 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 65000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 15199
KCl (mg/l) | 59107.7 | 59107.7 | JAR | 79.94 | STAB - 1 | 73.94 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 21000
CHLORIDES (mg/l) | 33500 | 33500 | 5" HWDPS | 73.94 | STAB - 2 | 73.94 | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 29000
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 73.94 | STAB - 3 |  | TFA (IN²) |  |  | 0.7777 | [12 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 273.57 |  |  | MPCL | 6
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 22
SOLIDS % | 40.84 | 40.84 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 11.25 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 111
DAILY WELL COST (US$) |  | 115688.8442 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15367649.6308 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 77.2% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.80SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P2/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4927 | 600/600/600 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4927 | 720/700/700 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2019-11-09 | 2019-12-09 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4927 | 900/900/900 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-11-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-11-13 | 2019-12-12 | NEXT BOP TEST DATE |  | 2019-11-29 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43795 | 43795.1875 | 4.5 | DRL | NPT-UP | W/L | CONDUCTED W/L DUMMY RUN DOWN TO 5021M PRIOR PERFORATION RUN.
43795.1875 | 43795.2917 | 2.5 | DRL | NPT-UP | W/L | HELD PJSM. PREPARED & ARMED PERF GUN.
43795.2917 | 43795.4896 | 4.75 | DRL | NPT-UP | W/L | RIH PERF GUN ON W/L DOWN TO 5018M. CORRELATED TOP STABLIZER & PERFORATED 1 FT INTERVAL (6 SPF). POOH. R/DOWN W.FORD GEARS.
43795.4896 | 43795.5312 | 1 | DRL | NPT-UP | STK | M/UP WORKING SINGLE & TDS. ATTEMPTED TO ESTABLISH CIRCULATION BY WORKING ON STUCK STRING.
43795.5312 | 43795.9479 | 10 | DRL | NPT-UP | STK | RESUMED CIRCULATION. CIRCULATED WITH 400 - 500 GPM. WORKED ON STRING BY UPWARD, DOWNWARD JARRING AND TORQUE, BUT NO SUCCESS. UPWARD : 80 - 100 TONS, DOWNWARD : 70 - 80 TONS, TORQUE : 16 - 18 KFTLBS.
43795.9479 | 43796 | 1.25 | DRL | NPT-UP | STK | PUMPED 60 BBL LUBRICANT PILL (7% TEQ-LUBE). WORKED ON STRING BY UPWARD JARRING ON SAME PARAMETERS, WHILE NOZZLING OUT LUBRICANT PILL.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43796 | 43796.0208 | 0.5 | DRL | NPT-UP | STK | CONT'D WORKING ON STRING WHILE NOZZLING OUT LUBRICANT PILL.
43796.0208 | 43796.0729 | 1.25 | DRL | NPT-UP | STK | CIRCULATED FOR BOTTOMS UP. MEANWHILE PREPARATIONS FOR FPIT RUN.
43796.0729 | 43796.125 | 1.25 | DRL | NPT-UP | RU | HELD PJSM. R/U W.FORD W/L GEARS. F/T FPIT AND STARTED RIH.
43796.125 | 43796.2292 | 2.5 | DRL | NPT-UP | W/L | OBSERVED RESTRICTED MOVEMENT OF WIRELINE DUE TO GROOVE IN HOOK. POOH W/L TOOLS & GRINDED THE GROOVE.
43796.2292 | 43796.25 | 0.5 | DRL | NPT-UP | W/L | P/U FPIT AGAIN & FUNCTION TESTED. RIH FPIT IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | RIH FPIT IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONDUCTED W.FORD W/L DUMMY RUN PRIOR PERFORATION. PERFORATED BOTTOM OF UPPER ST. STAB. WORKED ON STRING & RESUMED CIRCULATION. CONT'D WORKING ON STRING, BUT NO SUCCESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH FPIT & ESTABLISH FREE POINT. PLAN ACCORDINGLY.
REMARKS |  |  | WASH PIPE ROTATING HRS = 72 HRS ; CIRC HRS = 90.25 HRS @ 0:00 HRS.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15