## DDR#208
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 208
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-17
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | SAIFULLAH TURK/ SAYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4874 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 207.5833
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4874 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-07-16 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1130
DEPTH, MD (M) |  | 4874 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER | [14 empty] | PITS (BBL) | 630
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE | [14 empty] | ACT. SYS (BBL) | 1760
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. | [14 empty] | RESV. SYS (BBL) | 240
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE | [14 empty] | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES | [14 empty] | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 64 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 2600
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 82000
GEL ST. |  | 6/13 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 11000
WL (ml/30 min.) |  | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 93000
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 98530
KCl (mg/l) |  | 50908.9 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 148530
CHLORIDES |  | 23000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 220 | 6 1/2" DCS |  |  |  | HSI | [14 empty] | POB
OIL % |  | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 5
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 21
SOLIDS % |  | 19.47 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 8 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 44
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 13
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 111
DAILY WELL COST (US$) |  | 31870 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 13609196 | SHAKER-3 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 75.4% | MUD CLEANER | 2 x 140 + 1 x 120 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4862 |  | 500/650 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30/40 |  | 4862 |  | 500/650 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-16
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43297 | 43297.125 | 3 | EVAL | PT-P | POOH | CONT'D POOH FROM 1899M TO 233M.
43297.125 | 43297.1354 | 0.25 | EVAL | PT-P | FC | FLOW CHECKED.WELL STATIC.
43297.1354 | 43297.1771 | 1 | EVAL | PT-P | BHA | POOH BHA FROM 233M TO SURFACE. L/DOWN BIT + JAR.
43297.1771 | 43297.2708 | 2.25 | EVAL | PT-P | RU | PJSM- R/UP SHOOTING NIPPLE+WL BOP. R/UP WL GEARS +TOOLS.
43297.2708 | 43298 | 17.5 | EVAL | PT-P | W/L | CONDUCTED W.L LOG (OFFSET VSP) AS PER PROGRAM. (IN PROGRESS)
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-17
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43298 | 43298.2188 | 5.25 | EVAL | PT-P | W/L | CONT'D CONDUCTING W.L LOG (OFFSET VSP) AS PER PROGRAM.
43298.2188 | 43298.25 | 0.75 | EVAL | PT-P | RD | R/DOWN SCHL W.L TOOLS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | R/DOWN SCHL W.L.L TOOLS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH FROM 1899M TO 233M, FLOW CHECKED - WELL STATIC. POOH TO SURFACE, L/DOWN BIT + JAR. R/UP W.L AND CONDUCTED VSP LOG AS PER PROGRAM.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE CONDUCTING VSP LOG, R/DOWN W.L, RIH WITH MULE SHOE + DP'S TO 1500 M AS KILL STRING, WAIT ON FURTHER PLAN.
REMARKS |  |  | 9 5/8'' FLOAT EQPS. DISPATCHED TO W.FORD YARD.
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14