## DDR#21
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 21
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 2085 / 2085 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 20.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 2085 / 2085 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 67
2019-05-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MOD. LIGNO |  | HOLE SIZE (IN) |  | 17 1/2'' |  | BIT No. |  | 4 |  | BHA No. |  |  | 5 | IN (M) |  | 590 |  | OUT (M) |  |  | STRING (BBL) | 136
CHECK TIME | 15:30 | 23:45 | MD @ 00:00HR (M) |  | 2085 |  | SIZE (IN) |  | 17 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1905.96
DEPTH, MD (M) | 2075 | 2085 | TVD @ 00:00HR (M) |  | 2085 |  | MANUFACTURER |  | NOV |  | 17 1/2'' PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 951
MW IN (SG) | 1.45 | 1.47 | DAILY PROGRESS (M) |  | 67 |  | TYPE |  | TFH519S |  | PD |  |  | 9 | 5.125 |  | 7 5/8 REG |  | 4.29 | 1.3667 |  | ACT. SYS (BBL) | 2992.96
MW OUT (SG) | 1.45 | 1.45 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E260745 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.76 | 0.24212 |  | RESV. SYS (BBL) | 857
ECD (SG) |  |  | AVG. ROP (M/HR) |  | 5.93 |  | IADC CODE |  | S422 |  | MUD MOTOR (SLEEVE STAB) |  |  | 9.625 | 7 |  | 6 5/8 REG |  | 10.53 | 3.3546 |  | KILL MUD (BBL) | 550
FL TEMP. °F | 140 | 149 | AVG. WOB (TON) |  | 11 |  | NOZZLES |  | 3X 18, 2 X 16 |  | X/O |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.1 | 0.35043 |  | KILL MW (SG) | 1.97
µ FUNNEL (SEC) | 47 | 50 | AVG. RPM SURFACE |  | 68 |  | DEPTH IN (M) |  | 590 |  | FLOAT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | TOTAL | 3849.96
PV | 26 | 25 | AVG. RPM DOWNHOLE |  | 168 |  | DEPTH OUT (M) |  |  |  | ST. STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.44 | 0.77732 |  | DIESEL (LTR)
YIELD POINT | 32 | 30 | FLOWRATE (GPM) |  | 910 |  | METERAGE (M) |  | 1495 |  | LOWER S. SUB |  |  | 9.625 | 3.5 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | RIG TANK | 102913
GEL ST. | 8/10 | 9/11 | PRESSURE (PSI) |  | 3032 |  | RPM SURF. |  | 40-90 |  | SLIM PULSE |  |  | 9.5625 | 5 |  | 7 5/8 REG |  | 9.27 | 2.9532 |  | CAMP TANK | 17831
WL (ml/30 min.) | 4.6 | 4.5 | TORQ. ON-BTM (KLB-FT) |  | 6-12 |  | RPM BTM. |  | 140-190 |  | UPPER S. SUB |  |  | 9.5625 | 3 |  | 7 5/8 REG |  | 0.67 | 0.21344 |  | CONSUMED | 12987
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | WOB (TON) |  | 5-16 |  | ST. STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.37 | 0.75502 |  | RECEIVED | 24000
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 132 |  | AVG. ROP (M/HR) |  | 13.0136 |  | NMDC |  |  | 9 | 3.5 |  | 7 5/8 REG |  | 9.36 | 2.9818 |  | TOTAL | 120744
ALK (FILT.) | 0.3 | 0.4 | PICK-UP WT. (TON) |  | 133 |  | BIT ROT HRS. |  | 114.88 |  | 3 X 9 1/2'' DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.53 | 8.7703 |  | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 130 |  | K-REVS IN 24 HRS |  | 113.63 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29627 |  | RIG STORAGE | 430000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1133.69 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CAMP STORAGE | 85000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 25.3 |  | D. JAR |  |  | 7.9375 | 3.0625 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | CONSUMED | 196100
KCl (mg/l) | 57201 | 60061 | JAR | 158.7 | NMDC | 148.69 | JET VELOCITY (M/SEC) |  | 77.19 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | RECEIVED | 206100
CHLORIDES (mg/l) | 29000 | 28000 | MOTOR | 148.69 | STAB - 1 | 148.69 | TFA (IN²) |  | 1.138 |  | X/O |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | TOTAL
HARDNESS (mg/l) | 440 | 440 | 9 1/2" DCS | 158.7 | STAB - 2 | 148.69 | HSI |  | 1.403 |  | 10 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 3.4703 |  | POB
SAND % | 0.25 | 0.4 | 8" DCS | 158.7 | SPSA | 148.69 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 212.69 |  |  | MPCL | 5
LUBRICANT % | 0.5 | 0.5 | BHA ROT. HRS |  | 148.69 |  | BIT No. 4 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 29
SOLIDS % | 16.05 | 16.11 | ON BOTTOM HRS |  | 11.29 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 23 |  |  | SECURITY | 2
M.B.T. (lb/bbl) | 10 | 10 | CIRC. HRS |  | 19.2 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 27
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 1953/1953 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 121
DAILY WELL COST (US$) |  | 86240 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | 1981/1981 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2535730 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | LAST CSG SIZE | 20''
% OF AFE SPENT |  | 12.74% | MUD CLEANER | 3 x 120 | [6 empty] | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | LOT (EMW) | 1.95
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 411
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS.PSI |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 2007 | 260 / 260 / 260 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 2007 | 350 / 350 / 350 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 2007 | 400 / 400 / 400 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  | 16 | BRINE LOSSES IN 24 HRS |  |  |  |  | BRINE LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-05-28 |  | OPR. HRS OF CENTRIFUGE-2 |  |  | 16 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43609 | 43609.4167 | 10 | DRL | PT-P | DM | CONT'D DRILLING 17.5'' HOLE FROM 2018M TO 2073M. REAMED / WASHED DRILLED INTERVAL & RECORDED MWD SURVEY PRIOR TO CONNECTION. MEANWHILE INCREASED MUD WT. FROM 1.40SG TO 1.45SG.
43609.4167 | 43609.5 | 2 | DRL | PT-P | CIR | SWEPT OUT 20 BBL HI-VIS PILL AND CIRCULATED TILL SHAKERS CLEAN.
43609.5 | 43609.5104 | 0.25 | DRL | PT-P | FC | FLOW CHECKED, WELL STATIC.
43609.5104 | 43609.6354 | 3 | DRL | PT-P | WT | PERFORMED WIPER TRIP FROM 2073M TO 1760M. WHILE POOH, OBSERVED TIGHT SPOTS AT 1998M-1996M, 1953M & AT 1923M. CLEARED THE SAME WITH RECIPROCATION. RIH TO BOTTOM (WASHED DOWN LAST STAND).
43609.6354 | 43609.7083 | 1.75 | DRL | PT-P | DM | RESUMED DRILLING. DRILLED 17.5'' HOLE FROM 2073M TO 2080M. OBSERVED LEAKAGE FROM WASHPIPE.
43609.7083 | 43609.7812 | 1.75 | DRL | NPT-UP | POOH / RR | POOH TO 2045M. REPLACED & P/TESTED WASHPIPE. MEANWHILE CIRCULATED THROUGH CIRCULATING HEAD & KEPT STRING IN ROTATION. RIH DOWN TO BOTTOM.
43609.7812 | 43609.8229 | 1 | DRL | PT-P | DM | RESUMED DRILLING. DRILLED 17.5'' HOLE FROM 2080M TO 2085M. WHILE DRILLING, OBSERVED MOTOR STALLING FOLLOWED BY SPP SHOT. ROTARY STALLED, STRING STUCK.
43609.8229 | 43609.8542 | 0.75 | DRL | NPT-UP | STK | WORKED ON STUCK STRING SEVERAL TIMES BY JARRING UPWARD, STRING GOT RELEASED.
43609.8542 | 43609.9375 | 2 | DRL | NPT-UP | CIR | P/BACK FROM 2085M TO 2070M. SWEPT OUT 30 BBL HI-VIS PILL AND CIRCULATED TILL SHAKERS CLEAN. NO GAIN OBSERVED DURING CIRCULATION.
43609.9375 | 43609.9583 | 0.5 | DRL | NPT-UP | FC | FLOW CHECKED, OBSERVED WELL FLOWING AT 8-10 BBL/ HRS.
43609.9583 | 43610 | 1 | DRL | NPT-UP | CIR | DECIDED TO INCREASE MUD WT. PRIOR POOH. CONT'D CIRCULATION MEANWHILE INCREASING MUD WT. FROM 1.45SG TO 1.50SG (IN PROGRESS).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43610 | 43610.2292 | 5.5 | DRL | NPT-UP | CIR | CONT'D CIRCULATION MEANWHILE INCREASED MUD WT FROM 1.45 SG TO 1.51 SG IN / 1.48 SG OUT. (OBSERVED CUT MUD WT = 1.40SG AT BTMS UP). STILL INFLUX ENCOUNTERING.
43610.2292 | 43610.25 | 0.5 | DRL | NPT-UP | SHUT | STOPPED CIRCULATION, P/BACK TO 2064M. CLOSED ANNULAR BOP FOR WELL SHUT-IN.(PRESSURE STABILIZATION/MONITORING IN PROGRESS).
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE.
OPERATIONS AT 06:00 HRS |  |  | WELL SHUT-IN IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 17.5'' HOLE DOWN TO 2073M, PERFORMED WIPER TRIP TO 1760M, OBSVD FEW TIGHT SPOTS, CLEARED SAME BY RECIPROCATION, RIH TO BTM AT 2073M, RESUMED DRILLING, DRILLED 17.5'' HOLE FROM 2073M TO 2080M, OBSERVED LEAKAGE IN WASHPIPE, P/BACK TO 2045M, REPLACED & TESTED WASHPIPE, REAMED DOWN TO BTM AT 2080M, DRILLED 17.5'' HOLE FROM 2080M TO 2085M, OBSVD MOTOR STALLING FOLLOWED BY STRING STUCK, RELEASED SAME BY UPWARD JARRING, SWEPT OUT 30 HI-VIS PILL & CIRCULATED TO CLEAN HOLE, FLOW CHECKED, OBSVD WELL TRICKLING, DECIDED TO CIRCULATE MEANWHILE INCREASE MUD WT FROM 1.45SG TO 1.50SG (IN PROGRESS).
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CIRCULATE AND INCREASE MUD WT TO 1.50SG IN/OUT, ATTEMPT TO BALANCE THE WELL, IF NOT , SHUT-IN WELL, KILL WELL, OBSERVE WELL, POOH TO SURFACE
REMARKS |  |  | PUMPED 20 BBL HI-VIS BRIDGE PILL AT EVERY STAND.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14