## DDR#210
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 210
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-19
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | SAIFULLAH TURK/ SAYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4874 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 209.5833
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4874 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-07-18 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 11RR3 |  | BHA No. |  |  | 28 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1102.83
DEPTH, MD (M) |  | 4874 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | BAKER |  | 8 1/2" PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.37 |  |  | PITS (BBL) | 695
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TD506FX |  | BIT SUB (WITH F.V) |  |  | 6.5 | 2 3/4 |  | 4 1/2 IF |  | 1.07 |  |  | ACT. SYS (BBL) | 1797.83
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 5280230 |  | 6 X 6 1/2" DC |  |  | 6.5 | 2 13/16 |  | 4 1/2 IF |  | 55.53 |  |  | RESV. SYS (BBL) | 193
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | D. JAR |  |  | 6.375 | 3 |  | 4 1/2 IF |  | 5.97 |  |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6 X OPEN |  | 9 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.02 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 64 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) | [14 empty] | TOTAL | 2590.83
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 23 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 74400
GEL ST. |  | 6/11 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 9700
WL (ml/30 min.) |  | 3.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4250
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 84100
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 202320
KCl (mg/l) |  | 50718.2 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 202320
CHLORIDES |  | 23000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 220 | 6 1/2" DCS |  |  |  | HSI | [14 empty] | POB
OIL % |  | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 146.96 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT No. 11RR3 |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 14
SOLIDS % |  | 19.22 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 8 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 44
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 101
DAILY WELL COST (US$) |  | 32545 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 13677816 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 75.78% | MUD CLEANER | 2 x 170 + 1 x 170 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-18
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43299 | 43299.0208 | 0.5 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD.
43299.0208 | 43299.0417 | 0.5 | DRL | PT-P | SP | SPOTTED 25 BBL HI-VIS PILL AT 4700M.
43299.0417 | 43299.0521 | 0.25 | DRL | PT-P | POOH | POOH FROM 4700M TO 4600M
43299.0521 | 43299.0625 | 0.25 | DRL | PT-P | RU | R/UP SCHL. CMT EQP. CONNECTED CIRCULATING SWAGE WITH RIG LINE AND CMT UNIT.
43299.0625 | 43299.0833 | 0.5 | DRL | PT-P | P/T | FLUSHED CMT LINES WITH FRESH WATER. CLOSED VALVE AND PRESSURE TESTED SAME AT 3000 PSI, OK.
43299.0833 | 43299.25 | 4 | DRL | PT-P | CIR | RESUMED CIRCULATION, CIRCULATED TO CONDITION MUD. MEANWHILE PREPARED MIXED FLUID & CMT SLURRY.(ADDING CMT STARTED @ 0530)
43299.25 | 43299.3021 | 1.25 | DRL | PT-P | CMT | PUMPED 35 BBL SPACER OF 14.5 PPG WITH RIG PUMP. SWITCHED OVER TO DWS. PUMPED 50 BBLS OF BATCH MIXED CMT SLURRY OF 16.20 PPG FOLLOWED BY 15 BBLS OF SPACER OF 14.5 PPG WITH DWS PUMPING UNIT. SWITCHED TO RIG PUMPS. DISPLACED CMT WITH 221 BBLS OF MUD @ 6.5 BBL/MIN
43299.3021 | 43299.3542 | 1.25 | DRL | PT-P | POOH | R/DOWN CIR HEAD & POOH UP TO 4182M.
43299.3542 | 43299.4271 | 1.75 | DRL | PT-P | CIR | R/UP CIR HEAD. CLOSED PIPE RAM BOP. REVERSED OUT TWICE STRING CAPACITY. DUMPED 30 BBLS OF SPACER CONTAMINATED MUD( MAX SP.GR 1.54)
43299.4271 | 43299.4896 | 1.5 | DRL | PT-P | CIR | OPENED BOP. DIRECT CIRCULATED FOR 1.5 TIMES BOTTOMS UP VOLUME. NO SPACER CONTAMINATION OBSERVED.
43299.4896 | 43299.9167 | 10.25 | DRL | PT-P | POOH | POOH TO SURFACE. R/BACK 3 1/2'' DPS. L/DOWN MULE SHOE.
43299.9167 | 43300 | 2 | DRL | PT-P | RIH | M/UP 8.5" RR PDC BIT AS PER BHA & RIH DOWN TO 690M. FILLED UP STRING AFTER 15 STANDS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43300 | 43300.25 | 6 | DRL | PT-P | RIH | CONT'D RIH FROM 690M TO 3500M. FILLED UP STRING AFTER EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | WOC IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATION, SPOTTED 25 BBL HI-VIS AT 4700M , POOH TO 4600M, CONDITIONED MUD, PERFORMED CMT PLUG JOB AS PER PROGRAM, POOH TO 4182M, REVERSED OUT 2 STRING CAPACITY, DIRECT CIRCULATION FOR 1.5 TIMES BTMS UP VOL, POOH TO SURFACE, M/UP 8 1/2'' RR PDC BIT AS PER BHA, RIH DOWN TO 690M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH TO 3500 M, WOC, RIH TO TAG CMT, WAIT ON FURTHER PLAN.
REMARKS |  |  | BACKLOADED CORING EQP, BACKLOADED SCHL. UBHO.
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14