## DDR#211
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 211
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN - 1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-20
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 4900 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215
MPCL REP. (DSV): |  | SAIFULLAH TURK / SAYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4874 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 210.5833
RIG REP. (TP): |  | JAVED IQBAL / FAYYAZ HUSSAIN MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4874 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-07-19 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 9RR2 |  | BHA No. |  |  | 29 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1130.94
DEPTH, MD (M) |  | 4874 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | 8 1/2'' TRI-CONE BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.25 |  |  | PITS (BBL) | 732
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SB137C |  | 9 5/8'' CSG SCRAPER |  |  | 8.5 | 2.25 |  | 4 1/2 REG |  | 1.22 |  |  | ACT. SYS (BBL) | 1862.94
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | RH3659 |  | BIT SUB (F.V) |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 1.07 |  |  | RESV. SYS (BBL) | 151
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 137 |  | 6 X 6 1/2'' DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 55.53 |  |  | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3 X OPEN |  | D.JAR |  |  | 6.375 | 3 |  | 4 1/2 IF |  | 5.97 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 64 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | 9 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.02 |  |  | TOTAL | 2613.94
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) | [14 empty] | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) | [14 empty] | RIG TANK | 69500
GEL ST. |  | 6/11 | PRESSURE (PSI) |  |  |  | RPM SURF. | [14 empty] | CAMP TANK | 34050
WL (ml/30 min.) |  | 3.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 5550
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED | 25000
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 103550
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 145840
KCl (mg/l) |  | 50908.9 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 145840
CHLORIDES |  | 23000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 440000
CALCIUM |  | 220 | 6 1/2" DCS |  |  |  | HSI | [14 empty] | POB
OIL % |  | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 148.06 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT No. 9RR2 |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 15
SOLIDS % |  | 19.22 | ON BOTTOM HRS |  |  |  | BIT NO. 11RR3 |  | 1-1-WT-A-X-I-NO-BHA |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 8 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 43
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 11
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 101
DAILY WELL COST (US$) |  | 202860 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 13880676 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 76.91% | MUD CLEANER | 2 x 170 + 1 x 170 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-05-18 | 2018-06-17 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-06-17 | 2018-07-17 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-06-15 | 2018-07-15 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-11 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-06-24 | 2018-07-24 | NEXT BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-19
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43300 | 43300.25 | 6 | DRL | PT-P | RIH | RIH FROM 690M TO 3500M. FILLED UP STRING AFTER EVERY 15 STANDS.
43300.25 | 43300.3333 | 2 | DRL | PT-P | WOC | WOC.
43300.3333 | 43300.4062 | 1.75 | DRL | PT-P | RIH | RIH ON ELEVATOR DOWN TO 4200 M.
43300.4062 | 43300.4479 | 1 | DRL | PT-P | RIH | M/UP TDS. RIH PRECAUTIONARY WITH CIRCULATION & TAGGED CMT TOP @ 4396.5M.
43300.4479 | 43300.4896 | 1 | DRL | PT-P | DC | DRESSED CMT PLUG DOWN TO 4397M. CONFIRMED WITH 10 TONS WEIGHT. CLOSED PIPE RAM BOP & PRESSURE TESTED CMT PLUG @ 500 PSI. TEST OK
43300.4896 | 43300.5521 | 1.5 | DRL | PT-P | CIR | CIRCULATED TO HOMOGENIZE / CONDITION MUD.
43300.5521 | 43300.5625 | 0.25 | DRL | PT-P | FC | FLOW CHECKED.WELL STATIC.
43300.5625 | 43300.9375 | 9 | DRL | PT-P | RIH | PUMPED SLUG, POOH TO SURFACE. R/BACK BHA. L/DOWN JAR + BIT.
43300.9375 | 43301 | 1.5 | DRL | PT-P | DP | RIH 9 STANDS OF 3 1/2'' DP, POOH & L/DOWN 15 X 3 1/2'' DP'S SINGLE BY SINGLE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43301 | 43301.0521 | 1.25 | DRL | PT-P | DP | CONT'D L/DOWN 12 X 3 1/2'' DP'S SINGLE BY SINGLE.
43301.0521 | 43301.25 | 4.75 | DRL | PT-P | RIH | P/UP & M/UP 8.5'' RR TRI-CONE BIT + 9 5/8'' CSG SCRAPER. RIH AS PER BHA DOWN TO 2015M. FILLED UP STRING EVERY 15 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH WITH 9 5/8'' CSG SCRAPER IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | RIH DOWN TO 3500M, WOC, RIH TO 4200M, CONNECTED TDS & PRECUATIONARY WASHED DOWN FROM 4200M TO TAG CMT TOP @ 4396.5M, DRESSED CMT PLUG TO 4397M, CONFIRMED WITH 10 T WEIGHT, CLOSED BOP & PRESSURE TESTED CMT PLUG AT 500 PSI, OK. CIRCULATED TO CONDITION MUD. FLOW CHECKED - WELL STATIC, PUMPED SLUG AND POOH TO SURFACE. L/DOWN 3 1/2'' DP'S FROM DERRICK.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | L/DOWN 3 1/2'' DP'S FROM DERRICK, 9 5/8'' CSG SCRAPER TRIP.
REMARKS
Formulas:
DHARIAN - 1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14