## DDR#211
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 211
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-12-01
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 210.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-11-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 36 |  | BHA NO. |  |  | 49 | IN (M) |  | 5045 |  | OUT (M) |  |  | STRING (BBL) | 282.4
CHECK TIME | 11:00 | 23:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 19 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 771
DEPTH, MD (M) | 5045 | 5045 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.375 |  | MILL BIT |  |  | 8.375 |  |  | 4 1/2 REG |  | 0.7 |  |  | PITS (BBL) | 678
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | WEATHERFORD |  | BIT SUB (F.V) |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 1.06 | 0.13933 |  | ACT. SYS (BBL) | 1731.4
MW OUT (SG) |  | 1.85 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | INSERT BLADED MILL |  | ST. STAB |  |  | 8.375 | 2.875 |  | 4 1/2 IF |  | 1.55 | 0.20374 |  | RESV. SYS (BBL) | 325
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 110418 |  | 6 x DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 55.55 | 7.3016 |  | KILL MUD (BBL) | 680
FL TEMP. °F |  | 122 | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | - |  | D. JAR |  |  | 6.375 | 2.75 |  | 4 1/2 IF |  | 9.8 | 1.2881 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 70 | 66 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 4x PORTS |  | 2 x DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 18.52 | 2.4343 |  | TOTAL | 2056.4
PV | 48 | 47 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 5045 |  | 9 x HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 83.22 | 6.1059 |  | DIESEL (LTR)
YIELD POINT | 32 | 31 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 93903
GEL ST. | 11/14 | 12/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 18783
WL (ml/30 min) | 3.2 | 3.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 6171
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED | 24000
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 112686
ALK (FILT.) | 0.3/1.1 | 0.3/1.1 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 623753
MAX SHIELD % | 3 | 3 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 72000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 45508
KCl (mg/l) | 59107.7 | 58154.3 | JAR | 1.83 | STAB - 1 | 4.73 | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 64200
CHLORIDES (mg/l) | 33500 | 33000 | 5" HWDPS | 1.83 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | -
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 1.83 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 170.4 |  |  | MPCL | 5
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 1.83 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 15 |  |  | MPCL SERV | 19
SOLIDS % | 40.33 | 40.34 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 7 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 3 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 109
DAILY WELL COST (US$) |  | 98263.7316 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15585513.644 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 78.3% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4990 | 620/640 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4990 | 800/800 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2019-11-09 | 2019-12-09 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4990 | 920/940 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-11-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-11-13 | 2019-12-12 | NEXT BOP TEST DATE |  | 2019-11-29 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-11-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43799 | 43799.1562 | 3.75 | DRL | NPT-UP | POOH | CONT'D POOH FROM 1836M TO 229M (BHA TOP).
43799.1562 | 43799.1667 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED AT BHA - WELL STATIC.
43799.1667 | 43799.2917 | 3 | DRL | NPT-UP | BHA | POOH BHA TO SURFACE. L/D BHA FOR INSPECTION.
43799.2917 | 43799.4271 | 3.25 | DRL | NPT-UP | BHA | HELD PJSM. M/UP 8 3/8" FB MILL BIT & RIH AS PER BHA DOWN TO 170M. P/UP 8 x 6.5" DC + NEW D.JAR + 9 x 5" HWDPS FROM C. WALK DURING RIH.
43799.4271 | 43799.4375 | 0.25 | DRL | NPT-UP | CIR | FLUSHED BHA.
43799.4375 | 43799.8333 | 9.5 | DRL | NPT-UP | RIH | RIH FROM 170M TO 4540M. FILLED STRING AFTER EVERY 20 STANDS.
43799.8333 | 43799.8542 | 0.5 | DRL | NPT-UP | CIR | CIRCULATED STRING CAPACITY.
43799.8542 | 43800 | 3.5 | DRL | NPT-UP | RIH / RW | RESUMED RIH FROM 4540M TO 4952M. (REAMED FROM 4717M TO 4730M & WASHED DOWN TO 4744M. REAMED DOWN FROM 4905M TO 4917M & 4929M TO 4952M).
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43800 | 43800.1562 | 3.75 | DRL | NPT-UP | RW | CONT'D REAMING FROM 4952M TO 4999.12M. TAGGED & CONFIRMED TOP OF FISH AT 4999.12M.
43800.1562 | 43800.25 | 2.25 | DRL | NPT-UP | MIL | MILLED TOP OF FISH FROM 4999.12M TO 4999.27M & IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | MILLING IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH FROM 1836M TO SURFACE & L/D BHA. RIH WITH 8 3/8" FB MILL DOWN TO 4952M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | MILL TOP OF FISH & POOH TO SURFACE.
REMARKS |  |  | WASH PIPE ROTATING HRS = 73.8 HRS ; CIRC HRS = 119.15 HRS @ 0:00 HRS.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15