## DDR#214
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 214
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-12-04
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 213.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-12-03 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 37 |  | BHA NO. |  |  | 50 | IN (M) |  | 5045 |  | OUT (M) |  |  | STRING (BBL) | 0
CHECK TIME | 4:00 | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 20 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1170.3
DEPTH, MD (M) | 5045 | 5045 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 7.125 |  | SKIRTED MILL BIT |  |  | 7.125 |  |  | 4 1/2 REG |  | 1.92 |  |  | PITS (BBL) | 486
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | WEATHERFORD |  | BIT SUB (F.V) |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 1.06 | 0.13933 |  | ACT. SYS (BBL) | 1656.3
MW OUT (SG) | 1.85 |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | SKIRTED MILL |  | 9 x DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 83.32 | 10.9518 |  | RESV. SYS (BBL) | 326
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 11702883 |  | D. JAR |  |  | 6.375 | 2.75 |  | 4 1/2 IF |  | 9.8 | 1.2881 |  | KILL MUD (BBL) | 680
FL TEMP. °F | 140 |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | - |  | 3 x DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.78 | 3.6515 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 63 | 67 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6x PORTS |  | 9 x HWDP |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 83.22 | 6.1059 |  | TOTAL | 1982.3
PV | 47 | 46 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 5045 | [12 empty] | DIESEL (LTR)
YIELD POINT | 31 | 30 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 5045 | [12 empty] | RIG TANK | 100563
GEL ST. | 10/14 | 12/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 16879
WL (ml/30 min) | 3.2 | 3.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 7130
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3 |  | RPM BTM. | [15 empty] | RECEIVED | 23856
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 165 |  | WOB (TON) | [15 empty] | TOTAL | 117442
ALK (FILT.) | 0.4/1.2 | 0.4/1.2 | PICK-UP WT. (TON) |  | 173 |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 170 |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 582606
MAX SHIELD % | 3 | 3 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 61746
KCl (mg/l) | 60061.1 | 60061.1 | JAR | 27.36 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 65400
CHLORIDES (mg/l) | 33000 | 33000 | 5" HWDPS | 27.36 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | -
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 27.36 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 207.1 |  |  | MPCL | 5
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 7 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 16 |  |  | MPCL SERV | 20
SOLIDS % | 40.34 | 40.34 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 7.53 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 34188.9208 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15696716.4849 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 78.85% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4990 | 620/640 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4990 | 800/800 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2019-11-09 | 2019-12-09 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4990 | 920/940 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-12-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-11-13 | 2019-12-12 | NEXT BOP TEST DATE |  | 2019-12-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43802 | 43802.0208 | 0.5 | DRL | NPT-UP | MIL | OBSERVED ROTARY STALLED. P/U STRING / BIT UP TO 4995M TO RELEASE THE TORQUE.
43802.0208 | 43802.0521 | 0.75 | DRL | NPT-UP | CIR | SWEPT 25 BBL HI-VIS PILL.
43802.0521 | 43802.1979 | 3.5 | DRL | NPT-UP | MIL | ATTEMPTED TO SWALLOW THE FISH AGAIN. OBSERVED ROTARY STALLED MANY TIMES WHILE SWALLOWING FISH. ATTEMPTED TO CLEAR WITH ROTATION AND HIGH GPM. SWALLOWED FISH & SLOWLY MILLED DOWN TO 4999.73M.
43802.1979 | 43802.3021 | 2.5 | DRL | NPT-UP | CIR | SWEPT 25 BBL HI-VIS PILL & CIRCULATED TILL SHAKERS CLEAN.
43802.3021 | 43802.3125 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43802.3125 | 43802.3958 | 2 | DRL | NPT-UP | POOH | POOH FROM 4999.73M TO 4540M. (L/DOWN TOP SINGLE OF STAND # 166). PUMPED OUT TIGHT HOLE SECTION FROM 4720M TO 4709M.
43802.3958 | 43802.4062 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED - WELL STATIC.
43802.4062 | 43802.8542 | 10.75 | DRL | NPT-UP | POOH | POOH FROM 4540M TO 207M.
43802.8542 | 43802.8646 | 0.25 | DRL | NPT-UP | FC | FLOW CHECKED.WELL STATIC.
43802.8646 | 43802.9271 | 1.5 | DRL | NPT-UP | BHA | POOH BHA TO SURFACE. L/D JAR, SKIRT, MILL & BIT SUB.
43802.9271 | 43803 | 1.75 | DRL | NPT-UP | RS | SERVICED TDS. SLIPPED & CUT 100FT DRILL LINE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43802 | 43802.0208 | 0.5 | DRL | NPT-UP | RS | CONT'D WORKING ON DRILL LINE. ADJUSTED CROWN-O-MATIC & CALLIBRATED ACS.
43802.0208 | 43802.1979 | 4.25 | DRL | NPT-UP | BOPT | HELD PJSM. M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING. RIH 2x5" DP STDS. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/TESTED ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), LOWER PIPE RAMS, BLIND RAMS, HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. INSTALLED WEAR BUSHING & L/D PLUG ASSY.
43802.1979 | 43802.25 | 1.25 | DRL | NPT-UP | BHA | PREPARED RIG FLOOR FOR FISHING ASSEMBLY. HELD PJSM. P/U & M/U WASHOVER PIPE ASSY IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | M/U WASHOVER PIPE ASSY IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | MILLED THE FISH DOWN TO 4999.73M. CIRCULATED & POOH TO SURFACE. SLIPPED & CUT 100FT DRILL LINE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH WASHOVER PIPE + MILL BIT ASSY. PERFORM WASHOVER OPERATION & DRESS TOP OF FISH.
REMARKS |  |  | WASH PIPE ROTATING HRS = 99.33 HRS ; CIRC HRS = 147.36 HRS @ 0:00 HRS.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15