## DDR#215
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 215
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-12-05
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK / ADNAN / MOHSIN |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 214.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-12-04 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 38 |  | BHA NO. |  |  | 51 | IN (M) |  | 5045 |  | OUT (M) |  |  | STRING (BBL) | 286.2
CHECK TIME | 4:00 | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 21 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 765.8
DEPTH, MD (M) | 5045 | 5045 | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 7.125 |  | 8 3/8" ROTARY SHOE |  |  | 8.375 | 7.3125 |  | FJWP |  | 1.15 |  |  | PITS (BBL) | 610
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | WEATHERFORD |  | 2x8 1/8" W.PIPES |  |  | 8.125 | 7.25 |  | FJWP |  | 18.52 | 2.4343 |  | ACT. SYS (BBL) | 1662
MW OUT (SG) |  | 1.85 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MILL BIT |  | DRIVE SUB |  |  | 8.0625 | 2.25 |  | 4 1/2 REG |  | 0.55 | 0.072293 |  | RESV. SYS (BBL) | 388
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | 1360818 |  | BIT SUB |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 1.06 | 0.13933 |  | KILL MUD (BBL) | 680
FL TEMP. °F |  | 140 | AVG. WOB (TON) |  |  |  | IADC CODE |  |  | - |  | 9 x DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 83.32 | 10.9518 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 67 | 62 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6x PORTS |  | D. JAR |  |  | 6.375 | 2.75 |  | 4 1/2 IF |  | 9.8 | 0.71903 |  | TOTAL | 2050
PV | 46 | 47 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  | 5045 |  | 3 x DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.78 | 2.0382 |  | DIESEL (LTR)
YIELD POINT | 31 | 32 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  | 5045 |  | 9 x HWDP |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 83.22 | 6.1059 |  | RIG TANK | 120175
GEL ST. | 10/14 | 11/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 16324
WL (ml/30 min) | 3.2 | 3.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 4943
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 3-4 |  | RPM BTM. | [15 empty] | RECEIVED | 24000
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 167 |  | WOB (TON) | [15 empty] | TOTAL | 136499
ALK (FILT.) | 0.4/1.2 | 0.4/1.2 | PICK-UP WT. (TON) |  | 170 |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  | 163 |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 649971
MAX SHIELD % | 3 | 3 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 75000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 59237
KCl (mg/l) | 60061.1 | 59107.7 | JAR | 30.21 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 118700
CHLORIDES (mg/l) | 33000 | 32500 | 5" HWDPS | 30.21 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | -
HARDNESS (mg/l) | 320 | 320 | 6 1/2" DCS | 30.21 | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 225.4 |  |  | MPCL | 5
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  | 2.85 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 15 |  |  | MPCL SERV | 16
SOLIDS % | 40.34 | 40.36 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 9 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 4.9 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 105
DAILY WELL COST (US$) |  | 49124.6896 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15745841.1745 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 79.1% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 |  | 4990 | 620/640 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 |  | 4990 | 800/800 |  |  | KAMLIAL | 1245/1245
FIRE DRILL | 2019-11-09 | 2019-12-09 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 |  | 4990 | 920/940 |  |  | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-10-20 | 2019-11-19 | LAST BOP TEST DATE |  | 2019-12-04 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-11-13 | 2019-12-12 | NEXT BOP TEST DATE |  | 2019-12-19 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-04
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43803 | 43803.0208 | 0.5 | DRL | NPT-UP | RS | CONT'D WORKING ON DRILL LINE. ADJUSTED CROWN-O-MATIC & CALLIBRATED ACS.
43803.0208 | 43803.1979 | 4.25 | DRL | NPT-UP | BOPT | HELD PJSM. M/U COMBINATION TOOL ASSY & RETRIEVED WEAR BUSHING. RIH 2x5" DP STDS. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/TESTED ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), LOWER PIPE RAMS, BLIND RAMS, HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. INSTALLED WEAR BUSHING & L/D PLUG ASSY.
43803.1979 | 43803.3438 | 3.5 | DRL | NPT-UP | BHA | HELD PJSM. PREPARED RIG FLOOR FOR FISHING ASSEMBLY. P/U & M/U WASHOVER PIPE ASSY + MILL BIT AS PER BHA & RIH DOWN TO 225M.
43803.3438 | 43803.3542 | 0.25 | DRL | NPT-UP | CIR | FLUSHED BHA.
43803.3542 | 43803.7708 | 10 | DRL | NPT-UP | RIH | RIH FROM 225M TO 4540M. FILLED STRING AFTER EVERY 20 STANDS.
43803.7708 | 43803.7812 | 0.25 | DRL | NPT-UP | CIR | BROKE CIRCULATION.
43803.7812 | 43803.8958 | 2.75 | DRL | NPT-UP | RIH | RIH FROM 4540M TO 4999.9M. (WASHED DOWN FROM 4905M TO 4931M. REAMED AT 4931M. PRECAUTIONARY WASHED DOWN LAST STAND). TAGGED FISH AT 4999.9M. SWALLOWED THE FISH SUCCESSFULLY DOWN TO 5000.5M.
43803.8958 | 43804 | 2.5 | DRL | NPT-UP | F | WASHED OVER FROM 5000.5M TO 5015.7M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-05
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43804 | 43804.25 | 6 | DRL | NPT-UP | F | WASHED OVER FROM 5015.7M TO 5018.4M & IS IN PROGRESS. (OBSERVED FREQUENT ROTARY STALLING / TORQUE FLUCTUATIONS WITH PRESSURE INCREASE BELOW 5016M).
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | WASHOVER IS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONDUCTED BOP PRESSURE TEST AS PER PLAN. RIH WASHOVER PIPE + MILL BIT ASSY DOWN TO TOP OF FISH. SWALLOWED FISH & WASHED OVER FROM 5000.5M TO 5015.7M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | WASHOVER & DRESS TOP OF FISH. CIRCULATE & POOH TO SURFACE.
REMARKS |  |  | WASH PIPE ROTATING HRS = 102.18 HRS ; CIRC HRS = 152.26 HRS @ 0:00 HRS.
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+15