## DDR#217
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 217
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SAYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4874 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + 0.13
RIG REP. (TP): |  | TARIQ. M. BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4874 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-07-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  |  |  | BHA No. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1130.94
DEPTH, MD (M) |  | 4874 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  |  |  | EXPANDABLE ANCHOR |  |  | 5.75 | - |  | - |  | 2 |  |  | PITS (BBL) | 689
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  |  |  | WHIPSTOCK ASSY |  |  | 8 | - |  | BOLT |  | 5.57 |  |  | ACT. SYS (BBL) | 1819.94
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  | FAST-TRACK TRI MILL |  |  | 8.5 | 2.25 |  | 4 1/2 IF |  | 4.18 |  |  | RESV. SYS (BBL) | 0
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  |  |  | RUNNING TOOL |  |  | 6.5 | - |  | 4 1/2 IF |  | 1.79 |  |  | KILL MUD (BBL) | 1150
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  |  |  | 1 X 5" HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 9.3 |  |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 68 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  |  |  | MULTICYCLE VALVE |  |  | 6.75 | - |  | 4 1/2 IF |  | 1.61 |  |  | TOTAL | 2969.94
PV |  | 37 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | FLOAT SUB |  |  | 6.75 | 2.9375 |  | 4 1/2 IF |  | 0.77 |  |  | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | UBHO SUB |  |  | 6.875 | 3 7/16 |  | 4 1/2 IF |  | 0.96 |  |  | RIG TANK | 123000
GEL ST. |  | 6/11 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 12 X 6 1/2" DC |  |  | 6.5 | 2 13/16 |  | 4 1/2 IF |  | 111.06 |  |  | CAMP TANK | 30150
WL (ml/30 min.) |  | 3.3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 18 X 5" HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 168.24 |  |  | CONSUMED | 4650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 5" PUP JOINT |  |  | 5 | 3.25 |  | 4 1/2 IF |  | 3.08 |  |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 153150
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 78000
KCl (mg/l) |  | 50718.2 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 38000
CHLORIDES |  | 23000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) | [14 empty] | TOTAL | 400000
CALCIUM |  | 220 | 6 1/2" DCS |  |  |  | HSI | [14 empty] | POB
OIL % |  | 2 |  |  |  |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 308.56 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT No. |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 23 |  |  | MPCL SERV | 19
SOLIDS % |  | 19.22 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 8 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 110
DAILY WELL COST (US$) |  | 34311 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 14082804 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 78.03% | MUD CLEANER | 2 x 170 + 1 x 170 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-07-16 | 2018-07-31 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-07-19 | 2018-08-18 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | CHORGALI
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | SAKESAR
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-08-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | NAMMAL
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43306 | 43306.0208 | 0.5 | DRL | PT-P | CIR | CONT'D CIRCULATION TO CONDITION MUD.
43306.0208 | 43306.0312 | 0.25 | DRL | PT-P | FC | FLOW CHECKED - WELL STATIC.
43306.0312 | 43306.3333 | 7.25 | DRL | PT-P | POOH | PUMPED SLUG, POOH FROM 3498M TO SURFACE. L/DOWN STINGER/MULE SHOE
43306.3333 | 43306.5833 | 6 | DRL | PT-P | BOPT | PJSM. RETRIEVED WEAR BUSHING. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), TDS IBOP, FOSV, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE & LOWER PIPE RAM BOP (5" RAMS) @ 300/8000 PSI FOR 5/10 MIN - OK. PRESSURE TESTED BLIND RAM BOP @ 300/8000 PSI FOR 5/10 MIN.OK. RETRIEVED TEST PLUG, SET WEAR BUSHING INSIDE THS, & L/DOWN TEST PLUG ASSY.
43306.5833 | 43306.6354 | 1.25 | DRL | NPT-P | RS | HELD PJSM. CUT 104 FEET OF DRILL LINE & SLIPPED 104 FEET. ADJUSTED CROWN-O-MATIC & RESET ACS VALUES.
43306.6354 | 43306.875 | 5.75 | DRL | NPT-UP | OTH | ARRANGED SERVICES FOR SIDETRACK.
43306.875 | 43306.9167 | 1 | DRL | PT-UP | E/C | CHECKED AND CALIBRATED GYRO TOOL WITH UBHO AND W/LINE.
43306.9167 | 43307 | 2 | DRL | PT-UP | RU | HELD PJSM, P/UP & M/UP UBHO + FLOAT SUB + MULTI CYCLE VALVE + 1X JT 5'' HWDP + W.STOCK RUNNING TOOL + FAST TRACK TRI-MILL ASSY + W.STOCK ASSY. CONNECTED AND SECURED TRI-MILL ASSY WITH W.STOCK. INSTALLED NOZZLES IN LEAD MILL. CONNECTED HOSE WITH W.STOCK ASSY & LEAD MILL, FILLED UP RUNNING TOOL WITH HYDRAULIC OIL & INSTALLED PISTON IN SAME. ADJUSTED TOOL FACE OFFSET.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43307 | 43307.0729 | 1.75 | DRL | PT-UP | BHA | RIH W.STOCK ASSEMBLY AS PER BHA DOWN TO 308M. FILLED UP AFTER RIH BHA.
43307.0729 | 43307.25 | 4.25 | DRL | PT-UP | RIH | CONT'D RIH FROM 308M TO 1195M. FILLED UP STRING AFTER EVERY 7 STANDS.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH WITH WHIPSTOCK IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATION, FLOW CHECK, POOH TO SURFACE, BOP TEST AS PER POLICY, CUT & SLIPPED D.LINE, ARRANGED SERVICES FOR SIDETRACK, HELD PJSM, P/UP AND M/UP WHIPSTOCK ASSEMBLY.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH W.STOCK ASSY TO 3321M, RIH GYRO TOOLS ON W/LINE, ORIENTATION OF W.STOCK, SETTING, WINDOW CUTTING/MILLING OPERATION.
REMARKS |  |  | PREPARED 1150 BBL KILL MUD OF 2.0 S.G.
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14