## DDR#219
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 219
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 3318.5 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 2.13
RIG REP. (TP): |  | TARIQ. M. BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 3318.5 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 5.5
2018-07-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 12 |  | BHA No. |  |  | 31 | IN (M) |  | 3318.5 |  | OUT (M) |  |  | STRING (BBL) | 42
CHECK TIME | 11:59 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 648
DEPTH, MD (M) |  | 3318.5 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | HALLIBURTON |  | TRICONE BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 770
MW IN (SG) |  | 1.5 | DAILY PROGRESS (M) |  |  |  | TYPE |  | EQH30R |  | MUD MOTOR |  |  | 6.625 | - |  | 4 1/2 IF |  | 8.2 | 1.123 |  | ACT. SYS (BBL) | 1460
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | 12285957 |  | FLOAT SUB |  |  | 6.8125 | 2.75 |  | 4 1/2 IF |  | 0.82 | 0.1123 |  | RESV. SYS (BBL) | 139
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 537 |  | LOWER SAVER SUB |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | KILL MUD (BBL) | 1200
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3 x 18/32" |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 3318.5 |  | UBHO SUB |  |  | 6.8125 | 3 |  | 4 1/2 IF |  | 0.96 | 0.13148 |  | TOTAL | 2799
PV |  | 35 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.34 | 1.2792 |  | DIESEL (LTR)
YIELD POINT |  | 23 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 4 X 6 1/2" DCS |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 37.02 | 5.0701 |  | RIG TANK | 112000
GEL ST. |  | 6/9 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 15 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.21 | 10.4362 |  | CAMP TANK | 28850
WL (ml/30 min.) |  | 3.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | DRILLING JAR |  |  | 6.375 | 2.9375 |  | 4 1/2 IF |  | 5.98 | 0.819 |  | CONSUMED | 7450
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.11 | 6.2605 |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 140850
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 20000
KCl (mg/l) |  | 50718.2 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 20000
CHLORIDES |  | 23000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) |  | 0.7455 | [12 empty] | TOTAL | 400000
CALCIUM |  | 220 | 6 1/2" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 2 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 296.95 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  |  |  | BIT NO. 12 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 21 |  |  | MPCL SERV | 22
SOLIDS % |  | 19.22 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY | 4
M.B.T. |  | 8 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 47
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | [11 empty] | TOTAL | 111
DAILY WELL COST (US$) |  | 35363.8044 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | [11 empty] | WELL CONTROL
COMMULATIVE COST (US$) |  | 14198470.2848 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 78.67% | MUD CLEANER | 2 x 170 + 1 x 170 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-07-16 | 2018-07-31 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-07-19 | 2018-08-18 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-08-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43308 | 43308.2396 | 5.75 | DRL | PT-UP | MIL | MILLED 9 5/8" CASING WINDOW FROM 3313M TO 3318.5M.
43308.2396 | 43308.3438 | 2.5 | DRL | PT-UP | CIR | PUMPED 50 BBL HI-VIS PILL & CIRCULATED TO CLEAN HOLE, MEANWHILE ROTATED & RECIPROCATED STRING & PASSED MILLS SEVERAL TIMES THRU CASING WINDOW TO CLEAR ANY OBSTRUCTION.
43308.3438 | 43308.3542 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - WELL STATIC.
43308.3542 | 43308.5833 | 5.5 | DRL | PT-UP | POOH | POOH WHIPSTOCK MILLING ASSY FORM 3318.5M TO TOP OF BHA @ 308M.
43308.5833 | 43308.5938 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - WELL STATIC.
43308.5938 | 43308.6771 | 2 | DRL | PT-UP | BHA | POOH TO SURFACE & L/DOWN MILLING BHA. GAUGED & FOUND MILLING BITS WITHIN ACCEPTABLE LIMITS.
43308.6771 | 43308.7708 | 2.25 | DRL | PT-UP | BHA | P/UP & M/UP NEW 8 1/2" TCI BIT WITH MUD MOTOR & DIRECTIONAL BHA. ADJUSTED MUD MOTOR BEND TO 1.5 DEG & RIH BHA TO 29M.
43308.7708 | 43308.7917 | 0.5 | DRL | PT-UP | E/C | SHALLOW FUNCTION TESTED MUD MOTOR & MWD TOOL, FOUND OK.
43308.7917 | 43308.8646 | 1.75 | DRL | PT-UP | BHA | RIH DIRECTIONAL BHA FROM 29M TO 296M. WHILE RIH P/UP 1 X 6 1/2" DC + 6 X 5" HWDPS FROM PIPE RACKS.
43308.8646 | 43309 | 3.25 | DRL | PT-UP | RIH | RIH BHA FROM 296M TO 1500M. WHILE RIH FILLED UP STRING WITH MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43309 | 43309.1875 | 4.5 | DRL | PT-UP | RIH | CONT'D RIH FROM 1500M TO 3318.5M & PASSED BIT THRU CASING WINDOW WITHOUT ANY OBSTRUCTION. WHILE RIH FILLED UP STRING WITH MUD.
43309.1875 | 43309.25 | 1.5 | DRL | PT-UP | W/L | HELD PJSM. R/UP W.F W/LINE GEAR. RIH GYRO TOOL ON W/LINE TO 2500M.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | RIH GYRO TOOL ON W/LINE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | MILLED 9 5/8" CASING WINDOW FROM 3313M TO 3318.5M. PUMPED HI-VIS PILL & CIRCULATED TO CLEAN HOLE. POOH TO SURFACE. M/UP & RIH NEW 8 1/2" TCI BIT WITH MUD MOTOR & DIRECTIONAL BHA TO 1500M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH GYRO TOOL & ADJUST MUD MOTOR TOOLFACE. POOH GYRO TOOL TO SURFACE. KICK-OFF & DRILL AHEAD 8 1/2" HOLE IN SLIDE & ROTARY MODE.
REMARKS
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14