## DDR#221
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 221
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-07-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 3385 / 3383.9 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 4.13
RIG REP. (TP): |  | TARIQ. M. BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 3393 / 3391.9 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 42
2018-07-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | 5% KCL PERFLEX |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 12 |  | BHA No. |  |  | 31 | IN (M) |  | 3318.5 |  | OUT (M) |  |  | STRING (BBL) | 192
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 3385 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 508
DEPTH, MD (M) | 3357 | 3385 | TVD @ 00:00HR (M) |  | 3383.9 |  | MANUFACTURER |  | HALLIBURTON |  | TRICONE BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 810
MW IN (SG) | 1.5 | 1.5 | DAILY PROGRESS (M) |  | 42 |  | TYPE |  | EQH30R |  | MUD MOTOR |  |  | 6.625 | - |  | 4 1/2 IF |  | 8.2 | 1.123 |  | ACT. SYS (BBL) | 1510
MW OUT (SG) | 1.5 | 1.5 | INST. ROP (M/HR) |  | 1.5 |  | SERIAL NO. |  | 12285957 |  | FLOAT SUB |  |  | 6.8125 | 2.75 |  | 4 1/2 IF |  | 0.82 | 0.1123 |  | RESV. SYS (BBL) | 156
ECD (SG) | 1.56 | 1.56 | AVG. ROP (M/HR) |  | 1.92 |  | IADC CODE |  | 537 |  | LOWER SAVER SUB |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | KILL MUD (BBL) | 1200
FL TEMP. °F | 140 | 140 | AVG. WOB (TON) |  | 8 - 10 |  | NOZZLES |  | 3 x 18/32" |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 53 | 54 | AVG. RPM SURFACE |  | 0 - 30 |  | DEPTH IN (M) |  | 3318.5 |  | UBHO SUB |  |  | 6.8125 | 3 |  | 4 1/2 IF |  | 0.96 | 0.13148 |  | TOTAL | 2866
PV | 34 | 33 | AVG. RPM DOWNHOLE |  | 120 - 150 |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.34 | 1.2792 |  | DIESEL (LTR)
YIELD POINT | 22 | 22 | FLOWRATE (GPM) |  | 425 |  | METERAGE (M) |  | 66.5 |  | 4 X 6 1/2" DCS |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 37.02 | 5.0701 |  | RIG TANK | 122000
GEL ST. | 8/11 | 7/11 | PRESSURE (PSI) |  | 2450 - 2550 |  | RPM SURF. |  | 0 - 30 |  | 15 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.21 | 10.4362 |  | CAMP TANK | 27550
WL (ml/30 min.) | 3.2 | 3.2 | TORQ. ON-BTM (KLB-FT) |  | 2 - 3 |  | RPM BTM. |  | 120 - 150 |  | DRILLING JAR |  |  | 6.375 | 2.9375 |  | 4 1/2 IF |  | 5.98 | 0.819 |  | CONSUMED | 11650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1 - 2 |  | WOB (TON) |  | 6 - 10 |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.11 | 6.2605 |  | RECEIVED | 25000
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  | 134 |  | AVG. ROP (M/HR) |  | 1.8711 | [12 empty] | TOTAL | 149550
ALK (FILT.) | 0.4 | 0.4 | PICK-UP WT. (TON) |  | 136 |  | BIT ROT HRS. |  | 35.54 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 130 |  | K-REVS IN 24 HRS |  | 170.046 | [12 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS (ON BTM) |  | 278.622 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 66.7 | [12 empty] | CONSUMED | 131150
KCl (mg/l) | 49574.2 | 49574.2 | JAR | 22.46 | STAB - 1 |  | JET VELOCITY (M/SEC) |  | 56 | [12 empty] | RECEIVED | 131150
CHLORIDES | 23000 | 23000 | 5" HWDPS | 22.46 | STAB - 2 |  | TFA (IN²) |  | 0.7455 | [12 empty] | TOTAL | 400000
CALCIUM | 180 | 180 | 6 1/2" DCS | 22.46 | NMDC | 14.56 | HSI |  | 1.7 | [12 empty] | POB
OIL % | 2 | 2 | MUD MOTOR | 14.56 | SPSA | 14.56 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 296.95 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  | 22.46 |  | BIT NO. 12 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 21 |  |  | MPCL SERV | 19
SOLIDS % | 18.41 | 18.41 | ON BOTTOM HRS |  | 35.56 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY | 4
M.B.T. | 7.5 | 7.5 | CIRC. HRS |  | 39.51 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 20" SURFACE CASING |  |  | 594 | 3322 / 3321.2 |  | 3.14 | [6 empty] | MWD |  | TOTAL | 105
DAILY WELL COST (US$) |  | 81029.4325 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3352 / 3351.1 |  | 6.2 |  | 60.7 |  |  | 5.07 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14413368.4674 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | [11 empty] | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 79.86% | MUD CLEANER | 2 x 170 + 1 x 170 |  |  | 7" LINER | [14 empty] | FIT (EMW) | 1.8
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI) | 1932
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-07-16 | 2018-07-31 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 3322 |  | 450/450 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 3322 |  | 600/590 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 3322 |  | 800/790 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-07-19 | 2018-08-18 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-08-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43310 | 43311 | 24 | DRL | PT-UP | DM | DRILLED AHEAD 8 1/2" HOLE FROM 3343M TO 3385M IN ROTARY & SLIDE MODES. REAMED DRILLED SECTION & RECORDED MWD SURVEY PRIOR CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43311 | 43311.25 | 6 | DRL | PT-UP | DM | DRILLED AHEAD 8 1/2" HOLE FROM 3385M TO 3393M IN ROTARY & SLIDE MODES.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | REAMING
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED AHEAD 8 1/2" HOLE FROM 3343M TO 3385M IN ROTARY & SLIDE MODES. REAMED DRILLED SECTION & RECORDED MWD SURVEY PRIOR CONNECTION.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | REAM & RECORD MWD SURVEY. CIRCULATE & CLEAN HOLE. POOH TO SURFACE. M/UP & RIH NEW 8 1/2" PDC WITH DIRECTIONAL BHA TO BTM & DRILL AHEAD 8 1/2" HOLE AS PER DIRECTIONAL PLAN.
REMARKS |  |  | RELEASED W.F W/LINE SERVICES + GYRO ENGINEER & EQUIPMENT ON 29-JULY-2018.
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14