## DDR#223
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 223
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-01
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / MUHAMMAD AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 3395 / 3393.8 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 6.13
RIG REP. (TP): |  | TARIQ. M. BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 3402 / 3400.7 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 2
2018-07-31 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 13 |  | BHA No. |  |  | 32 | IN (M) |  | 3393 |  | OUT (M) |  |  | STRING (BBL) | 189
CHECK TIME |  | 23:59 | MD @ 00:00HR (M) |  | 3395 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 513
DEPTH, MD (M) |  | 3395 | TVD @ 00:00HR (M) |  | 3393.8 |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 846
MW IN (SG) |  | 1.65 | DAILY PROGRESS (M) |  | 2 |  | TYPE |  | MDSi616LPBX |  | MUD MOTOR |  |  | 6.625 | - |  | 4 1/2 IF |  | 8.2 | 1.123 |  | ACT. SYS (BBL) | 1548
MW OUT (SG) |  | 1.65 | INST. ROP (M/HR) |  | 2.7 |  | SERIAL NO. |  | JN5340 |  | FLOAT SUB |  |  | 6.8125 | 2.75 |  | 4 1/2 IF |  | 0.82 | 0.1123 |  | RESV. SYS (BBL) | 555
ECD (SG) |  | 1.71 | AVG. ROP (M/HR) |  | 2.77 |  | IADC CODE |  | 323 |  | LOWER SAVER SUB |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | KILL MUD (BBL) | 750
FL TEMP. °F |  | 121 | AVG. WOB (TON) |  | 2 - 6 |  | NOZZLES |  | 3x13 + 3x14 |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 56 | AVG. RPM SURFACE |  | 0 - 30 |  | DEPTH IN (M) |  | 3393 |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.34 | 1.2792 |  | TOTAL | 2853
PV |  | 38 | AVG. RPM DOWNHOLE |  | 120 - 150 |  | DEPTH OUT (M) |  |  |  | 4 X 6 1/2" DCS |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 37.02 | 5.0701 |  | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  | 425 |  | METERAGE (M) |  | 2 |  | 15 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.21 | 10.4362 |  | RIG TANK | 137000
GEL ST. |  | 9/14 | PRESSURE (PSI) |  | 2500 - 2700 |  | RPM SURF. |  | 0 - 30 |  | DRILLING JAR |  |  | 6.375 | 2.9375 |  | 4 1/2 IF |  | 5.98 | 0.819 |  | CAMP TANK | 26250
WL (ml/30 min.) |  | 3.4 | TORQ. ON-BTM (KLB-FT) |  | 3 - 4 |  | RPM BTM. |  | 120 - 150 |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.11 | 6.2605 |  | CONSUMED | 5650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  | 1 - 2 |  | WOB (TON) |  | 2 - 6 | [12 empty] | RECEIVED | 25000
ALK (MUD) |  | 0.5 | STRING WT. (TON) - ROT |  | 132 |  | AVG. ROP (M/HR) |  | 2.7778 | [12 empty] | TOTAL | 163250
ALK (FILT.) |  | 0.4 | PICK-UP WT. (TON) |  | 135 |  | BIT ROT HRS. |  | 0.72 | [12 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  | 130 |  | K-REVS IN 24 HRS |  | 6.57 | [12 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS (ON BTM) |  | 6.57 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 66.7 | [12 empty] | CONSUMED | 94690
KCl (mg/l) |  | 53006.3 | JAR | 39.68 | STAB - 1 |  | JET VELOCITY (M/SEC) |  | 49.8 | [12 empty] | RECEIVED | 94690
CHLORIDES |  | 25000 | 5" HWDPS | 39.68 | STAB - 2 |  | TFA (IN²) |  | 0.8397 | [12 empty] | TOTAL | 400000
CALCIUM |  | 180 | 6 1/2" DCS | 39.68 | NMDC | 31.78 | HSI |  | 1.4 | [12 empty] | POB
OIL % |  | 2 | MUD MOTOR | 31.78 | SPSA | 31.78 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 295.99 |  |  | MPCL | 4
LUBE % |  |  | BHA ROT. HRS |  | 39.68 |  | BIT NO. 12 |  | 2-2-WT-A-F-1-NO-HR |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 18
SOLIDS % |  | 23.89 | ON BOTTOM HRS |  | 42.24 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY | 4
M.B.T. |  | 7.5 | CIRC. HRS |  | 62.26 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 26
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3322 / 3321.2 |  | 3.14 | [6 empty] | MWD |  | TOTAL | 113
DAILY WELL COST (US$) |  | 61490.1298 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 3352 / 3351.1 |  | 6.2 |  | 60.7 |  |  | 5.07 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14518947.357 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 3379 / 3377.9 |  | 8.01 |  | 77.12 |  |  | 3 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 80.44% | MUD CLEANER | 2 x 170 + 1 x 170 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-07-16 | 2018-07-31 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 3393 |  | 235/225 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 3393 |  | 425/405 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 3393 |  | 680/650 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-07-19 | 2018-08-18 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-07-25 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-08-08 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-07-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43312 | 43312.0625 | 1.5 | DRL | NPT-UP | CIR | CIRCULATED & HOMOGENISED MUD COLUMN TO 1.65 SG.
43312.0625 | 43312.0833 | 0.5 | DRL | PT-UP | FC | FLOW CHECKED - OBSERVED WELL TRICKLING @ 2.8 BBLS/MIN & DECREASED TO 1.3 BBL/HR.
43312.0833 | 43312.1667 | 2 | DRL | PT-UP | POOH | POOH FROM 3327M TO 2510M.
43312.1667 | 43312.1875 | 0.5 | DRL | PT-UP | FC | FLOW CHECKED - WELL STATIC.
43312.1875 | 43312.3125 | 3 | DRL | PT-UP | POOH | POOH FROM 2510M TO 782M. FOUND HOLE NOT TAKING CALCULATED VOLUME TO FILL.
43312.3125 | 43312.3333 | 0.5 | DRL | PT-UP | FC | FLOW CHECKED - OBSERVED WELL TRICKLING @ 1.6 BBL/HR & DECREASED TO 1.25 BBL/HR.
43312.3333 | 43312.3958 | 1.5 | DRL | PT-UP | POOH | POOH FROM 782M TO TOP OF BHA @ 296M.
43312.3958 | 43312.4167 | 0.5 | DRL | PT-UP | FC | FLOW CHECKED - OBSERVED WELL TRICKLING @ 2 BBL/HR & DECREASED TO 1.13 BBL/HR.
43312.4167 | 43312.5 | 2 | DRL | PT-UP | BHA | POOH BHA FROM 296M TO SURFACE. L/DOWN UBHO. INSPECTED MWD TOOL, MUD MOTOR & BIT, FOUND OK.
43312.5 | 43312.5208 | 0.5 | DRL | PT-UP | E/C | RIH MUD MOTOR & MWD TOOL TO 20M. SHALLOW FUNCTION TESTED MUD MOTOR & MWD TOOL, FOUND OK. RECORDED 1050 PSI @ 425 GPM.
43312.5208 | 43312.625 | 2.5 | DRL | PT-UP | BHA | P/BACK TO SURFACE & L/DOWN 8 1/2" TCI BIT. M/UP & RIH NEW 8 1/2" PDC BIT WITH MUD MOTOR & DIRECTIONAL BHA TO 296M.
43312.625 | 43312.9583 | 8 | DRL | PT-UP | RIH | RIH BHA FROM 296M TO 3367M. PRECAUTIONARY WASHED DOWN LAST STAND & TAGGED BTM @ 3393M. WHILE RIH FILLED UP STRING WITH MUD.
43312.9583 | 43313 | 1 | DRL | PT-UP | DM | BROKE-IN NEW 8 1/2" PDC BIT & DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 3393M TO 3395M IN ROTARY MODE.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43313 | 43313.25 | 6 | DRL | PT-UP | DM | DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 3395M TO 3402M IN ROTARY & SLIDE MODES.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / SANDSTONE & CLAYSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2" DIRECTIONAL HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CIRCULATED & HOMOGENISED MUD COLUMN TO 1.65 SG. POOH FROM 3327M TO SURFACE. M/UP & RIH NEW 8 1/2" PDC BIT WITH MUD MOTOR & DIRECTIONAL BHA TO BTM @ 3393M. DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 3393M TO 3395M IN ROTARY MODE.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" DIRECTIONAL HOLE AS PER PLAN.
REMARKS
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14