## DDR#231
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 231
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-09
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 3878 / 3816.6 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 14.13
RIG REP. (TP): |  | TARIQ. M. BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 3900 / 3833.0 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-08-08 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 13RR1 |  | BHA No. |  |  | 33 | IN (M) |  | 3878 |  | OUT (M) |  |  | STRING (BBL) | 221
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 583
DEPTH, MD (M) |  | 3878 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 836
MW IN (SG) |  | 1.66 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MDSi616LBPX |  | XCEED 675 |  |  | 6.6875 | 3.75 |  | 4 1/2 IF |  | 8.05 | 1.1025 |  | ACT. SYS (BBL) | 1640
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN5340 |  | LOWER SAVER SUB |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | RESV. SYS (BBL) | 545
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 323 |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | KILL MUD (BBL) | 750
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3x13 + 3x14 |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.34 | 1.2792 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 58 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 3878 |  | 4 X 6 1/2" DCS |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 37.02 | 5.0701 |  | TOTAL | 2935
PV |  | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | 15 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.21 | 10.4362 |  | DIESEL (LTR)
YIELD POINT |  | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | DRILLING JAR |  |  | 6.375 | 2.9375 |  | 4 1/2 IF |  | 5.98 | 0.819 |  | RIG TANK | 108000
GEL ST. |  | 9/22 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.11 | 6.2605 |  | CAMP TANK | 31050
WL (ml/30 min.) |  | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. | [14 empty] | CONSUMED | 4650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 139050
ALK (FILT.) |  | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 75000
KCl (mg/l) |  | 54913 | JAR | 116.66 | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 35000
CHLORIDES |  | 26000 | 5" HWDPS | 116.66 | STAB - 2 |  | TFA (IN²) |  | 0.8397 | [12 empty] | TOTAL | 400000
CALCIUM |  | 180 | 6 1/2" DCS | 116.66 | NMDC | 108.73 | HSI | [14 empty] | POB
OIL % |  | 3.5 | XCEED RSS | 2.03 | SPSA | 108.73 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 295.02 |  |  | MPCL | 5
LUBE % |  |  | BHA ROT. HRS |  | 116.66 |  | BIT NO. 13RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 17
SOLIDS % |  | 23.87 | ON BOTTOM HRS |  | 168.99 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 217.66 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 9
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3775 / 3737.4 |  | 37.2 |  | 74.86 |  |  | 1.52 |  | MWD |  | TOTAL | 112
DAILY WELL COST (US$) |  | 39313.0699 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 3804 / 3760.2 |  | 39.1 |  | 75.64 |  |  | 2.03 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14897122.0553 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 3833 / 3782.5 |  | 40.69 |  | 77.26 |  |  | 1.96 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 82.54% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER |  |  |  | 3858 / 3801.4 |  | 41.21 |  | 77.48 |  |  | 0.65 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-07-16 | 2018-07-31 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 3892 |  | 390/380 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 3892 |  | 550/550 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 3892 |  | 760/750 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-07-19 | 2018-08-18 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-08 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-08-22 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-08
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43320 | 43320.0312 | 0.75 | DRL | PT-UP | POOH | POOH FROM 667M TO TOP OF BHA @ 295M.
43320.0312 | 43320.0417 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - LEVEL STATIC.
43320.0417 | 43320.125 | 2 | DRL | PT-UP | BHA | POOH BHA FROM 295M TO SURFACE. WHILE POOH L/DOWN JAR + MWD TOOL (FOUND MWD TOOL WASHED OUT) + FLOAT SUB + MUD MOTOR + BIT.
43320.125 | 43320.3125 | 4.5 | DRL | PT-UP | BOPT | HELD PJSM. RETRIEVED WEAR BUSHING. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), TDS IBOP, FOSV, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE & LOWER PIPE RAM BOP (5" RAMS) @ 300/8000 PSI FOR 5/10 MIN - OK. RETRIEVED TEST PLUG, SET WEAR BUSHING INSIDE THS, FUNCTION TESTED BLIND RAM & L/DOWN TEST PLUG ASSY AND TEST PUMP.
43320.3125 | 43320.3542 | 1 | DRL | PT-UP | BHA | P/UP, M/UP & RIH SAME 8 1/2" PDC BIT (RR1) WITH SLB XCEED DIRECTIONAL BHA DOWN TO 25M.
43320.3542 | 43320.3646 | 0.25 | DRL | PT-UP | E/C | SHALLOW FUNCTION TESTED XCEED & MWD TOOL, FOUND OK. RECORDED 700 PSI @ 400 GPM.
43320.3646 | 43320.4062 | 1 | DRL | PT-UP | BHA | RIH DIRECTIONAL BHA FROM 25M TO 295M.
43320.4062 | 43320.7083 | 7.25 | DRL | PT-UP | RIH | RIH BHA FROM 295M TO 3307M (INSIDE 9 5/8" CASING WINDOW). WHILE RIH FILLED UP STRING WITH MUD.
43320.7083 | 43320.7812 | 1.75 | DRL | NPT-P | RS | CUT & SLIPPED 93 FEET DRILLING LINE. CALIBRATED ACS + CROWN-O-MATIC + HOOK LOAD SENSORS.
43320.7812 | 43320.875 | 2.25 | DRL | PT-UP | RIH | CONT'D RIH FROM 3307M TO 3848M ON ELEVATORS. WHILE RIH FILLED UP STRING WITH MUD.
43320.875 | 43320.9167 | 1 | DRL | NPT-UP | STK | M/UP TDS TO PRECAUTIONARY REAM/WASH DOWN LAST STAND. OBSERVED HIGH ERRATIC TORQUE, ROTARY STALLED & STRING STUCK - UNABLE TO ROTATE & RECIPROCATE STRING. R/BACK DP STAND & M/UP WORKING 5" DP SINGLE. WORKED & RELEASED STRING WITH 75 TON OVERPULL AND P/BACK TO 3832M.
43320.9167 | 43321 | 2 | DRL | PT-UP | RW | PUMPED 25 BBL HI-VIS PILL & HARD REAMED FROM 3832M TO 3864M. MEANWHILE STARTED INCREASING MWT.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43321 | 43321.0729 | 1.75 | DRL | PT-UP | RW | CONT'D HARD REAMED FROM 3864M TO BTM @ 3878M, RECORDED MWD SURVEY & DOWNLINKED XCEED RSS. MEANWHILE INCREASING MWT.
43321.0729 | 43321.25 | 4.25 | DRL | PT-UP | DM | TAGGED BTM & DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 3878M TO 3900M. MEANWHILE INCREASED MWT TO 1.68 SG.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / SANDSTONE, CLAYSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2" DIRECTIONAL HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH BIT FROM 667M TO SURFACE. P/TESTED BOP STACK. M/UP & RIH SAME 8 1/2" PDC BIT (RR1) WITH SLB XCEED DIRECTIONAL BHA TO 3307M. CUT & SLIPPED DRILLING LINE. RIH FROM 3307M TO 3848M ON ELEVATORS. ATTEMPTED TO PRECAUTIONARY REAM/WASH DOWN LAST STAND. OBSERVED HIGH ERRATIC TORQUE, ROTARY STALLED & STRING STUCK. WORKED & RELEASED STRING WITH 75 TON OVERPULL AND P/BACK TO 3832M. PUMPED 25 BBL HI-VIS PILL & HARD REAMED FROM 3832M TO 3864M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" DIRECTIONAL HOLE AS PER PLAN.
REMARKS |  |  | INCREASING DIESEL QUANTITY IN MUD TO 5% TO INCREASE LUBRICITY.
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14