## DDR#232
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 232
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-10
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 3956 / 3873.2 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 15.13
RIG REP. (TP): |  | TARIQ. M. BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 3973 / 3885.4 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 78
2018-08-09 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 13RR1 |  | BHA No. |  |  | 33 | IN (M) |  | 3878 |  | OUT (M) |  |  | STRING (BBL) | 215
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 3956 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 607
DEPTH, MD (M) | 3918 | 3956 | TVD @ 00:00HR (M) |  | 3873.2 |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 805
MW IN (SG) | 1.68 | 1.68 | DAILY PROGRESS (M) |  | 78 |  | TYPE |  | MDSi616LBPX |  | XCEED 675 |  |  | 6.6875 | 3.75 |  | 4 1/2 IF |  | 8.05 | 1.1025 |  | ACT. SYS (BBL) | 1627
MW OUT (SG) | 1.68 | 1.68 | INST. ROP (M/HR) |  | 3 |  | SERIAL NO. |  | JN5340 |  | LOWER SAVER SUB |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | RESV. SYS (BBL) | 525
ECD (SG) | 1.76 | 1.76 | AVG. ROP (M/HR) |  | 3.93 |  | IADC CODE |  | 323 |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | KILL MUD (BBL) | 750
FL TEMP. °F | 151 | 152 | AVG. WOB (TON) |  | 5 - 10 |  | NOZZLES |  | 3x13 + 3x14 |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.34 | 1.2792 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 56 | 59 | AVG. RPM SURFACE |  | 80 - 120 |  | DEPTH IN (M) |  | 3878 |  | 4 X 6 1/2" DCS |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 37.02 | 5.0701 |  | TOTAL | 2902
PV | 35 | 37 | AVG. RPM DOWNHOLE |  | 80 - 120 |  | DEPTH OUT (M) |  |  |  | 15 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 140.21 | 10.4362 |  | DIESEL (LTR)
YIELD POINT | 30 | 29 | FLOWRATE (GPM) |  | 450 |  | METERAGE (M) |  | 78 |  | DRILLING JAR |  |  | 6.375 | 2.9375 |  | 4 1/2 IF |  | 5.98 | 0.819 |  | RIG TANK | 122000
GEL ST. | 8/23 | 9/23 | PRESSURE (PSI) |  | 2880 - 3000 |  | RPM SURF. |  | 80 - 120 |  | 9 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.11 | 6.2605 |  | CAMP TANK | 30400
WL (ml/30 min.) | 3.4 | 3.4 | TORQ. ON-BTM (KLB-FT) |  | 6 - 14 |  | RPM BTM. |  | 80 - 120 | [12 empty] | CONSUMED | 10650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 5 - 7 |  | WOB (TON) |  | 5 - 10 | [12 empty] | RECEIVED | 24000
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 139 |  | AVG. ROP (M/HR) |  | 3.9295 | [12 empty] | TOTAL | 152400
ALK (FILT.) | 0.4 | 0.3 | PICK-UP WT. (TON) |  | 150 |  | BIT ROT HRS. |  | 19.85 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  | 130 |  | K-REVS IN 24 HRS |  | 139.69 | [12 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 139.69 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 70.3 | [12 empty] | CONSUMED | 70460
KCl (mg/l) | 61014.4 | 61967.8 | JAR | 139.89 | STAB - 1 |  | JET VELOCITY (M/SEC) |  | 52.5 | [12 empty] | RECEIVED | 70460
CHLORIDES | 28500 | 29000 | 5" HWDPS | 139.89 | STAB - 2 |  | TFA (IN²) |  | 0.8397 | [12 empty] | TOTAL | 400000
CALCIUM | 180 | 180 | 6 1/2" DCS | 139.89 | NMDC | 131.96 | HSI |  | 1.7 | [12 empty] | POB
OIL % | 3 | 3 | XCEED RSS | 25.26 | SPSA | 131.96 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 295.02 |  |  | MPCL | 5
LUBE % | 2 | 2 | BHA ROT. HRS |  | 139.89 |  | BIT NO. 13RR1 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 17
SOLIDS % | 24.8 | 24.78 | ON BOTTOM HRS |  | 188.84 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 15 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 26.81 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3858 / 3801.3 |  | 41.21 |  | 77.48 |  |  | 1.01 |  | MWD |  | TOTAL | 107
DAILY WELL COST (US$) |  | 61374.6062 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 3887 / 3822.8 |  | 42.99 |  | 77.94 |  |  | 1.87 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 14958496.6615 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 3918 / 3845.5 |  | 42.98 |  | 78.63 |  |  | 0.46 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 82.88% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER |  |  |  | 3946 / 3865.9 |  | 43.8 |  | 79.28 |  |  | 1 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-07-16 | 2018-07-31 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 3892 |  | 390/380 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 3892 |  | 550/550 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 3892 |  | 760/750 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-07-19 | 2018-08-18 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-08 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-08-22 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-09
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43321 | 43321.0729 | 1.75 | DRL | PT-UP | RW | HARD REAMED FROM 3864M TO BTM @ 3878M, RECORDED MWD SURVEY & DOWNLINKED XCEED RSS. MEANWHILE INCREASING MWT.
43321.0729 | 43321.3021 | 5.5 | DRL | PT-UP | DM | TAGGED BTM & DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 3878M TO 3905M. MEANWHILE INCREASED MWT TO 1.68 SG.
43321.3021 | 43321.3438 | 1 | DRL | NPT-UP | STK | WHILE REAMING DOWN PRIOR CONNECTION OBSERVED HIGH ERRATIC TORQUE FROM 3880M - 3885M, ROTARY STALLED & STRING STUCK @ 3882M - UNABLE TO ROTATE & RECIPROCATE STRING. WORKED SEVERAL TIMES & RELEASED STRING WITH 75 TON OVERPULL. REAMED/BACK REAMED TO CLEAR TIGHT HOLE & RECORDED MWD SURVEY.
43321.3438 | 43322 | 15.75 | DRL | PT-UP | DM | DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 3905M TO 3956M. REAMED DRILLED SECTION & RECORDED MWD SURVEY PRIOR CONNECTION.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-10
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43322 | 43322.25 | 6 | DRL | PT-UP | DM | DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 3956M TO 3973M. REAMED DRILLED SECTION & RECORDED MWD SURVEY PRIOR CONNECTION.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / SANDSTONE, CLAYSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2" DIRECTIONAL HOLE
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | HARD REAMED FROM 3864M TO BTM @ 3878M. DRILLED 8 1/2" DIRECTIONAL HOLE FROM 3878M TO 3905M. MEANWHILE INCREASED MWT TO 1.68 SG. OBSERVED STRING STUCK @ 3882M WHILE REAMING PRIOR CONNECTION, WORKED & RELEASED STRING. DRILLED AHEAD 8 1/2" DIRECTIONAL HOLE FROM 3905M TO 3956M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" DIRECTIONAL HOLE AS PER PLAN.
REMARKS
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14