## DDR#234
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 234
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-12
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | RAHAT SHAKOOR RAO / M. AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 4002 / 3905.6 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 17.13
RIG REP. (TP): |  | TARIQ. M. BUTT / KHALID GILANI |  |  | MD/TVD @ 06:00HRS: |  | 4002 / 3905.6 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-08-11 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  |  |  | BIT NO. |  | 13RR2 |  | BHA No. |  |  | 34 | IN (M) |  | 4002 |  | OUT (M) |  |  | STRING (BBL) | 212
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  |  |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 620
DEPTH, MD (M) |  | 4002 | TVD @ 00:00HR (M) |  |  |  | MANUFACTURER |  | SMITH |  | PDC BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.26 | 0.035609 |  | PITS (BBL) | 769
MW IN (SG) |  | 1.68 | DAILY PROGRESS (M) |  |  |  | TYPE |  | MDSi616LBPX |  | GT MUD MOTOR |  |  | 6.625 | - |  | 4 1/2 IF |  | 9.55 | 1.3079 |  | ACT. SYS (BBL) | 1601
MW OUT (SG) |  | 1.68 | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN5340 |  | FLOAT SUB |  |  | 6.75 | 2.9375 |  | 4 1/2 IF |  | 0.77 | 0.10546 |  | RESV. SYS (BBL) | 586
ECD (SG) |  | 1.76 | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 323 |  | STRING STAB |  |  | 8.375 | 3.0625 |  | 4 1/2 IF |  | 1.41 | 0.19311 |  | KILL MUD (BBL) | 750
FL TEMP. °F |  | 148 | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3x13 + 3x14 |  | LOWER SAVER SUB |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4002 |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.45 | 1.2942 |  | TOTAL | 2937
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.34 | 1.2792 |  | DIESEL (LTR)
YIELD POINT |  | 30 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  |  |  | 3 X 6 1/2" DCS |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 27.76 | 3.8019 |  | RIG TANK | 125000
GEL ST. |  | 10/26 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 18 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 168.24 | 12.5226 |  | CAMP TANK | 29100
WL (ml/30 min.) |  | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | DRILLING JAR |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 5.78 | 0.79161 |  | CONSUMED | 7650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.08 | 4.1742 |  | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 154100
ALK (FILT.) |  | 0.3 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 161380
KCl (mg/l) |  | 61967.8 | JAR | 2.25 | STAB - 1 | 2.25 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 161380
CHLORIDES |  | 28500 | 5" HWDPS | 163.95 | STAB - 2 |  | TFA (IN²) |  | 0.8397 | [12 empty] | TOTAL | 400000
CALCIUM |  | 180 | 6 1/2" DCS | 163.95 | NMDC | 155.99 | HSI | [14 empty] | POB
OIL % |  | 4.5 | MUD MOTOR | 2.25 | SPSA | 155.99 | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 289.24 |  |  | MPCL | 5
LUBE % |  | 2 | BHA ROT. HRS |  | 163.95 |  | BIT NO. 13RR1 |  | 1-1-WT-A-X-I-NO-BHA |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 17
SOLIDS % |  | 24.83 | ON BOTTOM HRS |  | 206.4 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 3.61 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 55
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 3887 / 3822.8 |  | 42.99 |  | 77.94 |  |  | 1.87 |  | MWD |  | TOTAL | 114
DAILY WELL COST (US$) |  | 46425.504 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 3918 / 3845.5 |  | 42.98 |  | 78.63 |  |  | 0.46 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15069659.4753 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 3946 / 3865.9 |  | 43.8 |  | 79.28 |  |  | 1 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 83.49% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER |  |  |  | 3974 / 3885.9 |  | 44.99 |  | 80.94 |  |  | 1.78 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P2/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-07-16 | 2018-07-31 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 | [7 empty] | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-07-19 | 2018-08-18 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-08 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-08-22 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-11
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43323 | 43323.0521 | 1.25 | DRL | PT-UP | POOH | POOH BIT FROM 3700M TO 3307M (INSIDE 9 5/8" CASING WINDOW) ON ELEVATORS.
43323.0521 | 43323.0625 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - LEVEL STATIC.
43323.0625 | 43323.3229 | 6.25 | DRL | PT-UP | POOH | POOH FROM 3307M TO TOP OF BHA @ 295M.
43323.3229 | 43323.3333 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED - LEVEL STATIC.
43323.3333 | 43323.4167 | 2 | DRL | PT-UP | BHA | POOH BHA FROM 295M TO SURFACE. WHILE POOH L/DOWN JAR + MWD TOOL + XCEED RSS + BIT.
43323.4167 | 43323.4479 | 0.75 | DRL | PT-UP | BHA | P/UP & M/UP SAME 8 1/2" PDC BIT (13RR2) WITH MUD MOTOR DIRECTIONAL BHA. ADJUSTED MUD MOTOR BEND TO 1.5 DEG & RIH BHA TO 31M.
43323.4479 | 43323.4583 | 0.25 | DRL | PT-UP | E/C | SHALLOW FUNCTION TESTED MUD MOTOR & MWD TOOL, FOUND OK. RECORDED 750 PSI @ 350 GPM.
43323.4583 | 43323.5104 | 1.25 | DRL | PT-UP | BHA | RIH MUD MOTOR DIRECTIONAL BHA FROM 31M TO 289M.
43323.5104 | 43323.8542 | 8.25 | DRL | PT-UP | RIH | RIH BHA FROM 289M TO 3746M & OBSERVED OBSTRUCTION. WHILE RIH FILLED UP STRING WITH MUD.
43323.8542 | 43324 | 3.5 | DRL | PT-UP | RW | ATTEMPTED TO CLEAR OBSTRUCTION @ 3746M WITH WASHING DOWN, NO SUCCESS. REAMED DOWN FROM 3746M TO 3870M & HARD REAMED FROM 3870M TO 3906M. OBSERVED HIGH ERRATIC TORQUE, FREQUENT ROTARY STALLING & FORMATION CUTTINGS ON SHAKERS WHILE REAMING DOWN.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-12
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43324 | 43324.2396 | 5.75 | DRL | PT-UP | RW | CONT'D HARD REAMED FROM 3906M TO BTM @ 4002M. OBSERVED HIGH ERRATIC TORQUE, FREQUENT ROTARY STALLING & FORMATION CUTTINGS ON SHAKERS WHILE REAMING DOWN.
43324.2396 | 43324.25 | 0.25 | DRL | PT-UP | CIR | PUMPED & DISPLACING 20 BBL HI-VIS PILL OUT OF STRING PRIOR DRILLING AHEAD.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / SANDSTONE, CLAYSTONE & SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH BIT FROM 3700M TO SURFACE & L/DOWN SLB XCEED RSS. M/UP & RIH SAME 8 1/2" PDC BIT (13RR2) WITH MUD MOTOR DIRECTIONAL BHA & OBSERVED OBSTRUCTION @ 3746M. REAMED DOWN FROM 3746M TO 3870M & HARD REAMED FROM 3870M TO 3906M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2" DIRECTIONAL HOLE IN ROTARY & SLIDE MODES.
REMARKS
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14