## DDR#236
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 236
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-12-26
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 235.9792
RIG REP.: |  | TARIQ BUTT / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-12-25 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 4:00 | 20:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1162
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | REAMER SHOE |  |  | 7 | 6.094 |  | VAMTOP |  | 0.9 |  |  | PITS (BBL) | 560
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | 1ST LINER JT |  |  | 7 | 6.094 |  | VAMTOP |  | 12.434 |  |  | ACT. SYS (BBL) | 1722
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | 2ND LINER JT |  |  | 7 | 6.094 |  | VAMTOP |  | 12.479 |  |  | RESV. SYS (BBL) | 250
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | FLOAT COLLAR |  |  | 7 | 6.094 |  | VAMTOP |  | 0.8 |  |  | KILL MUD (BBL) | 660
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 3RD LINER JT |  |  | 7 | 6.094 |  | VAMTOP |  | 12.33 |  |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 57 | 60 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | LANDING COLLAR |  |  | 7 | 6.094 |  | VAMTOP |  | 0.61 |  |  | TOTAL | 1972
PV | 44 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 37 X LINER JTS |  |  | 7 | 6.094 |  | VAMTOP |  | 452 |  |  | DIESEL (LTR)
YIELD POINT | 27 | 26 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 118993
GEL ST. | 9/12 | 9/13 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 17751
WL (ml/30 min) | 3 | 3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5739
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 136744
ALK (FILT.) | 0.4/1.2 | 0.4/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 698872
MAX SHIELD % | 3 | 3 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 87000
KCl (%) | 6 | 6 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 51518
KCl (mg/l) | 61014.4 | 61014.4 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 63000
CHLORIDES (mg/l) | 33500 | 33500 | 5" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS |  | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 491.553 |  |  | MPCL | 4
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 21
SOLIDS % | 40.33 | 40.33 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 14 RR7 |  |  | 4-2-BT-N-X-I-WT-TD |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 31652 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17242979 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 86.62% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-12-12 | 2020-01-11 | LAST BOP TEST DATE |  | 2019-12-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-12-13 | 2020-01-12 | NEXT BOP TEST DATE |  | 2020-01-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43824 | 43824.0417 | 1 | LINER | PT-P | RIH | RIH FROM 4133M TO 4549M.
43824.0417 | 43824.0521 | 0.25 | LINER | PT-P | CIR | BROKE CIRCULATION.
43824.0521 | 43824.125 | 1.75 | LINER | PT-P | RIH | CONT'D RIH FROM 4133M TO 4997M. PRECAUTIONARY WASHED DOWN LAST STAND.
43824.125 | 43824.2188 | 2.25 | LINER | PT-P | CIR | SWEPT OUT 25 BBL HI-VIS PILL. KEPT CIRCULATING TO CONDITION MUD.
43824.2188 | 43824.25 | 0.75 | LINER | PT-P | SP | SPOTTED 50 BBL HI-VIS PILL.
43824.25 | 43824.2812 | 0.75 | LINER | PT-P | POOH | POOH FROM 4997M TO 4847M.
43824.2812 | 43824.3542 | 1.75 | LINER | PT-P | POOH / CIR | PUMPED OUT FROM 4847M TO 4532M (INSIDE CSG).
43824.3542 | 43824.3646 | 0.25 | LINER | PT-P | FC | FLOW CHECKED- WELL STATIC.
43824.3646 | 43824.7292 | 8.75 | LINER | PT-P | POOH | POOH FROM 4532M TO 191M (TOP OF BHA).
43824.7292 | 43824.7396 | 0.25 | LINER | PT-P | FC | FLOW CHECKED- WELL STATIC.
43824.7396 | 43824.7917 | 1.25 | LINER | PT-P | BHA | POOH FROM 191M TO SURFACE. L/DOWN D. JAR, STABS & BIT.
43824.7917 | 43824.8229 | 0.75 | LINER | PT-P | RU | PREPARED RIG FLOOR. R/UP W.FORD TRS GEARS FOR 7'' LINER JOB
43824.8229 | 43824.8438 | 0.5 | LINER | PT-P | SM | HELD PJSM, DISCUSSED SAFETY CONCERNS PRIOR 7'' LINER JOB.
43824.8438 | 43825 | 3.75 | LINER | PT-P | RC | P/UP AND M/UP 7'' LINER SHOE TRACK (R/SHOE + 1ST JT + 2ND JT + F/COLLAR + 3RD JT + L/COLLAR = 39M, SPECS : 7'' X 32 # , VT ). CHECKED AND ENSURED INTEGRITY OF FLOATS, OK. CONT'D P/UP, M/UP AND RIH 7'' LINER FROM 39M TO 209M (17 JTS). FILLED UP EVERY JOINT. INSTALLED CENTRALIZERS AS PER PROGRAM.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43825 | 43825.1458 | 3.5 | LINER | PT-P | RC | CONT'D RIH 7'' LINER FROM 209M TO 491M (40 JTS).
43825.1458 | 43825.1667 | 0.5 | LINER | PT-P | CIR | CIRCULATED 1.5 TIMES LINER CAPACITY.
43825.1667 | 43825.25 | 2 | LINER | PT-P | RC | INSPECTED & INSTALLED 7'' LINER HANGER ASSEMBLY. CIRCULATED MEANWHILE FILLED UP PBR WITH HI-VIS GEL.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | 7'' LINER JOB IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH TO 4997M, CIRCULATED TO CONDITION MUD, SPOTTED 50 BBL HI-VIS AND POOH TO SURFACE, L/DOWN JAR, STABS AND BIT, R/UP W.FORD TRS, HELD PJSM, 7'' LINER JOB IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | 7'' LINER JOB & CEMENT JOB.
REMARKS |  |  | WASH PIPE ROTATING HRS = 118.14 HRS ; CIRC HRS = 207.22 HRS @ 0:00 HRS.
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14