## DDR#237
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 237
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-12-27
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HAMZA / TALHA |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 236.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-12-26 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  |  |  | BHA NO. |  |  |  | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 12:00 | 11:59 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  |  |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1054.5
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  |  |  | REAMER SHOE |  |  | 7 | 6.094 |  | VAMTOP |  | 0.9 |  |  | PITS (BBL) | 706
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  |  |  | 1ST LINER JT |  |  | 7 | 6.094 |  | VAMTOP |  | 12.434 |  |  | ACT. SYS (BBL) | 1760.5
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  |  |  | 2ND LINER JT |  |  | 7 | 6.094 |  | VAMTOP |  | 12.479 |  |  | RESV. SYS (BBL) | 252
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  |  |  | FLOAT COLLAR |  |  | 7 | 6.094 |  | VAMTOP |  | 0.8 |  |  | KILL MUD (BBL) | 660
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 3RD LINER JT |  |  | 7 | 6.094 |  | VAMTOP |  | 12.33 |  |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 64 | 57 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  |  |  | LANDING COLLAR |  |  | 7 | 6.094 |  | VAMTOP |  | 0.61 |  |  | TOTAL | 2012.5
PV | 43 | 41 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 37 X LINER JTS |  |  | 7 | 6.094 |  | VAMTOP |  | 452 |  |  | DIESEL (LTR)
YIELD POINT | 25 | 22 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 115688
GEL ST. | 9/13 | 7/9 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 17196
WL (ml/30 min) | 3 | 3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 3860
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 132884
ALK (FILT.) | 0.4/1.2 | 0.4/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 757744
MAX SHIELD % | 3 | 3 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) | 6 | 6 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 42628
KCl (mg/l) | 61014.4 | 61014.4 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 94500
CHLORIDES (mg/l) | 33500 | 33000 | 5" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS |  | STAB - 3 |  | TFA (IN²) | [15 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 491.553 |  |  | MPCL | 4
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 22
SOLIDS % | 40.33 | 40.34 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 54
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 109
DAILY WELL COST (US$) |  | 36415 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17279394 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 86.8% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-12-12 | 2020-01-11 | LAST BOP TEST DATE |  | 2019-12-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-12-13 | 2020-01-12 | NEXT BOP TEST DATE |  | 2020-01-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-26
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43825 | 43825.1458 | 3.5 | DRL | PT-P | RC | CONT'D RIH 7'' LINER FROM 209M TO 491M (40 JTS).
43825.1458 | 43825.1667 | 0.5 | DRL | PT-P | CIR | CIRCULATED 1.5 TIMES LINER CAPACITY.
43825.1667 | 43825.25 | 2 | DRL | PT-P | RC | INSPECTED & INSTALLED 7'' LINER HANGER ASSEMBLY AND RIH DOWN TO 501M . CIRCULATED MEANWHILE FILLED UP PBR WITH HI-VIS GEL.
43825.25 | 43825.6146 | 8.75 | DRL | PT-P | RC | CONT'D RIH 7'' LINER ON 5" DPS FROM 501M TO 3153M. FILLED STRING AFTER EVERY 15 STANDS.
43825.6146 | 43825.6458 | 0.75 | DRL | PT-P | CIR | BROKE CIRCULATION.
43825.6458 | 43825.8333 | 4.5 | DRL | PT-P | RIH/RC | CONT'D RIH 7'' LINER ON 5" DPS FROM 3153M TO 4529M.
43825.8333 | 43825.8542 | 0.5 | DRL | PT-P | CIR | BROKE CIRCULATION. MEANWHILE RECORDED WEIGHTS.
43825.8542 | 43825.9375 | 2 | DRL | PT-P | RC | CONT'D RIH 7'' LINER ON 5'' DP's FROM 4529M TO 4958M.
43825.9375 | 43825.9688 | 0.75 | DRL | PT-P | WD | PRECAUTIONARY WASHED DOWN FROM 4958M TO TAG BTM AT 4997M.
43825.9688 | 43826 | 0.75 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43826 | 43826.0208 | 0.5 | DRL | PT-P | RU | P/UP AND M/UP CMT HEAD PRE LOADED WITH DP DART.
43826.0208 | 43826.0625 | 1 | DRL | PT-P | RC | DROPPED & CHASED BALL WITH MUD @ 2 BPM. OBSERVED SPP INCREASED FROM 300 PSI TO 1800 PSI. STOPPED PUMP. HELD SPP FOR 2 MINUTES. BLED OFF TO 500 PSI. SLACKED OFF STRING. OBSERVED LINER HANGER SLIPS BITE & HOLDING. APPLIED LINER WEIGHT + 17 TON WEIGHT ON SLIPS FOR 5 MINS. FOUND LINER HANGER SLIPS HOLDING. INCREASED SPP TO 2000 PSI TO RELEASE SETTING TOOL. HELD PRESSURE FOR 2 MINUTES THAN BLED OFF TO 'ZERO'. P/U STRING 2' TO CHECK TOOL RELEASED. OBSERVED FREE STRING MOVING. CONFIRMED SETTING TOOL RELEASED. SLACKED 15 TONS WEIGHT INCREASED SPP TO 3200 PSI GRADUALLY, OBSERVED SUDDEN PRESSURE DROPPED. BALL SEAT SHEARED, OK. RESUMED CIRCULATION.
43826.0625 | 43826.1771 | 2.75 | DRL | PT-P | CIR | CIRCULATED TO CONDITION MUD. MEANWHILE STARTED PREPARING MIX FLUID. H/UP DOWEL CMT.
43826.1771 | 43826.2188 | 1 | DRL | PT-P | SM/ P/T | HELD PJSM, CLOSED LO-TORQUE VALVE. PRESSURE TESTED DOWEL LINES AT 500/5000 PSI. OBSERVED LEAKAGE AT 5000 PSI. BLED OFF PRESSURE.
43826.2188 | 43826.25 | 0.75 | DRL | PT-P | CIR | RESUMED CIRCULATION TO CONDITION MUD MEANWHILE ADDING RETARDER IN MIXED FLUID & FIXING DOWEL CMT LINES FOR P/TEST.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | CIRCULATION TO CONDITION MUD MEANWHILE PREPARING FOR CMT JOB
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH 7" LINER TO 491M, M/U LINER HANGER ASSEMBLY. CONT'D RIH ON DPS DOWN TO 3153M. BROKE CIRCULATION. RIH DOWN TO 4997M. CIRCULATED TO CONDITION MUD.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | SET LINER HANGER. PERFORM CEMENT JOB. POOH TO 4300M. CIRCULATE TO CLEAN HOLE. POOH TO SURFACE. RIH 8-1/2" BIT DOWN TO TOL.
REMARKS |  |  | WASH PIPE ROTATING HRS = 118.14 HRS ; CIRC HRS = 211.22 HRS @ 0:00 HRS.
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14