## DDR#238
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 238
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-12-28
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 237.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-12-27 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 43 |  | BHA NO. |  |  | 56 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL)
CHECK TIME | 6:00 | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 14RR8 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1102
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 8.5 |  | PDC BIT |  |  | 8.5 |  |  | 4 1/2 REG |  | 0.26 | 0.034184 |  | PITS (BBL) | 580
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 1.06 | 0.13937 |  | ACT. SYS (BBL) | 1682
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSi616 |  | 9 X DC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 83.35 | 10.9587 |  | RESV. SYS (BBL) | 203
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JN5340 |  | 9 X HWDP |  |  | 5 | 3 |  | 4 1/2 IF |  | 84.15 | 6.1545 |  | KILL MUD (BBL) | 660
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE | [15 empty] | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 54 | 64 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 6 X 18/32 | [12 empty] | TOTAL | 1885
PV | 41 | 42 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT | 22 | 24 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 109961
GEL ST. | 9/13 | 11/15 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 16562
WL (ml/30 min) | 3 | 3 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 6361
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) | 0.5 | 0.5 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 126523
ALK (FILT.) | 0.4/1.2 | 0.5/1.2 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 735808
MAX SHIELD % | 3 | 3 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 87000
KCl (%) | 6 | 6 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 67436
KCl (mg/l) | 61014.4 | 61014.4 | JAR |  | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 52500
CHLORIDES (mg/l) | 33500 | 33000 | 5" HWDPS |  | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 300 | 300 | 6 1/2" DCS |  | STAB - 3 |  | TFA (IN²) |  |  | 1.49 | [12 empty] | POB
PENETREX % | 2 | 2 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 168.82 |  |  | MPCL | 2
MAX GUARD % | 2 | 2 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 13 |  |  | MPCL SERV | 17
SOLIDS % | 40.34 | 40.34 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS | [8 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 52
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 102
DAILY WELL COST (US$) |  | 31146 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17310540 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 86.96% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-12-12 | 2020-01-11 | LAST BOP TEST DATE |  | 2019-12-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-12-13 | 2020-01-12 | NEXT BOP TEST DATE |  | 2020-01-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-27
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43826 | 43826.0208 | 0.5 | LINER | PT-P | RU | P/UP AND M/UP CMT HEAD PRE LOADED WITH DP DART.
43826.0208 | 43826.0625 | 1 | LINER | PT-P | RC | DROPPED & CHASED BALL WITH MUD @ 2 BPM. OBSERVED SPP INCREASED FROM 300 PSI TO 1800 PSI. STOPPED PUMP. HELD SPP FOR 2 MINUTES. BLED OFF TO 500 PSI. SLACKED OFF STRING. OBSERVED LINER HANGER SLIPS BITE & HOLDING. APPLIED LINER WEIGHT + 17 TON WEIGHT ON SLIPS FOR 5 MINS. FOUND LINER HANGER SLIPS HOLDING. INCREASED SPP TO 2000 PSI TO RELEASE SETTING TOOL. HELD PRESSURE FOR 2 MINUTES THAN BLED OFF TO 'ZERO'. P/U STRING 2' TO CHECK TOOL RELEASED. OBSERVED FREE STRING MOVING. CONFIRMED SETTING TOOL RELEASED. SLACKED 15 TONS WEIGHT INCREASED SPP TO 3200 PSI GRADUALLY, OBSERVED SUDDEN PRESSURE DROPPED. BALL SEAT SHEARED, OK. RESUMED CIRCULATION.
43826.0625 | 43826.1771 | 2.75 | LINER | PT-P | CIR | CIRCULATED TO CONDITION MUD. MEANWHILE STARTED PREPARING MIX FLUID. H/UP DOWEL CMT.
43826.1771 | 43826.2188 | 1 | LINER | PT-P | SM/ P/T | HELD PJSM, CLOSED LO-TORQUE VALVE. PRESSURE TESTED DOWEL LINES AT 500/5000 PSI. OBSERVED LEAKAGE AT 5000 PSI. BLED OFF PRESSURE.
43826.2188 | 43826.2604 | 1 | LINER | PT-P | CIR | RESUMED CIRCULATION TO CONDITION MUD MEANWHILE ADDING RETARDER IN MIXED FLUID & FIXING DOWEL CMT LINES FOR P/TEST.
43826.2604 | 43826.2812 | 0.5 | LINER | PT-P | P/T | CLOSED LO-TORQUE VALVE, P/TESTED DOWEL CMT LINES AT 500/4800 PSI. HELD FOR 10 MINS, OK.
43826.2812 | 43826.3333 | 1.25 | LINER | PT-P | CIR | CIRCULATED TO CONDITION MUD. MEANWHILE ADDED RETARDER IN MIX FLUID & WEIGHTED UP CMT SLURRY.
43826.3333 | 43826.4479 | 2.75 | LINER | PT-P | CMC | PERFORMED 7'' LINER CMT JOB AS FOLLOWS: PUMPED 70 BBL SPACER (16.4 PPG) FROM RIG PUMP. SWITCHED OVER TO DOWEL UNIT, PUMPED 10 BBL SPACER FOLLOWED BY BATCH MIXED 110 BBL GasBLOK SLURRY (17.4 PPG) @ 4 BPM. ADDED CemNET AS PER PROGRAM. DROPPED DP DART, DISPLACEMENT WAS CARRIED OUT FROM DOWEL UNIT. OBSERVED WIPER PLUG PINS SHEARED AFTER DISPLACING 252.5 BBL AT 2600 PSI, DISPLACED LINER VOLUME = 54.5 BBLs TO BUMP PLUGS AT 1200 PSI, GRADUALLY INCREASED PRESSURE TO 2000 PSI, HELD FOR 5 MINS, OK. FURTHER INCREASED PRESSURE TO 4000 PSI FOR LINER TEST. HELD FOR 5 MINUTES, OK. BLED OFF PRESSURE, NO BACK FLOW OBSERVED. TOTAL DIPLACEMENT = 252.5 + 54.5 BBLs. LINER WAS ROTATED DURING DISPLACEMENT. NO LOSSES OBSERVED DURING CMT JOB.
43826.4479 | 43826.4688 | 0.5 | LINER | PT-P | RD | R/D AND L/D WF CMT HEAD. SET 7" LINER TOP PKR WITH BOTH SHEAR INDICATION 15 T / 25 T COMPRESSION.
43826.4688 | 43826.4896 | 0.5 | LINER | PT-P | POOH | POOH FROM 4996M TO 4350M.
43826.4896 | 43826.5729 | 2 | LINER | PT-P | CIR | DIRECT CIRCULATED TO CONDITION MUD, DUMPED 120 BBL CMT/SPACER CONTAMINATION.
43826.5729 | 43826.9479 | 9 | LINER | PT-P | POOH | CONT'D POOH FROM 4350 TO SURFACE. L/DOWN WF LINER HANGER SETTING TOOL.
43826.9479 | 43827 | 1.25 | LINER | PT-P | BHA | P/UP AND M/UP USED 8 1/2'' PDC BIT + BIT SUB. RIH AS PER BHA TO 168M. FLUSHED BHA.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43827 | 43827.25 | 6 | LINER | PT-P | RIH | RIH FROM 168M TO 3137M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | RIH WITH 8 1/2'' BIT IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | SET LINER HANGER. PERFORMED CEMENT JOB AS PER PROGRAM. POOH TO 4350M. CIRCULATED TOCONDITION MUD. POOH TO SURFACE. B/OUT AND L/DOWN LH SETTING TOOL. P/UP AND M/UP 8 1/2'' PDC BIT + BIT SUB, RIH AS PER BHA TO 168M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | RIH WITH 8 1/2'' BIT TO TAG TOL AT +/- 4495M, CIRCULATE TO CONDITION MUD, POOH TO SURFACE, L/DOWN 8 1/2'' BIT, CLEAN OUT TRIP WITH 6'' BIT.
REMARKS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14