## DDR#240
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 240
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-12-30
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK/ HAMZA MEHMOOD |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 239.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-12-29 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 44 |  | BHA NO. |  |  | 57 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 250
CHECK TIME |  | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 20 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 760.5
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.013874 |  | PITS (BBL) | 770
MW IN (SG) |  | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB (F.V) |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.074227 |  | ACT. SYS (BBL) | 1780.5
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSI613 |  | 15 X DC's |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 137.35 | 9.5282 |  | RESV. SYS (BBL) | 489
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JP2216 |  | D.JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.21 | 0.63891 |  | KILL MUD (BBL) | 340
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 3 X DC's |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 27.29 | 1.8931 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) |  | 73 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3X12 |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.8 | 6.3876 |  | TOTAL | 2269.5
PV |  | 45 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) | [15 empty] | DIESEL (LTR)
YIELD POINT |  | 30 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 99504
GEL ST. |  | 12/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 15455
WL (ml/30 min) |  | 4.2 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5881
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED
ALK (MUD) |  | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 114959
ALK (FILT.) |  | 0.5/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH |  | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 771804
MAX SHIELD % |  | 2.5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 88000
KCl (%) |  | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 46858
KCl (mg/l) |  | 59107.7 | JAR | 0.6 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 118700
CHLORIDES (mg/l) |  | 32000 | 3.5" HWDPS | 0.6 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 19000
HARDNESS (mg/l) |  | 360 | 4.75" DCS | 0.6 | STAB - 3 |  | TFA (IN²) |  |  | 0.331 | [12 empty] | POB
PENETREX % |  | 1.5 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 344.92 |  |  | MPCL | 4
MAX GUARD % |  | 1.5 | DAILY BHA ROT. HRS |  | 0.6 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 13 |  |  | MPCL SERV | 23
SOLIDS % |  | 40.38 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 14RR8 |  |  | 4-2-BT-N-X-I-WT-TD |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 8 |  |  | SECURITY
M.B.T. (lb/bbl) |  | 5 | DAILY CIRC. HRS |  | 2.4 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 30583 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17601979 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 88.43% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-12-12 | 2020-01-11 | LAST BOP TEST DATE |  | 2019-12-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-12-13 | 2020-01-12 | NEXT BOP TEST DATE |  | 2020-01-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43828 | 43828.1146 | 2.75 | LINER | PT-P | POOH | POOH FROM 2165M TO 830M.
43828.1146 | 43828.3646 | 6 | LINER | PT-P | DP | POOH FROM 830M TO SURFACE, L/DOWN 23 STANDS OF 5''- G-105 DP's + 3 STANDS OF 6.5" DCs & 3 STANDS OF 5" HWDPS SGL BY SGL DURING POOH.
43828.3646 | 43828.5625 | 4.75 | LINER | PT-P | BHA/ DP | PJSM. M/UP NEW 6" PDC BIT ON SLIM HOLE STRING & RIH DOWN TO 545 M. P/UP 18X4.75" DCs+18X3.5" HWDPs & 18X 3.5" DPs DURING RIH.
43828.5625 | 43828.5729 | 0.25 | LINER | PT-P | CIR | FLUSHED BHA.
43828.5729 | 43828.9479 | 9 | LINER | PT-P | RIH | RIH SLIM STRING ON 5" DP's DOWN TO 4484M. FILLED STRING AFTER EVERY 20 STANDS.
43828.9479 | 43828.9896 | 1 | LINER | PT-P | RW | WASHED DOWN FROM 4484M TO 4512M. WHILE WASHING DOWN OBSERVED OBSTRUCTION AT 4496M (TOL). CLEANED OUT AND CLEARED FROM 4496M TO 4501M.
43828.9896 | 43829 | 0.25 | LINER | PT-P | RIH | CONT'D RIH FROM 4512M TO 4540M. OBSERVED OBSTRUCTION AT 4540M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43829 | 43829.1771 | 4.25 | LINER | PT-P | RW | CLEANED OUT 7'' LINER FROM 4540M TO TAG TOP OF PLUGS/L.COLLAR AT 4957.5M.
43829.1771 | 43829.25 | 1.75 | LINER | PT-P | DFS | CLEANED OUT PLUGS /L.COLLAR FROM 4957.5M TO 4958.5M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | CLEANING OUT PLUGS/L.COLLAR IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH TO SURFACE, L/DOWN ADDITIONAL 5'' DP's STDS, ALL BHA COMPONENTS, P/UP AND M/UP 6'' PDC BIT & SLIM BHA FOR CLEAN OUT TRIP. RIH TO 4540M. CLEANED OUT ACROSS TOL.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE RIH FROM 4540M TO TAG TOP OF PLUGS / L/COLLAR AT +/- 4956M, CLEAN OUT PLUGS / FLOATS / CMT DOWN TO +/- 4993M, CIRCULATION TO CLEAN HOLE, POOH TO SURFACE, SCRAPER TRIP.
REMARKS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14