## DDR#241
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 241
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-12-31
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK/ HAMZA MEHMOOD |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 240.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-12-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 45 |  | BHA NO. |  |  | 58 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 60
CHECK TIME | 2:00 | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 20RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 1015.4
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.013874 |  | PITS (BBL) | 732
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | 7'' SCRAPER |  |  | 5.875 | 1.5625 |  | 3 1/2 REG |  | 1.01 | 0.070065 |  | ACT. SYS (BBL) | 1807.4
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSI613 |  | BIT SUB (F.V) |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.074227 |  | RESV. SYS (BBL) | 452
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JP2216 |  | 15 X DC's |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 137.35 | 9.5282 |  | KILL MUD (BBL) | 340
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | D.JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.21 | 0.63891 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 66 | 73 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3X12 |  | 3 X DC's |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 27.29 | 1.0266 |  | TOTAL | 2259.4
PV | 44 | 44 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.8 | 6.3876 |  | DIESEL (LTR)
YIELD POINT | 28 | 30 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 16 X DP's |  |  | 3.5 |  |  | 3 1/2 IF |  | 152.64 | 3.4698 |  | RIG TANK | 93167
GEL ST. | 10/14 | 11/16 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | X/O (P x P) |  |  | 6.4375 | 2.375 |  | 4 1/2 REG |  | 0.79 | 0.017958 |  | CAMP TANK | 14983
WL (ml/30 min) | 4 | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 9.625'' SCRAPER |  |  | 7.9375 | 2.25 |  | 4 1/2 REG |  | 1.23 | 0.02796 |  | CONSUMED | 6809
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | BIT SUB |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 1.06 | 0.024096 |  | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 108150
ALK (FILT.) | 0.5/1.3 | 0.5/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 627518
MAX SHIELD % | 2.5 | 2.5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 83000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 67346
KCl (mg/l) | 57201 | 57201 | JAR | 10.1 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 63800
CHLORIDES (mg/l) | 31500 | 31500 | 3.5" HWDPS | 10.1 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 39000
HARDNESS (mg/l) | 340 | 340 | 4.75" DCS | 10.1 | STAB - 3 |  | TFA (IN²) |  |  | 0.331 | [12 empty] | POB
PENETREX % | 1.5 | 1.5 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 501.65 |  |  | MPCL | 4
MAX GUARD % | 1.5 | 1.5 | DAILY BHA ROT. HRS |  | 9.5 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 23
SOLIDS % | 40.4 | 40.4 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 20 |  |  | 1-1-WT-A-X-I-NO-BHA |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 13.15 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 6
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 107
DAILY WELL COST (US$) |  | 34519 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17636499 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 88.6% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-12-12 | 2020-01-11 | LAST BOP TEST DATE |  | 2019-12-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-12-13 | 2020-01-12 | NEXT BOP TEST DATE |  | 2020-01-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43829 | 43829.1771 | 4.25 | LINER | PT-P | RW | CLEANED OUT 7'' LINER FROM 4540M TO TAG TOP OF PLUGS/L.COLLAR AT 4957.5M.
43829.1771 | 43829.5104 | 8 | LINER | PT-P | DFS / DC | DRILLED OUT PLUGS /L.COLLAR FROM 4957.5M TO 4958.5M. DRILLED CEMENT BELOW LANDING COLLAR. DRILLED OUT F.COLLAR @ 4971M. DRILLED CEMENT BELOW F.COLLAR DOWN TO 4993M.
43829.5104 | 43829.6146 | 2.5 | LINER | PT-P | CIR | PUMPED 25 BBLS HV PILL & CIRCULATED TILL SHAKERS CLEAN.
43829.6146 | 43829.625 | 0.25 | LINER | PT-P | FC | FLOW CHECKED. WELL STATIC.
43829.625 | 43829.8021 | 4.25 | LINER | PT-P | POOH | PUMPED SLUG. POOH FROM 4993M TO 3195M.
43829.8021 | 43829.8542 | 1.25 | LINER | PT-P | RS | SLIPPED AND CUT 35M D.LINE. ADJUSTED CROWN-O-MATIC & ACS.
43829.8542 | 43830 | 3.5 | LINER | PT-P | POOH | POOH FROM 3195M TO 1553M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43830 | 43830.0938 | 2.25 | LINER | PT-P | POOH | CONT'D POOH FROM 1553M TO 546M (TOP OF 3 1/2'' DP's).
43830.0938 | 43830.1042 | 0.25 | LINER | PT-P | FC | FLOW CHECKED - WELL STATIC.
43830.1042 | 43830.1979 | 2.25 | LINER | PT-P | POOH / BHA | POOH FROM 546M TO SURFACE. RACKED BACK BHA. B/OUT AND EVALUATED BIT CONDITION, OK.
43830.1979 | 43830.25 | 1.25 | LINER | PT-P | BHA | P/UP AND M/UP USED 6'' PDC BIT + 7'' CSG SCRAPER. RIH AS PER BHA TO 157M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | RIH WITH 7' SCRAPER IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D RIH FROM 4540M TO TAG TOP OF PLUGS / L/COLLAR AT 4957.5 M, DRILLED OUT F. COLLAR (4971M) / CMT DOWN TO 4993M, CIRCULATION TO CLEAN HOLE, POOH TO 1553M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH TO SURFACE, 7'' X 9.625'' SCRAPER TRIP, W/LINE LOGGING.
REMARKS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14