## DDR#242
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 242
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 01/01/2020 0:00
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK/ HAMZA MEHMOOD |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 241.9792
RIG REP.: |  | JAVED MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | -
2019-12-31 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 45 |  | BHA NO. |  |  | 58 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 265
CHECK TIME | 11:00 | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 20RR |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 741.3
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.013874 |  | PITS (BBL) | 789
MW IN (SG) | 1.85 | 1.85 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | 7'' SCRAPER |  |  | 5.875 | 1.5625 |  | 3 1/2 REG |  | 1.01 | 0.070065 |  | ACT. SYS (BBL) | 1795.3
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSI613 |  | BIT SUB (F.V) |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.074227 |  | RESV. SYS (BBL) | 452
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JP2216 |  | 15 X DC's |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 137.35 | 9.5282 |  | KILL MUD (BBL) | 340
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | D.JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.21 | 0.63891 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 75 | 70 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3X12 |  | 3 X DC's |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 27.29 | 1.0266 |  | TOTAL | 2247.3
PV | 44 | 43 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.8 | 6.3876 |  | DIESEL (LTR)
YIELD POINT | 29 | 28 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) |  |  |  |  | 16 X DP's |  |  | 3.5 |  |  | 3 1/2 IF |  | 152.64 | 3.4698 |  | RIG TANK | 89295
GEL ST. | 11/16 | 10/14 | PRESSURE (PSI) |  |  |  | METERAGE (M) |  |  |  |  | X/O (P x P) |  |  | 6.4375 | 2.375 |  | 4 1/2 REG |  | 0.79 | 0.017958 |  | CAMP TANK | 14434
WL (ml/30 min) | 4 | 4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. |  |  |  |  | 9.625'' SCRAPER |  |  | 7.9375 | 2.25 |  | 4 1/2 REG |  | 1.23 | 0.02796 |  | CONSUMED | 4421
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  |  | BIT SUB |  |  | 6.5 | 3 |  | 4 1/2 IF |  | 1.06 | 0.024096 |  | RECEIVED
ALK (MUD) | 0.6 | 0.6 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 103729
ALK (FILT.) | 0.5/1.3 | 0.5/1.3 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 10 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 619125
MAX SHIELD % | 2.5 | 2.5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 80000
KCl (%) | 5.5 | 5.5 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 58827
KCl (mg/l) | 57201 | 57201 | JAR | 10.1 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 96900
CHLORIDES (mg/l) | 31500 | 31500 | 3.5" HWDPS | 10.1 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE
HARDNESS (mg/l) | 360 | 360 | 4.75" DCS | 10.1 | STAB - 3 |  | TFA (IN²) |  |  | 0.331 | [12 empty] | POB
PENETREX % | 1.5 | 1.5 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 501.65 |  |  | MPCL | 4
MAX GUARD % | 1.5 | 1.5 | DAILY BHA ROT. HRS |  |  |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [7 empty] | 13 |  |  | MPCL SERV | 30
SOLIDS % | 40.4 | 40.4 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. 20RR |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [7 empty] | 8 |  |  | SECURITY
M.B.T. (lb/bbl) | 5 | 5 | DAILY CIRC. HRS |  | 5.21 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 114
DAILY WELL COST (US$) |  | 30670 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17667169 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 88.75% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW) | 2
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI) | 968.937
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-12-12 | 2020-01-11 | LAST BOP TEST DATE |  | 2019-12-24 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-12-13 | 2020-01-12 | NEXT BOP TEST DATE |  | 2020-01-07 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-12-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43830 | 43830.0938 | 2.25 | LINER | PT-P | POOH | CONT'D POOH FROM 1553M TO 546M (TOP OF 3 1/2'' DP's).
43830.0938 | 43830.1042 | 0.25 | LINER | PT-P | FC | FLOW CHECKED - WELL STATIC.
43830.1042 | 43830.1979 | 2.25 | LINER | PT-P | POOH / BHA | POOH FROM 546M TO SURFACE. RACKED BACK BHA. B/OUT AND EVALUATED BIT CONDITION, OK.
43830.1979 | 43830.3125 | 2.75 | LINER | PT-P | BHA | P/UP AND M/UP USED 6'' PDC BIT + 7'' CSG SCRAPER. RIH AS PER BHA TO 501M. ADDED 9.625'' SCRAPER IN STRING.
43830.3125 | 43830.625 | 7.5 | LINER | PT-P | COC / RIH | CONT'D RIH FROM 501M TO 3695M. FILLED UP STRING AFTER EVRY 15 STDS.
43830.625 | 43830.6354 | 0.25 | LINER | PT-P | RS | SERVICED TDS
43830.6354 | 43830.7604 | 3 | LINER | PT-P | COC / RIH | CONT'D RIH FROM 3695M DOWN TO 4841M. FILLED UP STRING EVERY 15 STDS. CLEANED OUT ACROSS TOL = 4496M.
43830.7604 | 43830.8542 | 2.25 | LINER | PT-P | COC | WORKED ON SCRAPER WITH CIRCULATION FROM 4841M TO 4993M.
43830.8542 | 43830.9375 | 2 | LINER | PT-P | CIR / COC | CIRCULATED FOR BTM UP, KEPT CIRCULATING TILL SHAKERS CLEAN.
43830.9375 | 43830.9479 | 0.25 | LINER | PT-P | FC | FLOW CHECKED - WELL STATIC.
43830.9479 | 43831 | 1.25 | LINER | PT-P | POOH / COC | POOH FROM 4993M TO 4740M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-01
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43831 | 43831.25 | 6 | LINER | PT-P | POOH / COC | PUMPED SLUG. POOH FROM 4740M TO 2580M. WHILE POOH WORKED ON SCRAPER FROM 4612M TO 4496M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | POOH 7'' X 9.625'' SCRAPERS IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D POOH TO SURFACE, P/UP AND M/UP 6'' USED PDC BIT + 7'' SCRAPER, RIH 7 '' X 9.625'' SCRAPER TO 4993M, CIRCULATION TO CLEAN HOLE, POOH TO 4740M AND IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE POOH 7'' X 9.625'' SCRAPER ASSEMBLY, L/DOWN JAR, SCRAPERS + PDC BIT, PERFORM W/LINE LOGGING, CHANGE BOP RAM, BOPT, CONDITION TRIP.
REMARKS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14