## DDR#243
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 243
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-21
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4381 / 4183.19 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 26.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4381 / 4183.19 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 14
2018-08-20 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 13RR2 |  | BHA No. |  |  | 34 | IN (M) |  | 4002 |  | OUT (M) | 4381 |  | STRING (BBL)
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4381 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1015
DEPTH, MD (M) |  | 4381 | TVD @ 00:00HR (M) |  | 4183.19 |  | MANUFACTURER |  | SMITH | [12 empty] | PITS (BBL) | 724
MW IN (SG) |  | 1.68 | DAILY PROGRESS (M) |  | 14 |  | TYPE |  | MDSi616LBPX | [12 empty] | ACT. SYS (BBL) | 1739
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | JN5340 | [12 empty] | RESV. SYS (BBL) | 606
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | 323 | [12 empty] | KILL MUD (BBL) | 600
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 3x13 + 3x14 | [12 empty] | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 59 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4002 | [12 empty] | TOTAL | 2945
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  | 4381 | [12 empty] | DIESEL (LTR)
YIELD POINT |  | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 379 | [12 empty] | RIG TANK | 129000
GEL ST. |  | 12/29 | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 0 - 90 | [12 empty] | CAMP TANK | 23250
WL (ml/30 min.) |  | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 128 - 217 | [12 empty] | CONSUMED | 9650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 3 - 09 | [12 empty] | RECEIVED
ALK (MUD) |  | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  | 2.3942 | [12 empty] | TOTAL | 152250
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  | 158.3 | [12 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 77.62 | [12 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 1835.25 | [12 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 171740
KCl (mg/l) |  | 51194.9 | JAR |  | STAB - 1 |  | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 171740
CHLORIDES |  | 24000 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) |  | 0.8397 | [12 empty] | TOTAL | 400000
CALCIUM |  | 180 | 6 1/2" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5.5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [10 empty] | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  |  |  | BIT NO. 13RR2 |  | 2-2-WT-A-X-I-BT-BHA |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 14
SOLIDS % |  | 25.03 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 13
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4251 /4087.44 |  | 41.87 |  | 73.93 |  |  | 0.87 |  | MWD |  | TOTAL | 108
DAILY WELL COST (US$) |  | 41668 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4280 /4108.96 |  | 42.36 |  | 74.15 |  |  | 0.53 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15495951 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4306 /4128.08 |  | 42.94 |  | 74.76 |  |  | 0.82 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 85.85% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER |  |  |  | 4336 /4150.09 |  | 42.69 |  | 75.52 |  |  | 0.57 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P3) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4356 |  | 700/710 |  | FORMATION TOP, MD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4356 |  | 860/870 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4356 |  | 1040/1045 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-08-09 | 2018-09-08 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-08 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-08-22 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-20
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43332 | 43332.25 | 6 | DRL | PT-UP | DM | DRILLED 8 1/2'' DIRECTIONAL HOLE FROM 4367M TO 4381M IN ROTARY MODE. STOPPED DRILLING DUE TO BHA HRS.
43332.25 | 43332.375 | 3 | DRL | PT-UP | CIR | CIRCULATED TO CLEAN HOLE. ATTEMPTED TO RECORD SURVEY, OBSERVED NO RESPONSE FROM MWD TOOL.
43332.375 | 43332.3854 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED. WELL STATIC.
43332.3854 | 43332.5417 | 3.75 | DRL | PT-UP | POOH | RESUMED POOH. POOH UP TO 3300M. OPEN HOLE CONDITION GOOD.
43332.5417 | 43332.5521 | 0.25 | DRL | PT-UP | FC / PS | FLOW CHECKED. WELL STATIC.
43332.5521 | 43332.8229 | 6.5 | DRL | PT-UP | POOH | POOH TO BHA.
43332.8229 | 43332.8333 | 0.25 | DRL | PT-UP | FC | FLOW CHECKED. WELL STATIC.
43332.8333 | 43333 | 4 | DRL | PT-UP | BHA | CONT'D POOH BHA AND L/DOWN ALL BHA COMPONENTS FOR INSPECTION. FOUND MWD TOOL WASHED OUT. L/DOWN MUD MOTOR + BIT.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43333 | 43333.0625 | 1.5 | DRL | PT-UP | BHA | CONT'D L/DOWN 12 X 6 1/2'' DC'S SINGLE BY SINGLE FROM DERRICK.
43333.0625 | 43333.25 | 4.5 | DRL | PT-UP | BOPT | HELD PJSM. RETRIEVED WEAR BUSHING. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), TDS IBOP, FOSV, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE & LOWER PIPE RAM BOP (5" RAMS) @ 300/8000 PSI FOR 5/10 MIN - OK.
TOTAL |  | 6
FORMATION / LITHOLOGY
OPERATIONS AT 06:00 HRS |  |  | BOP TEST IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | DRILLED 8 1/2" DIRECTIONAL HOLE DOWN TO 4381M IN ROTARY MODE, CIRCULATED TO CLEAN HOLE, FLOW CHECKED, POOH TO SURFACE MEANWHILE L/DOWN ALL BHA COMPONENTS FOR INSPECTION.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | CONTINUE L/DOWN REMAINING BHA FROM DERRICK, PERFORM BOP TEST, P/UP AND M/UP NEW BHA + BIT AND RIH TO RESUME DRILLING.
REMARKS |  |  | RELEASED PBL SUB ON 20-8-2018, DURING BOPT REPLACED DRAWWORKS MOTOR BEARING.
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14