## DDR#244
9
MARI PETROLEUM COMPANY LIMITED
[7 empty] | 'EID MUBARAK' | [13 empty] | Report No. |  | 244
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-22
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4381 / 4183.19 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 27.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4385 / 4186.45 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-08-21 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 14 |  | BHA No. |  |  | 35 | IN (M) |  | 4381 |  | OUT (M) |  |  | STRING (BBL) | 248
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4381 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 660.5
DEPTH, MD (M) | 4381 | 4381 | TVD @ 00:00HR (M) |  | 4183.19 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.23 | 0.0315 |  | PITS (BBL) | 826
MW IN (SG) | 1.68 | 1.68 | DAILY PROGRESS (M) |  |  |  | TYPE |  | SKH616M |  | XP MUD MOTOR |  |  | 6.625 | - |  | 4 1/2 IF |  | 8.22 | 1.1258 |  | ACT. SYS (BBL) | 1734.5
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E244696 |  | FLOAT SUB |  |  | 6.75 | 3 |  | 4 1/2 IF |  | 0.54 | 0.073956 |  | RESV. SYS (BBL) | 597
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M322 |  | STRING STAB |  |  | 8.375 | 2.8125 |  | 4 1/2 IF |  | 2.22 | 0.30404 |  | KILL MUD (BBL) | 600
FL TEMP. °F |  | 156 | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6x14 |  | LOWER SAVER SUB |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 60 | 59 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4381 |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.43 | 1.2915 |  | TOTAL | 2931.5
PV | 38 | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.11 | 1.2477 |  | DIESEL (LTR)
YIELD POINT | 24 | 24 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 0 |  | 3 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.77 | 3.8033 |  | RIG TANK | 124800
GEL ST. | 11/26 | 11/25 | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 0 - 90 |  | 18 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.7 | 12.4824 |  | CAMP TANK | 22600
WL (ml/30 min.) | 3.4 | 3.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 128 - 217 |  | DRILLING JAR |  |  | 6.25 | 2.8125 |  | 4 1/2 IF |  | 5.99 | 0.82037 |  | CONSUMED | 4850
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.1 | 4.1757 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 147400
ALK (FILT.) | 0.5 | 0.6 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 114600
KCl (mg/l) | 51271.2 | 51480.9 | JAR | 0.8 | STAB - 1 | 0.8 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 114600
CHLORIDES | 24000 | 24000 | 5" HWDPS | 0.8 | STAB - 2 |  | TFA (IN²) |  | 0.9019 | [12 empty] | TOTAL | 400000
CALCIUM | 180 | 200 | 6 1/2" DCS | 0.8 | NMDC |  | HSI | [14 empty] | POB
OIL % | 5.5 | 5.5 | MUD MOTOR | 0.8 | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 287.91 |  |  | MPCL | 3
LUBE % | 2 | 2 | BHA ROT. HRS |  | 0.8 |  | BIT NO. 14 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 14
SOLIDS % | 25.03 | 25.03 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 1.91 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 46
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4280 /4108.96 |  | 42.36 |  | 74.15 |  |  | 0.53 |  | MWD |  | TOTAL | 100
DAILY WELL COST (US$) |  | 56202 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4306 /4128.08 |  | 42.94 |  | 74.76 |  |  | 0.82 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15552154 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4336 /4150.09 |  | 42.69 |  | 75.52 |  |  | 0.57 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 86.17% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER |  |  |  | 4368 /4173.61 |  | 42.69 |  | 78.61 |  |  | 1.96 |  | MWD |  | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4383 |  | 700/700 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4383 |  | 870/880 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4383 |  | 1080/1090 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-08-09 | 2018-09-08 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-09-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-21
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43333 | 43333.0625 | 1.5 | DRL | PT-UP | BHA | CONT'D L/DOWN 12 X 6 1/2'' DC'S SINGLE BY SINGLE FROM DERRICK.
43333.0625 | 43333.3125 | 6 | DRL | PT-UP | BOPT | HELD PJSM. RETRIEVED WEAR BUSHING. M/UP TEST PLUG ASSY & SET TEST PLUG INSIDE 11" THS. FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP, ROTARY HOSE & STANDPIPE @ 300/5000 PSI FOR 5/10 MIN - OK. P/TESTED UPPER VARIABLE PIPE RAM BOP (4.5" - 7"), TDS IBOP, FOSV, HCR VALVES, MANUAL VALVES @ KILL LINE/CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE & LOWER PIPE RAM BOP (5" RAMS) & BLIND / SHEAR RAM BOP @ 300/8000 PSI FOR 5/10 MIN - OK. RACKED BACK 2X5" HWDPs. SET WEAR BUSHING. L/DOWN TEST PLUG ASSEMBLY.
43333.3125 | 43333.3958 | 2 | DRL | PT-UP | BHA | M/UP 8.5"TC BIT+MUD MOTOR+ S.STAB+ SPSA. ADJUSTED ABH TO 1.5 DEGREE. SCRIBED TOOL FACE. SET SLIM PULSE INTO SPSA. FUNCTION TESTED MWD TOOL. WORKING GOOD.RECORDED 600-620 PSI SPP @ 320 GPM.
43333.3958 | 43333.5 | 2.5 | DRL | PT-UP | BHA | L/DOWN 8.5" TC BIT.M/UP NEW 8.5" PDC BIT(NOV-SKH616M-E244696--6X14 JETS) WITH MOTOR & RIH AS PER BHA DOWN TO 287 M. DURING RIH P/UP 3X6.5''DC+24X5" HWDPS & 6.5 D.JAR FROM CAT WALK SINGLE BY SINGLE. DRIFTED & WASHED ALL BHA MEMBERS.
43333.5 | 43333.9583 | 11 | DRL | PT-UP | RIH | RIH DOWN TO 4356M. FILLED UP STRING EVERY 15 STANDS.
43333.9583 | 43334 | 1 | DRL | PT-UP | RW | PRECAUTIONARY WASHED/REAMED DOWN FROM 4356M TO 4373M. OBSERVED HARD REAMING AT 4373M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43334 | 43334.0625 | 1.5 | DRL | PT-UP | RW | CONT'D REAMED DOWN FROM 4373M TO BTM AT 4381M. OBSERVED FREQUENT ROTARY STALLING WHILE REAMING.( TRQ LIMIT SET @ 16 KFP).
43334.0625 | 43334.25 | 4.5 | DRL | PT-UP | DM | RESUMED DRILLING AFTER BROKE IN THE BIT. DRILLED 8 1/2'' DIRECTIONAL HOLE FROM 4381M TO 4385M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA
OPERATIONS AT 06:00 HRS |  |  | DRILLING 8 1/2'' DIRECTIONAL HOLE IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | L/DOWN REMAINING BHA FROM DERRICK, PERFORMED BOP TEST, P/UP AND M/UP NEW BHA +BIT AND RIH TO 4356M. REAMED DOWN FROM 4356M TO 4373M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | REAM DOWN TO BOTTOM AT 4381M, DRILL AHEAD 8 1/2'' DIRECTIONAL HOLE.
REMARKS |  |  | MARKED TOP OF KULDANA @3776m MD/3738m TVD..
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14