## DDR#244
9
MARI PETROLEUM COMPANY LIMITED
[6 empty] | PAKISTAN ZINDABAD | [15 empty] | Report No. |  | 244
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [6 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 01/03/2020 0:00
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [6 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [6 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | SAIFULLAH TURK/ HAMZA MEHMOOD |  |  | MD/TVD @ 00:00HRS: |  | 5045 | 5045 | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 243.9792 |  |  |  | 242.9
RIG REP.: |  | JAVED MUGHAL / KHALID M GILANI |  |  | MD/TVD @ 06:00HRS: |  | 5045 | 5045 | [12 empty] | 234.5 (D/Hole) + 8.4 (Liner) + 1.08 (Testing) |  |  |  | 1.0792
2020-01-02 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | PERFLEX MUD |  | HOLE SIZE (IN) |  |  |  | RUN NO. |  |  | 46 |  | BHA NO. |  |  | 59 | IN (M) |  |  |  | OUT (M) |  |  | STRING (BBL) | 269
CHECK TIME | 11:00 | 22:00 | MD @ 00:00HR (M) |  |  |  | BIT NO. |  |  | 20RR1 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH (M) | WT. (TON) |  | ANNULUS (BBL) | 732
DEPTH, MD (M) |  |  | TVD @ 00:00HR (M) |  |  |  | SIZE (IN) |  |  | 6 |  | PDC BIT |  |  | 6 |  |  | 3 1/2 REG |  | 0.2 | 0.013874 |  | PITS (BBL) | 678
MW IN (SG) | 1.85 | 1.5 | DAILY PROGRESS (M) |  |  |  | MANUFACTURER |  |  | SMITH |  | BIT SUB |  |  | 4.75 | 2 |  | 3 1/2 IF |  | 1.07 | 0.074227 |  | ACT. SYS (BBL) | 1679
MW OUT (SG) |  | 1.5 | INST. ROP (M/HR) |  |  |  | TYPE |  |  | MDSI613 |  | 15 X DC's |  |  | 4.75 | 2.0625 |  | 3 1/2 IF |  | 137.35 | 9.5282 |  | RESV. SYS (BBL) | 1317
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | SERIAL NO. |  |  | JP2216 |  | D.JAR |  |  | 4.75 | 2.25 |  | 3 1/2 IF |  | 9.21 | 0.63891 |  | KILL MUD (BBL) | 340
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | IADC CODE |  |  |  |  | 3 X DC's |  |  | 4.75 | 2.125 |  | 3 1/2 IF |  | 27.29 | 1.0266 |  | KILL MW (SG) | 2.28
µ FUNNEL (SEC) | 73 | 80 | AVG. RPM SURFACE |  |  |  | NOZZLES (1/32") |  |  | 3 X 12 |  | 18 X HWDP |  |  | 3.5 | 2.25 |  | 3 1/2 IF |  | 169.8 | 6.3876 |  | TOTAL | 2996
PV | 43 | 33 | AVG. RPM DOWNHOLE |  |  |  | DEPTH IN (M) |  |  |  |  | 18 X DP's |  |  | 3.5 |  |  | 3 1/2 IF |  | 171.72 | 3.9035 |  | DIESEL (LTR)
YIELD POINT | 28 | 36 | FLOWRATE (GPM) |  |  |  | DEPTH OUT (M) | [15 empty] | RIG TANK | 103498
GEL ST. | 10/13 | 15/20 | PRESSURE (PSI) |  |  |  | METERAGE (M) | [15 empty] | CAMP TANK | 13344
WL (ml/30 min) | 4.2 | 4.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM SURF. | [15 empty] | CONSUMED | 5823
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | RPM BTM. | [15 empty] | RECEIVED | 23812
ALK (MUD) | 0.5 | 0.4 | STRING WT. (TON) - ROT |  |  |  | WOB (TON) | [15 empty] | TOTAL | 116842
ALK (FILT.) | 0.4/1.2 | 0.3/0.8 | PICK-UP WT. (TON) |  |  |  | AVG. ROP (M/HR) | [15 empty] | WATER (LTR)
pH | 10 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | BIT ROT HRS. | [15 empty] | RIG STORAGE | 532732
MAX SHIELD % | 2.5 | 1.5 | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | K-REVS IN 24 HRS | [15 empty] | CAMP STORAGE | 77000
KCl (%) | 5.5 | 3 | TOOLS | ROT HRS | TOOLS | ROT HRS | CUMM. K-REVS | [15 empty] | CONSUMED | 107071
KCl (mg/l) | 57201 | 33367.3 | JAR | 10.33 | STAB - 1 |  | ANN. VEL. (M/MIN) | [15 empty] | RECEIVED | 128400
CHLORIDES (mg/l) | 31000 | 18000 | 3.5" HWDPS | 10.33 | STAB - 2 |  | JET VELOCITY (M/SEC) | [15 empty] | DRL WASTE | 20000
HARDNESS (mg/l) | 340 | 340 | 4.75" DCS | 10.33 | STAB - 3 |  | TFA (IN²) |  |  | 0.331 | [12 empty] | POB
PENETREX % | 1.5 | 1.5 |  |  |  |  | HSI |  |  |  |  | TOTAL LENGTH (M) | [7 empty] | 516.64 |  |  | MPCL | 6
MAX GUARD % | 1.5 | 0.7 | DAILY BHA ROT. HRS |  | 0.23 |  | DULL CODE |  |  | (I-O-D-L-B-G-O-R) |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 32
SOLIDS % | 40.41 | 23.9 | DAILY ON BOTTOM HRS |  |  |  | BIT NO. |  |  |  |  | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY
M.B.T. (lb/bbl) | 5 | 7 | DAILY CIRC. HRS |  | 6.46 | [6 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 51
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 5
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 3 x 140 |  |  | 30" CONDUCTOR |  |  |  | 37 | 4911 |  | 2.2 |  | 257.25 |  |  |  |  | MWD |  | TOTAL | 118
DAILY WELL COST (US$) |  | 34289 | SHAKER-2 | 3 x 140 |  |  | 20" SURFACE / K-55, 133# |  |  |  | 579 | 4938 |  | 1.66 |  | 232.4 |  |  |  |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 17730740 | SHAKER-3 | 3 x 120 |  |  | 13 5/8" X 13 3/8" (P-110, 88.2/72) |  |  |  | 2419 | 4967 |  | 0.96 |  | 208.88 |  |  |  |  | MWD |  | LAST CSG SIZE
% OF AFE SPENT |  | 89.07% | MUD CLEANER | 3 x 170 |  |  | 9 5/8'' (VM140HC / VM 150) |  |  |  | 4549 | 4995 |  | 1.22 |  | 159.31 |  |  |  |  | MWD |  | FIT (EMW)
[7 empty] | 7'' LINER (VM140HC / 32) |  |  |  | 4496 - 4996
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [9 empty] | SLOW CIRCULATION RATE (1.85SG) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE |  | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PSI (P1/P3) |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | CHINA | 13.625 | 10000 | P-1 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 30 | [5 empty] | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | CHINA | 13.625 | 10000 | P-2 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 40 | [5 empty] | KAMLIAL | 1245/1245
FIRE DRILL | 2019-12-12 | 2020-01-11 | BLIND RAMS | CHINA | 13.625 | 10000 | P-3 - F-1600HL |  | 5.5 |  | 12" | 5555 | 97% |  | 0.0855 |  | 50 | [5 empty] | MURREE / KULD | 1416/1416
PIT DRILL | 2019-08-26 | 2019-09-25 | LOWER RAMS | CHINA | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | CHORGALI | 4576/4576
KICK DRILL | 2019-11-10 | 2019-12-10 | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | SAKESAR | 4667/4667
TRIP DRILL | 2019-12-12 | 2020-01-11 | LAST BOP TEST DATE |  | 2020-01-02 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | 0 | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | NAMMAL | 4756/4756
STRETCHER DRILL | 2019-12-13 | 2020-01-12 | NEXT BOP TEST DATE |  | 2020-01-16 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | 0 | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | PATALA | 4790/4790
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-02
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43832 | 43832.2083 | 5 | TEST | PT-P | BOPT | FLUSHED BOP STACK WITH WATER. P/TESTED ANNULAR BOP @ 500/4500 PSI FOR 5/10 MIN - OK. P/TESTED ROTARY HOSE & STANDPIPE MANIFOLD @ 500/6000 PSI FOR 5/10 MIN - OK. P/TESTED BOP; UPPER VARIABLE PIPE RAMS (2 7/8" - 5") WITH 3 1/2'' DP, LOWER PIPE RAMS WITH 5'' DP, BLIND RAMS, HYD & MANUAL IBOP, FOSV, HCR & MANUAL VALVES @ KILL & CHOKE LINE, CHOKE MANIFOLD MASTER VALVE, CO-FLEXIP HOSE @ 500/9000 PSI FOR 5/10 MIN - OK. INSTALLED WEAR BUSHING & L/D PLUG ASSY.
43832.2083 | 43832.2917 | 2 | TEST | PT-P | BHA | P/UP AND M/UP USED 6'' PDC BIT + BIT SUB. RIH AS PER BHA DOWN TO 516M
43832.2917 | 43832.6771 | 9.25 | TEST | PT-P | RIH | CONT'D RIH. RIH DOWN TO 4993M.
43832.6771 | 43832.6875 | 0.25 | TEST | PT-P | SM | PJSM PRIOR TO DISPLACEMENT.
43832.6875 | 43832.9479 | 6.25 | TEST | PT-P | CIR | PUMPED 40 BBLS LOW VIS PILL AS SPACER & STARTED DISPLACING HEAVIER MUD : 1.85 SG WITH LIGHTER MUD ; 1.50 SG. KEPT CIRCULATING TILL MUD COLUMN HOMOGENIZED ; MUD WT IN /OUT = 1.50 SG. SECURED RETURN MUD.
43832.9479 | 43832.9583 | 0.25 | TEST | PT-P | SM | HELD PJSM, HOOKED UP DOWEL LINES.
43832.9583 | 43832.9792 | 0.5 | TEST | PT-P | P/T | FLUSHED DOWEL LINES WITH FRESH WATER. CLOSED LO-TORQUE VALVE. P/TESTED DOWEL LINES AT 500/5000 PSI, HELD FOR 10MINS OK.
43832.9792 | 43833 | 0.5 | TEST | PT-P | CT | OPENED LO-TORQUE VALVE, CLOSED BOP (UPR). INCREASED PRESSURE GRADUALLY IN INCREMENTS OF 500 PSI & P/ TESTED 7'' LINER @ 4000 PSI. HELD FOR 10 MINS, OK.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2020-01-03
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43833 | 43833.0104 | 0.25 | TEST | PT-P | FC | FLOW CHECKED - WELL STATIC.
43833.0104 | 43833.0521 | 1 | TEST | PT-P | SP | SPOTTED 60 BBL HV PILL PRIOR POOH.
43833.0521 | 43833.25 | 4.75 | TEST | PT-P | POOH | POOH FROM 4993M TO 3166M.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | PATALA / LIMESTONE, SHALE
OPERATIONS AT 06:00 HRS |  |  | POOH IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONDUCTED BOPT AS PER POLICY, RIH WITH 6'' USED PDC + SLICK BHA TO 4993M, DISPLACED MUD AND CONDITIONED SAME, P/TESTED 7'' LINER AT 4000PSI.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | SPOT 60 BBL H-V PILL, POOH TO SURFACE, WHILE POOH L/DOWN ADDITIONAL 5'' DP'S SGL BY SGL FROM CATWALK, DST COMMENCEMENT.
REMARKS
Formulas:
MIRAJ-1 = [PERFLEX MUD]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14