## DDR#245
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 245
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-23
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4404 / 4200.08 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 28.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 23
2018-08-22 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 14 |  | BHA No. |  |  | 35 | IN (M) |  | 4381 |  | OUT (M) |  |  | STRING (BBL) | 249
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4404 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 659.59
DEPTH, MD (M) | 4397 | 4404 | TVD @ 00:00HR (M) |  | 4200.08 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.23 | 0.0315 |  | PITS (BBL) | 869
MW IN (SG) | 1.72 | 1.76 | DAILY PROGRESS (M) |  | 23 |  | TYPE |  | SKH616M |  | XP MUD MOTOR |  |  | 6.625 | - |  | 4 1/2 IF |  | 8.22 | 1.1258 |  | ACT. SYS (BBL) | 1777.59
MW OUT (SG) |  |  | INST. ROP (M/HR) |  | 2.01 |  | SERIAL NO. |  | E244696 |  | FLOAT SUB |  |  | 6.75 | 3 |  | 4 1/2 IF |  | 0.54 | 0.073956 |  | RESV. SYS (BBL) | 539
ECD (SG) |  | 1.83 | AVG. ROP (M/HR) |  | 2.06 |  | IADC CODE |  | M322 |  | STRING STAB |  |  | 8.375 | 2.8125 |  | 4 1/2 IF |  | 2.22 | 0.30404 |  | KILL MUD (BBL) | 600
FL TEMP. °F | 157 | 157 | AVG. WOB (TON) |  | 3.5 |  | NOZZLES |  | 6x14 |  | LOWER SAVER SUB |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) | 60 | 63 | AVG. RPM SURFACE |  | 45 |  | DEPTH IN (M) |  | 4381 |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.43 | 1.2915 |  | TOTAL | 2916.59
PV | 34 | 39 | AVG. RPM DOWNHOLE |  | 165 |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.11 | 1.2477 |  | DIESEL (LTR)
YIELD POINT | 25 | 26 | FLOWRATE (GPM) |  | 425 |  | METERAGE (M) |  | 23 |  | 3 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.77 | 3.8033 |  | RIG TANK | 117800
GEL ST. | 16/26 | 15/29 | PRESSURE (PSI) |  | 3000-3350 |  | RPM SURF. |  | 0 - 90 |  | 18 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.7 | 12.4824 |  | CAMP TANK | 21950
WL (ml/30 min.) | 3.4 | 3.5 | TORQ. ON-BTM (KLB-FT) |  | 8-10 |  | RPM BTM. |  | 128 - 217 |  | DRILLING JAR |  |  | 6.25 | 2.8125 |  | 4 1/2 IF |  | 5.99 | 0.82037 |  | CONSUMED | 7650
CT ( in/32) | 1 | 1 | TORQ. OFF-BTM (KLB-FT) |  | 5-8 |  | WOB (TON) |  | 2-10 |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.1 | 4.1757 |  | RECEIVED
ALK (MUD) | 0.4 | 0.4 | STRING WT. (TON) - ROT |  | 144 |  | AVG. ROP (M/HR) |  | 2.0591 | [12 empty] | TOTAL | 139750
ALK (FILT.) | 0.5 | 0.5 | PICK-UP WT. (TON) |  | 185 |  | BIT ROT HRS. |  | 11.17 | [12 empty] | WATER (LTR)
PH | 9.5 | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  | 110.12 | [12 empty] | RIG STORAGE | 300000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  | 110.12 | [12 empty] | CAMP STORAGE | 35000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  | 66.5 | [12 empty] | CONSUMED | 95000
KCl (mg/l) | 50908.9 | 50527.6 | JAR | 17.08 | STAB - 1 | 17.08 | JET VELOCITY (M/SEC) |  | 46.2 | [12 empty] | RECEIVED | 30000
CHLORIDES | 23500 | 23300 | 5" HWDPS | 17.08 | STAB - 2 |  | TFA (IN²) |  | 0.9019 | [12 empty] | TOTAL | 335000
CALCIUM | 180 | 200 | 6 1/2" DCS | 17.08 | NMDC |  | HSI |  | 1.3 | [12 empty] | POB
OIL % | 5.4 | 5 | MUD MOTOR | 17.08 | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 287.91 |  |  | MPCL | 3
LUBE % | 2 | 2 | BHA ROT. HRS |  | 17.08 |  | BIT NO. 14 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 14
SOLIDS % | 26.17 | 27.08 | ON BOTTOM HRS |  | 11.17 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY | 4
M.B.T. | 10 | 10 | CIRC. HRS |  | 25.74 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 44
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 8
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4306 /4128.08 |  | 42.94 |  | 74.76 |  |  | 0.82 |  | MWD |  | TOTAL | 98
DAILY WELL COST (US$) |  | 52153 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4336 /4150.09 |  | 42.69 |  | 75.52 |  |  | 0.57 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15604307 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4368 /4173.61 |  | 42.69 |  | 78.61 |  |  | 1.96 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 86.46% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4385 |  | 850/850 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4385 |  | 1025/1025 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4385 |  | 1225/1250 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-08-09 | 2018-09-08 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-09-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-22
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43334 | 43334.0625 | 1.5 | DRL | PT-UP | RW | CONT'D REAMED DOWN FROM 4373M TO BTM AT 4381M. OBSERVED FREQUENT ROTARY STALLING WHILE REAMING.( TRQ LIMIT SET @ 16 KFP).
43334.0625 | 43334.2812 | 5.25 | DRL | PT-UP | DM | RESUMED DRILLING AFTER BROKE IN THE BIT. DRILLED 8 1/2'' DIRECTIONAL HOLE IN ROTARY MODE FROM 4381M TO 4387M.
43334.2812 | 43334.4271 | 3.5 | DRL | PT-UP | DM | DRILLED IN SLIDE MODE FROM 4387M TO 4392M
43334.4271 | 43334.4792 | 1.25 | DRL | PT-UP | DM | DRILLED IN ROTARY MODE FROM 4392M TO 4397 M.
43334.4792 | 43334.6042 | 3 | DRL | PT-UP | DM | DRILLED IN SLIDE MODE FROM 4397M TO 4402.
43334.6042 | 43334.6562 | 1.25 | DRL | NPT-UP | STK | DURING PICK UP FROM 4402 (AFTER SLIDE) TIGHT HOLE OBSERVED FROM 4402 M TO 4399M. UNABLE TO ROTATE STRING.ATTEMPTED TO CLEAR WITH RECIPROCATION, FAILED. STRING GOT STUCK AT 4399M (BIT DEPTH). WORKED ON STUCK STRING. ESTABLISHED STRING ROTATION WITH TORQUE & OVER PULL. PULLED BACK TO 4382 M WITH BACK REAMING.STRING STALLED SEVERAL TIMES.MAXIMUM OVER PULL APPLIED 40 TONS
43334.6562 | 43334.9375 | 6.75 | DRL | NPT-UP | CIR | CIRCULATED AT 4382M & INCREASED MUD SP.GR FROM 1.68 SG TO 1.76 SG. RECIPROCATED STRING DURING CIRCULATION.
43334.9375 | 43334.9583 | 0.5 | DRL | NPT-UP | RW | REAMED DOWN FROM 4382M TO BTM AT 4402M.
43334.9583 | 43335 | 1 | DRL | PT-UP | DM | RESUMED DRILLING. DRILLED 8 1/2'' DIRECTIONAL HOLE IN ROTARY MODE FROM 4402M TO 4404M.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-23
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43335 | 43335.1979 | 4.75 | DRL | PT-UP | DM | CONT'D DRILLING AHEAD 8 1/2'' DIRECTIONAL HOLE FROM 4404M TO 4412M.
43335.1979 | 43335.25 | 1.25 | DRL | NPT-UP | STK | DURING WASHING UP AFTER STAND DOWN, OBSERVED SPP SHOT TO 4200 PSI, STOPPED PUMPS MEANWHILE PRESSURE TRAPPED @ 4200PSI. STRING GOT STUCK AT 4407M. ATTEMPTED TO CLEAR WITH RECIPROCATION, FAILED. TRIED TO ESTABLISH ROTATION, NO SUCCESS. BLED OFF SPP, WORKED ON STUCK STRING WITH COMBINATION OF OVER PULL & TORQUE, OBSERVED JAR NOT OPERATING. TRIED TO ESTABLISH CIRCULATION, NO SUCCESS. MAX. O/PULL APPLIED 70 TONS. MAX SLACK OFF 50 TONS. WORK ON STUCK STRING IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | WORK ON STUCK STRING IN PROGRESS.
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CONT'D REAM DOWN TO BTM AT 4381M, DRILLED AHEAD 8 1/2'' DIRECTIONAL HOLE FROM 4381M TO 4402M IN ROTARY/SLIDE MODE, DURIND P/UP AFTER SLIDE GOT STRING STUCK, WORKED ON STRING AND RELEASED SAME, P/BACK TO 4382M WITH BACK REAMING, CIRCULATED AND INCREASED M.WT FROM 1.68SG TO 1.76SG, REAMED DOWN TO BTM AND RESUMED DRILLING, DRILLED DOWN TO 4404M.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | DRILL AHEAD 8 1/2'' DIRECTIONAL HOLE.
REMARKS
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14