## DDR#247
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 247
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-25
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 30.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-08-24 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 14 |  | BHA No. |  |  | 35 | IN (M) |  | 4381 |  | OUT (M) |  |  | STRING (BBL) | 249
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4412 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 665.97
DEPTH, MD (M) |  | 4412 | TVD @ 00:00HR (M) |  | 4206.22 |  | MANUFACTURER |  | NOV |  | PDC BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.23 | 0.0315 |  | PITS (BBL) | 877
MW IN (SG) |  | 1.79 | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | SKH616M |  | XP MUD MOTOR |  |  | 6.625 | - |  | 4 1/2 IF |  | 8.22 | 1.1258 |  | ACT. SYS (BBL) | 1786
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E244696 |  | FLOAT SUB |  |  | 6.75 | 3 |  | 4 1/2 IF |  | 0.54 | 0.073956 |  | RESV. SYS (BBL) | 684
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M322 |  | STRING STAB |  |  | 8.375 | 2.8125 |  | 4 1/2 IF |  | 2.22 | 0.30404 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6x14 |  | LOWER SAVER SUB |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4381 |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.43 | 1.2915 |  | TOTAL | 2970
PV |  | 38 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.11 | 1.2477 |  | DIESEL (LTR)
YIELD POINT |  | 26 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 31 |  | 3 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.77 | 3.8033 |  | RIG TANK | 105500
GEL ST. |  | 14/28 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 18 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 167.7 | 12.4824 |  | CAMP TANK | 20650
WL (ml/30 min.) |  | 3.4 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | DRILLING JAR |  |  | 6.25 | 2.8125 |  | 4 1/2 IF |  | 5.99 | 0.82037 |  | CONSUMED | 5150
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  |  |  | 6 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 56.1 | 4.1757 |  | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) | [14 empty] | TOTAL | 126150
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. | [14 empty] | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS | [14 empty] | RIG STORAGE | 360000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS | [14 empty] | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 148950
KCl (mg/l) |  | 50908.9 | JAR | 21.87 | STAB - 1 | 21.87 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 148950
CHLORIDES |  | 23500 | 5" HWDPS | 21.87 | STAB - 2 |  | TFA (IN²) |  | 0.9019 | [12 empty] | TOTAL | 400000
CALCIUM |  | 200 | 6 1/2" DCS | 21.87 | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR | 21.87 | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 287.91 |  |  | MPCL | 4
LUBE % |  | 2 | BHA ROT. HRS |  | 21.87 |  | BIT NO. 14 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 20 |  |  | MPCL SERV | 19
SOLIDS % |  | 28.09 | ON BOTTOM HRS |  | 15.93 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 16 |  |  | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS |  | 30.57 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 49
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 10
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 24
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4306 /4128.08 |  | 42.94 |  | 74.76 |  |  | 0.82 |  | MWD |  | TOTAL | 110
DAILY WELL COST (US$) |  | 34341 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4336 /4150.09 |  | 42.69 |  | 75.52 |  |  | 0.57 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15680989 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4368 /4173.61 |  | 42.69 |  | 78.61 |  |  | 1.96 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 86.88% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4385 |  | 850/850 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4385 |  | 1025/1025 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4385 |  | 1225/1250 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-08-09 | 2018-09-08 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-09-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-24
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43336 | 43336.0833 | 2 | DRL | NPT-UP | E/C | CHECKED AND CALIBERATED W.FORD W.LINE TOOLS. MEANWHILE CONT'D WORKING ON STUCK STRING.
43336.0833 | 43336.1771 | 2.25 | DRL | NPT-UP | RU | HELD PJSM, R/U W.FORD W.LINE GEARS & TOOLS FOR FPIT.
43336.1771 | 43336.5417 | 8.75 | DRL | NPT-UP | WL | W.FORD W.LINE FPIT JOB CONCLUDED.FOUND STRING 100 % FREE @ 4302.38M.CHECKED CLEARANCE INSIDE STRING DOWN TO 4385M. PULLED OUT FPIT TO SURFACE.
43336.5417 | 43336.6458 | 2.5 | DRL | NPT-UP | OTH | ARRANGED X-OVER FOR RECOVERY OF SLIM PULSE ON W.FORD WIRE LINE. MEANWHILE WORKED ON STUCK STRING.
43336.6458 | 43336.6667 | 0.5 | DRL | NPT-UP | RU | R/UP FISHING TOOL ON WIRE LINE TO RETRIEVE MWD TOOL (SLIM PULSE).
43336.6667 | 43337 | 8 | DRL | NPT-UP | WL | RIH SLIM PULSE FISHING TOOL ON WIRE LINE INSIDE STRING. ENGAGED MWD TOOL & UNSEATED WITH 1000 POUNDS OVER PULL. POOH IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-25
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43337 | 43337.0625 | 1.5 | DRL | NPT-UP | WL | POOH FISHING TOOL + MWD TOOL (SLIM PULSE) ON WIRE LINE TO SURFACE & L/DOWN SAME .
43337.0625 | 43337.2188 | 3.75 | DRL | NPT-UP | STK | PRE-BACK OFF WORKED ON STUCK STRING.
43337.2188 | 43337.25 | 0.75 | DRL | NPT-UP | RU | HELD PJSM, R/UP STRING SHOT FOR BACK OFF JOB IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | R/UP W.FORD STRING SHOT FOR BACK OFF IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | CHECKED AND CALIBERATED W.FORD FPIT TOOLS, PERFORMED FPIT JOB AS PER PROGRAM, ARRANGED X/OVER FOR MWD FISHING TOOL, PERFORMED WIRE LINE JOB TO RETRIEVE MWD TOOL (SLIM PULSE).
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | POOH FISHING TOOL + FISH (MWD: SLIM PULSE) TO SURFACE, BACK OFF JOB, CIRCULATE, POOH TO SURFACE.
REMARKS |  |  | WEIGHTED UP SURFACE MUD SYSTEM TO 1.80 SG, FISHING ENGR. ARRIVED AT LOCATION ON 24-08-18.
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14