## DDR#25
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 25
DAILY DRILLING REPORT
WELL NAME: |  | MIRAJ-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-29
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2019-05-04 00:30
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5270 / 5270 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 240
MPCL REP.: |  | MASOOD KAMAL / TALHA / AHSEN |  |  | MD/TVD @ 00:00HRS: |  | 2085 / 2085 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 24.9792
RIG REP.: |  | JAVED MUGHAL / KHALID JILANI |  |  | MD/TVD @ 06:00HRS: |  | 2085 / 2085 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2019-05-28 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD DATA / MUD TYPE |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL MODIFIED LIGNO. |  | HOLE SIZE (IN) |  | 17 1/2'' |  | BIT No. |  | 4 |  | BHA No. |  |  | 5 | IN (M) |  | 590 |  | OUT (M) |  |  | STRING (BBL) | 136
CHECK TIME | 14:00 | 23:00 | MD @ 00:00HR (M) |  | 2085 |  | SIZE (IN) |  | 17 1/2'' |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 1905.96
DEPTH, MD (M) | 2085 | 2085 | TVD @ 00:00HR (M) |  | 2085 |  | MANUFACTURER |  | NOV |  | 17 1/2'' PDC BIT |  |  | 17.5 |  |  | 7 5/8 REG |  | 0.36 |  |  | PITS (BBL) | 893
MW IN (SG) | 2.02 | 2.02 | DAILY PROGRESS (M) |  |  |  | TYPE |  | TFH519S |  | PD |  |  | 9 | 5.125 |  | 7 5/8 REG |  | 4.29 | 1.3667 |  | ACT. SYS (BBL) | 2934.96
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E260745 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.76 | 0.24212 |  | RESV. SYS (BBL) | 1144
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | S422 |  | MUD MOTOR (SLEEVE STAB) |  |  | 9.625 | 7 |  | 6 5/8 REG |  | 10.53 | 3.3546 |  | KILL MUD (BBL)
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | ` |  | 3X 18, 2 X 16 |  | X/O |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 1.1 | 0.35043 |  | KILL MW (SG)
µ FUNNEL (SEC) | 64 | 66 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 590 |  | FLOAT SUB |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | TOTAL | 4078.96
PV | 47 | 47 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | ST. STAB |  |  | 17.375 | 3 |  | 7 5/8 REG |  | 2.44 | 0.77732 |  | DIESEL (LTR)
YIELD POINT | 31 | 29 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 1495 |  | LOWER S. SUB |  |  | 9.625 | 3.5 |  | 7 5/8 REG |  | 0.78 | 0.24849 |  | RIG TANK | 118907
GEL ST. | 14/16 | 12/14 | PRESSURE (PSI) |  |  |  | RPM SURF. |  | 40-90 |  | SLIM PULSE |  |  | 9.5625 | 5 |  | 7 5/8 REG |  | 9.27 | 2.9532 |  | CAMP TANK | 25236
WL (ml/30 min) | 6.5 | 6.6 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  | 140-190 |  | UPPER S. SUB |  |  | 9.5625 | 3 |  | 7 5/8 REG |  | 0.67 | 0.21344 |  | CONSUMED | 5745
CT ( in/32) | 2 | 2 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) |  | 5-16 |  | ST. STAB |  |  | 17.375 | 2.9375 |  | 7 5/8 REG |  | 2.37 | 0.75502 |  | RECEIVED
ALK (MUD) | 0.3 | 0.4 | STRING WT. (TON) - ROT |  | 132 |  | AVG. ROP (M/HR) |  | 13.0136 |  | NMDC |  |  | 9 | 3.5 |  | 7 5/8 REG |  | 9.36 | 2.9818 |  | TOTAL | 144143
ALK (FILT.) | 0.2 | 0.3 | PICK-UP WT. (TON) |  | 133 |  | BIT ROT HRS. |  | 114.88 |  | 3 X 9 1/2'' DC |  |  | 9.5 | 3 |  | 7 5/8 REG |  | 27.53 | 8.7703 |  | WATER (LTR)
PH | 9.2 | 9.5 | SLACK-OFF WT. (TON) |  | 130 |  | K-REVS IN 24 HRS |  | 113.63 |  | X/O |  |  | 9.5 | 3 |  | 6 5/8 REG |  | 0.93 | 0.29627 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF CURRENT INHOLE BHA |  |  |  | CUMM. K-REVS |  | 1133.69 |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.34 | 4.0953 |  | CAMP STORAGE | 93500
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) |  |  |  | D. JAR |  |  | 7.9375 | 3.0625 |  | 6 5/8 REG |  | 9.56 | 2.1347 |  | CONSUMED | 54200
KCl (mg/l) | 49574.2 | 51480.9 | JAR | 158.7 | NMDC | 148.69 | JET VELOCITY (M/SEC) |  |  |  | 2 X 8'' DC |  |  | 8 | 2.8125 |  | 6 5/8 REG |  | 18.43 | 4.1154 |  | RECEIVED | 54200
CHLORIDES (mg/l) | 25000 | 25000 | MOTOR | 148.69 | STAB - 1 | 148.69 | TFA (IN²) |  | 1.138 |  | X/O |  |  | 7.3125 | 2.8125 |  | 5 1/2 FH |  | 0.81 | 0.18087 |  | TOTAL | 493500
HARDNESS (mg/l) | 460 | 440 | 9 1/2" DCS | 158.7 | STAB - 2 | 148.69 | HSI |  |  |  | 10 X 5 1/2'' HWDP |  |  | 5.5 | 3.25 |  | 5 1/2 FH |  | 94.38 | 3.4703 |  | POB
SAND % | 0.25 | 0.5 | 8" DCS | 158.7 | SPSA | 148.69 | DULL CODE |  | (I/O/D/L/B/G/O/R) |  | TOTAL LENGTH (M) | [7 empty] | 212.69 |  |  | MPCL | 5
LUBRICANT % |  |  | BHA ROT. HRS |  | 148.69 |  | BIT No. 4 |  |  |  | BHA WT. IN MUD (TON) | [7 empty] | 33 |  |  | MPCL SERV | 31
SOLIDS % | 34.52 | 34.02 | ON BOTTOM HRS |  | 11.29 | [5 empty] | WT. BELOW JAR IN MUD (TON) | [7 empty] | 23 |  |  | SECURITY
M.B.T. (lb/bbl) | 7.5 | 7.5 | CIRC. HRS |  | 19.2 | [5 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 53
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 7
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 25
APPROVED AFE (US$) |  | 19906000 | SHAKER-1 | 1 X 120 | 2 X 120 |  | 30" CONDUCTOR |  |  | 37 | 1953/1953 |  | 0.08 | [6 empty] | MWD |  | TOTAL | 121
DAILY WELL COST (US$) |  | 120106.259 | SHAKER-2 | 1 X 100 | 2 X 100 |  | 20'' SURFACE/ K-55, 133# |  |  | 579 | 1981/1981 |  | 0.11 | [6 empty] | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 2970452.9891 | SHAKER-3 | 1 X 100 | 2 X 100 | [5 empty] | 2011/2011 |  | 0.14 | [6 empty] | MWD |  | LAST CSG SIZE | 20"
% OF AFE SPENT |  | 14.92% | MUD CLEANER | 3 x 120 | [6 empty] | 2039/2039 |  | 0.11 | [6 empty] | MWD |  | FIT (EMW) | 1.95
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) | PRESS.PSI |  |  | KICK TOL. (BBL)
BOP DRILL |  |  | ANNULAR | JX CHINA | 21.25 | 5000 | P-1 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 30 |  | 2064 | 280 / 280 / 280 |  |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JX CHINA | 21.25 | 5000 | P-2 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 40 |  | 2064 | 380 / 380 / 380 |  |  | NAGRI | SURFACE
FIRE DRILL | 2019-05-09 | 2019-06-08 | BLIND RAMS | JX CHINA | 21.25 | 5000 | P-3 - F-1600HL | 6 |  | 12" | 4670 | 97% |  | 0.101 |  | 50 |  | 2064 | 430 / 430 / 430 |  |  | CHINJI | 338/338
PIT DRILL |  |  | LOWER RAMS |  |  |  | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | KAMLIAL | 1245/1245
KICK DRILL |  |  | DIVERTER INFO |  |  |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS |  |  |  |  | LOSSES IN SECTION | [5 empty] | MURREE / KULD | 1416/1416
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2019-05-14 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI
STRETCHER DRILL |  |  | NEXT BOP TEST DATE |  | 2019-06-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-28
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43613 | 43613.6667 | 16 | DRL | NPT-UP | WC | KILLED WELL WITH 1.90 SG KILL MUD IN FIRST STAGE. RECORDED MAX MW OUT = 1.86 SG AFTER WELL KILLING & MIN MW OUT = 1.10 SG DURING WELL KILLING. SHUT-IN & OBSERVED WELL. RECORDED SIDP = 380 PSI & SICP = 380 PSI.
43613.6667 | 43613.875 | 5 | DRL | NPT-UP | WC | WHILE WEIGHTING UP THE MUD, REPEATED SHUT-IN PROCEDURE AND RECORDED SIDPP = 300 PSI & SICP = 300 PSI. ATTEMPTED TO BREAK CIRCULATION THRU CHOKE & OBSERVED SPP INCREASED TO 900 PSI & TRAPPED INSIDE STRING (SUSPECTED BIT NOZZLES PLUGGED). WORKED & UN-PLUGGED NOZLLES.
43613.875 | 43614 | 3 | DRL | NPT-UP | WC | HELD PJSM. WELL KILLING IN SECOND STAGE WITH 2.02 SG KILL MUD IS IN PROGRESS.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2019-05-29
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43614 | 43614.25 | 6 | DRL | NPT-UP | WC | WELL KILLING IN SECOND STAGE WITH 2.02 SG KILL MUD IS IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | MURREE / CLAYSTONE, SANDSTONE, SILTSTONE
OPERATIONS AT 06:00 HRS |  |  | WELL KILLING IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | WELL CONTROL REMAINED IN PROGRESS.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | KILL WELL, OBSERVE WELL, CIRCULATE AND HOMOGENIZE MUD, POOH TO SURFACE.
REMARKS
Formulas:
MIRAJ-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+21