## DDR#253
9
MARI PETROLEUM COMPANY LIMITED
[21 empty] | Report No. |  | 253
DAILY DRILLING REPORT
WELL NAME: |  | DHARIAN-1-ST-1 |  |  | CONTRACTOR / RIG: |  | MDU / RIG MARI-3 | [5 empty] | DATE: (DD-MM-YY HH:MM) | [6 empty] | 2018-08-31
CLASSIFICATION: |  | EXPLORATORY |  |  | R.T. - G.L. ELEV. (M) |  | 10.5 METER | [5 empty] | SPUD DATE: (DD-MM-YY HH:MM) | [6 empty] | 2017-12-21 10:00
BLOCK / COUNTRY: |  | GHAURI BLOCK / PAKISTAN |  |  | PLANNED MD/TVD (M): |  | 5675 / 5110 METER | [5 empty] | PLANNED DAYS (DRY HOLE): | [6 empty] | 215 + |  |  | 130
MPCL REP. (DSV): |  | SAIFULLAH TURK / SYED HAMZA |  |  | MD/TVD @ 00:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAYS SINCE SPUD: | [6 empty] | 216.46 + |  |  | 36.13
RIG REP. (TP): |  | JAVED IQBAL MUGHAL / FAYYAZ MIRANI |  |  | MD/TVD @ 06:00HRS: |  | 4412 / 4206.22 METER | [5 empty] | DAILY PROGRESS @ 00:00HRS: | [6 empty] | 0
2018-08-30 | [6 empty] | (00:00 HRS - 00:00 HRS) 24 HRS DRILLING DATA
MUD TYPE / MUD DATA |  |  | DRILLING PARAMETERS |  |  |  | BIT DATA |  |  |  | BHA INFORMATION (CURRENT IN HOLE) | [10 empty] | MUD VOLUME (BBL)
MUD TYPE | KCL LIGNOSULPHONATE |  | HOLE SIZE (IN) |  | 8.5 |  | BIT NO. |  | 14 |  | BHA No. |  |  | 36 | IN (M) |  | 4302 |  | OUT (M) |  |  | STRING (BBL) | 247
CHECK TIME | 12:00 | 23:59 | MD @ 00:00HR (M) |  | 4412 |  | SIZE (IN) |  | 8.5 |  | COMPONENT DETAILS |  |  | OD (IN) | ID (IN) |  | CONN. |  | LENGTH | WT. (TON) |  | ANNULUS (BBL) | 668
DEPTH, MD (M) |  | 4412 | TVD @ 00:00HR (M) |  | 4206.22 |  | MANUFACTURER |  | NOV |  |  |  |  | FISH | [7 empty] | PITS (BBL) | 884
MW IN (SG) |  | 1.8 | DAILY PROGRESS (M) |  | 0 |  | TYPE |  | SKH616M |  | PDC BIT |  |  | 8.5 | - |  | 4 1/2 REG |  | 0.23 | 0.0315 |  | ACT. SYS (BBL) | 1799
MW OUT (SG) |  |  | INST. ROP (M/HR) |  |  |  | SERIAL NO. |  | E244696 |  | XP MUD MOTOR |  |  | 6.625 | - |  | 4 1/2 IF |  | 8.22 | 1.1258 |  | RESV. SYS (BBL) | 618
ECD (SG) |  |  | AVG. ROP (M/HR) |  |  |  | IADC CODE |  | M322 |  | FLOAT SUB |  |  | 6.75 | 3 |  | 4 1/2 IF |  | 0.54 | 0.073956 |  | KILL MUD (BBL) | 500
FL TEMP. °F |  |  | AVG. WOB (TON) |  |  |  | NOZZLES |  | 6x14 |  | STRING STAB |  |  | 8.375 | 2.8125 |  | 4 1/2 IF |  | 2.22 | 0.30404 |  | KILL MW (SG) | 2
µ FUNNEL (SEC) |  | 60 | AVG. RPM SURFACE |  |  |  | DEPTH IN (M) |  | 4381 |  | LOWER SAVER SUB |  |  | 6.625 | 2.75 |  | 4 1/2 IF |  | 0.6 | 0.082174 |  | TOTAL | 2917
PV |  | 39 | AVG. RPM DOWNHOLE |  |  |  | DEPTH OUT (M) |  |  |  | SLIM PULSE |  |  | 6.625 | 2.8125 |  | 4 1/2 IF |  | 9.43 | 1.2915 |  | DIESEL (LTR)
YIELD POINT |  | 25 | FLOWRATE (GPM) |  |  |  | METERAGE (M) |  | 31 |  | NMDC |  |  | 6.5 | 2.8125 |  | 4 1/2 IF |  | 9.11 | 1.2477 |  | RIG TANK | 122000
GEL ST. |  | 13/27 | PRESSURE (PSI) |  |  |  | RPM SURF. |  |  |  | 3 X 6 1/2" DCS |  |  | 6.5 | 2.75 |  | 4 1/2 IF |  | 27.77 | 3.8033 |  | CAMP TANK | 16750
WL (ml/30 min.) |  | 3.5 | TORQ. ON-BTM (KLB-FT) |  |  |  | RPM BTM. |  |  |  | 5 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 46.5 | 6.3685 |  | CONSUMED | 6650
CT ( in/32) |  | 1 | TORQ. OFF-BTM (KLB-FT) |  |  |  | WOB (TON) | [14 empty] | RECEIVED
ALK (MUD) |  | 0.3 | STRING WT. (TON) - ROT |  |  |  | AVG. ROP (M/HR) |  |  |  | FISHING BHA | [10 empty] | TOTAL | 138750
ALK (FILT.) |  | 0.5 | PICK-UP WT. (TON) |  |  |  | BIT ROT HRS. |  |  |  | 1 X 5" HWDPS |  |  | 5 | 3 |  | 4 1/2 IF |  | 9.33 | 0.69446 |  | WATER (LTR)
PH |  | 9.5 | SLACK-OFF WT. (TON) |  |  |  | K-REVS IN 24 HRS |  |  |  | 6 1/2'' WFD D.JAR |  |  | 6.5 | 2.75 |  | 4 1/2IF |  | 9.92 | 0.73837 |  | RIG STORAGE | 400000
HTHP WL |  |  | ROTATING HRS OF BHA CURRENTLY IN HOLE |  |  |  | CUMM. K-REVS |  |  |  | 6 X 5'' HWDP |  |  | 5 | 3 |  | 4 1/2IF |  | 56.04 | 4.1712 |  | CAMP STORAGE | 40000
HTHP CT |  |  | TOOLS | ROT HRS | TOOLS | ROT HRS | ANN. VEL. (M/MIN) | [14 empty] | CONSUMED | 35000
KCl (mg/l) |  | 50908.9 | JAR |  | STAB - 1 | 0 | JET VELOCITY (M/SEC) | [14 empty] | RECEIVED | 35000
CHLORIDES |  | 23500 | 5" HWDPS |  | STAB - 2 |  | TFA (IN²) |  | 0.9019 | [12 empty] | TOTAL | 440000
CALCIUM |  | 200 | 6 1/2" DCS |  | NMDC |  | HSI | [14 empty] | POB
OIL % |  | 5 | MUD MOTOR |  | SPSA |  | DULL CODE |  | I-O-D-L-B-G-O-R |  | TOTAL LENGTH (M) | [7 empty] | 0 |  |  | MPCL | 3
LUBE % |  | 2 | BHA ROT. HRS |  |  |  | BIT NO. 14 |  |  |  | BHA WT. IN MUD (TON) | [10 empty] | MPCL SERV | 19
SOLIDS % |  | 28.09 | ON BOTTOM HRS | [7 empty] | WT. BELOW JAR IN MUD (TON) | [10 empty] | SECURITY | 4
M.B.T. |  | 10 | CIRC. HRS | [7 empty] | MARGIN OF OVERPULL (TON) | [10 empty] | RIG STAFF | 50
TENTATIVE WELL COST |  |  | SHALE SHAKER DATA |  |  |  | CASING DATA |  |  |  | WELL DEVIATION DATA | [10 empty] | RIG SERV | 12
|  |  | SCREENS | UPPER | LOWER | REMARKS | SIZE / SPECIFICATIONS |  |  | SHOE (M) | MD/TVD(M) |  | INCL. (°) |  | AZIM (°N) |  |  | DLS (°/100FT) |  | REMARKS |  | CATERING | 23
APPROVED AFE (US$) |  | 18049000 | SHAKER-1 | 2 x 120 | 1 x 120 |  | 13 3/8" INTERMEDIATE CSG |  |  | 2354 | 4306 /4128.08 |  | 42.94 |  | 74.76 |  |  | 0.82 |  | MWD |  | TOTAL | 111
DAILY WELL COST (US$) |  | 34601 | SHAKER-2 | 2 x 120 | 1 x 120 |  | 9 5/8" PRODUCTION CSG |  |  | 4532 | 4336 /4150.09 |  | 42.69 |  | 75.52 |  |  | 0.57 |  | MWD |  | WELL CONTROL
COMMULATIVE COST (US$) |  | 15898278 | SHAKER-3 | 2 x 140 | 1 x 120 |  | 9 5/8" CSG WINDOW |  |  | 3312 | 4368 /4173.61 |  | 42.69 |  | 78.61 |  |  | 1.96 |  | MWD |  | LAST CSG SIZE | 9 5/8"
% OF AFE SPENT |  | 88.08% | MUD CLEANER | 2 x 200 + 1 x 200 |  |  | 7" LINER | [14 empty] | FIT (EMW)
QHSE SAFETY DRILLS |  |  | BOP CONFIGURATION |  |  |  | MUD PUMPS DATA | [8 empty] | SLOW CIRCULATION RATE (P1/P2) | [5 empty] | MAASP (PSI)
DESCRIPTION | DATE | NEXT DUE | DESCRIPTION | MAKE | ø (IN) | WP (PSI) | TYPE | LINER |  | STROKE | RATING | EFF% |  | BBL/STK |  | SPM |  | MD (M) |  | PRESS. |  | KICK TOL. (BBL)
BOP DRILL | 2018-08-09 | 2018-08-24 | ANNULAR | JIANGSU XINDE | 13.625 | 10000 | P-1 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 30 |  | 4385 |  | 850/850 |  | FORMATION TOP, MD/TVD (M)
H2S DRILL |  |  | UPPER RAMS | JIANGSU XINDE | 13.625 | 10000 | P-2 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 40 |  | 4385 |  | 1025/1025 |  | CHINJI | 342
FIRE DRILL | 2018-07-21 | 2018-08-20 | BLIND RAMS | JIANGSU XINDE | 13.625 | 10000 | P-3 - F-1600HL | 6 " |  | 12" | 4670 PSI | 97% |  | 0.101 |  | 50 |  | 4385 |  | 1225/1250 |  | KAMLIAL | 1255
PIT DRILL | 2018-07-13 | 2018-08-13 | LOWER RAMS | JIANGSU XINDE | 13.625 | 10000 | CENTRIFUGES DATA |  |  |  | DOWNHOLE FLUID LOSSES | [10 empty] | MURREE | 1445
KICK DRILL | 2018-08-09 | 2018-09-08 | DIVERTER INFO |  | - |  | OPERATING HRS IN LAST 24 HRS |  |  |  | LOSSES IN 24 HRS (BBL) |  |  |  |  | LOSSES IN SECTION (BBL) | [5 empty] | KULDANA | 3776/3738
TRIP DRILL |  |  | LAST BOP TEST DATE |  | 2018-08-21 |  | OPR. HRS OF CENTRIFUGE-1 |  |  |  | MUD LOSSES IN 24 HRS |  |  |  |  | MUD LOSSES | [5 empty] | CHORGALI-1
STRETCHER DRILL | 2018-07-21 | 2018-08-20 | NEXT BOP TEST DATE |  | 2018-09-04 |  | OPR. HRS OF CENTRIFUGE-2 |  |  |  | CMT LOSSES IN 24 HRS |  |  |  |  | CMT LOSSES | [5 empty] | SAKESAR-1
(00:00 - 00:00) 24 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-30
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43342 | 43342.0729 | 1.75 | DRL | NPT-UP | W/L | P/UP STRING AND OBSERVED OVER PULL. WORKED ON STRING BY UPWARD/DOWNWARD JARRING, NO SUCCESS. POOH W.LINE TO SURFACE, L/DOWN TOOL.(FOUND SEVER TOOL FIRED).
43342.0729 | 43342.4479 | 9 | DRL | NPT-UP | STK | M/UP TDS AND STARTED CIRCULATION. CONT'D WORKING ON BREAKING SEVER CONNECTION BY UPWARD / DOWNWARD JARRING. COMBINATION OF TORQUE WITH UPWARD/DOWNWARD JARRING WAS APPLIED. CONT'D WORKING ON BREAKING SEVERED CONNECTION/JOINT. MEANWHILE PREPARED SEVERING TOOL TO SEVERE STRING FROM 4349M.
43342.4479 | 43342.6667 | 5.25 | DRL | NPT-UP | W/L | PJSM. R/UP W.FORD W.LINE & RUN INSIDE STRING SEVERING TOOL. CORRELATED. APPLIED 90 TON TENSION ON STRING.(265 TON HOOK LOAD) FIRED SEVERING TOOL. NO INDICATION OBSERVED AT RIG FLOOR. PULLED OUT W.LINE. FOUND TOOL FIRED & SINKER BAR LEFT INSIDE STRING.
43342.6667 | 43343 | 8 | DRL | NPT-UP | STK | M/UP TDS AND STARTED CIRCULATION. CONT'D WORKING ON BREAKING SEVER CONNECTION BY UPWARD / DOWNWARD JARRING. COMBINATION OF TORQUE WITH UPWARD/DOWNWARD JARRING. KEPT TRYING TO BREAK IT FROM SEVER POINT, NO SUCCESS. DECIDED TO BACK OFF FROM 4339M. PREPARED TOOL MEANWHILE WORKED ON BREAKING SEVER CONNECTION, NO SUCCESS. TRANSMITTED LH TORQUE (14 KFP / 14 TURNS) IN STAGES & RECIPROCATED STRING TO TRANSMIT TORQUE- 185 TONS TO 240 TONS. RELEASED SAME. TORQUED UP STRING WITH RH TORQUE (21 KFP / 21 TURNS). RELEASED TORQUE TO ENSURE STRING TIGHTENED.
TOTAL |  | 24
(00:00 - 06:00) 06 HOURS OPERATIONS SUMMARY | [5 empty] | 2018-08-31
TIME (HH:MM) |  |  | TIME CODING |  |  | DETAILS OF OPERATIONS IN SEQUENCE AND REMARKS
FROM | TO | DURATION | PHASE | CLASS | OPERATION
43343 | 43343.0729 | 1.75 | DRL | NPT-UP | RU | HELD PJSM. ARMED BACK-OFF TOOL, MEANWHILE PREPARED RIG FLOOR FOR BACK OFF JOB.
43343.0729 | 43343.25 | 4.25 | DRL | NPT-UP | W/L | RAN IN W.FORD W.LINE INSIDE STRING TO 4000M. WORKED ON STRING, APPLIED LH TORQUE (14 KFP / 14 TURNS) IN STAGES AND RECIPROCATED STRING TO TRANSMIT TORQUE - 185 TONS TO 240 TONS. CONT'D RAN IN W.LINE INSIDE STRING, OBSERVED OBSTRUCTION @ 4338M. DISCUSSED AND DECIDED TO BACK OFF @ 4331M. CORRELATED AND FIRED BACK OFF TOOL (NO INDICATION OBSERVED AT RIG FLOOR), PULLED OUT W.LINE TO 4200M. P/UP STRING OBSERVED O/PULL. RELEASED LH TORQUE, OBSERVED 13 TURNS ON SURFACE. PULLING OUT W.LINE FROM INSIDE STRING IN PROGRESS.
TOTAL |  | 6
FORMATION / LITHOLOGY |  |  | KULDANA :
OPERATIONS AT 06:00 HRS |  |  | PULLING OUT W.LINE FROM INSIDE STRING IN PROGRESS
24HR SUMMARY (00:00 HRS - 00:00 HRS) |  |  | POOH W.LINE TO SURFACE (FOUND SEVER TOOL FIRED) WORKED ON BREAKING THE SEVER CONNECTION/JOINT, NO SUCCESS, PERFORMED SEVER TOOL JOB TO SEVER AT 4349M, WORKED ON BREAKING THE SEVER CONNECTION/ JOINT, NO SUCCESS. DECIDED TO GO FOR BACK OFF JOB MEANWHILE PREPARING TOOL FOR BACK OFF JOB.
24HR FORECAST (00:00 HRS - 00:00 HRS) |  |  | R/UP W.FORD TOOL, PERFORM BACK OFF JOB, POOH TO SURFACE, RIH WITH OEDP FOR CMT PLUG.
REMARKS |  |  | MANAGER (DRILLING) & AM (DRILLING) ARRIVED ON LOCATION.
Formulas:
DHARIAN-1-ST-1 = [DATE]+30
CONTRACTOR / RIG: = [CONTRACTOR / RIG:, row above]+14